2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [6 empty] | Open Space |  |  | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103427 | Freehold | Subsoil |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/36a | Suffolk Sheet 2 | 105 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [6 empty] | National Trust |  |  | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [9 empty] | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [6 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [6 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [6 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant is continuing its engagement with the statutory undertaker. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant is continuing its engagement with the statutory undertaker as part of ongoing coordination activities. The Applicant maintains its expectation that National Grid Ventures will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK313281 | Freehold |  |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK311340 | Freehold |  |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK311340 | Freehold | Subsoil |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold | Subsoil |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [9 empty] | SU |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/188 | Kent Sheet 2 | 105 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf | [5 empty] | SU and known operational | Agreed and in latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. | 10.2.2026 - Meeting with the Network Rail Agent on the 20 January confirmed that the Heads of Terms are broadly agreed for the Kent section of the project, with the outstanding matter being the OHL Clearance over the active railway crossing. The NR agent confirmed that there was an engineering assessment being undertaken on the Benhall Bridge section of the project, in Suffolk. The NR agent has confirmed that the Framework Agreement between NR and NGET is still in place and that template documents will follow that format. | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 29.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this is being taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. In relation to Protective Provisions, the Applicant is continuing to pursue engagement with the statutory undertaker. It has now received Network Rail’s comments on the Applicant’s proposed protective provisions . Based on those comments, it has made further amendments to the protective provisions which can be seen in the dDCO submitted at Deadline 7. The Applicant has now also received the draft framework agreement which is under review. The Applicant hopes to set up a meeting to discuss the outstanding points with Network Rail soon after Deadline 7. The Applicant believe that Heads of Term will be signed after Deadline 7. The Applicant will provide an update to the Examining Authority in due course. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Heads of Terms negotiations ongoing |  | 2026-09-11
7/21 | Suffolk Sheet 7 | 719 square metres, or thereabouts, of railway, works and land situated to the east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf | [5 empty] | SU and known operational | Agreed and in latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. | 10.2.2026 - Meeting with the Network Rail Agent on the 20 January confirmed that the Heads of Terms are broadly agreed for the Kent section of the project, with the outstanding matter being the OHL Clearance over the active railway crossing. The NR agent confirmed that there was an engineering assessment being undertaken on the Benhall Bridge section of the project, in Suffolk. The NR agent has confirmed that the Framework Agreement between NR and NGET is still in place and that template documents will follow that format. | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 29.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this is being taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. In relation to Protective Provisions, the Applicant is continuing to pursue engagement with the statutory undertaker. It has now received Network Rail’s comments on the Applicant’s proposed protective provisions . Based on those comments, it has made further amendments to the protective provisions which can be seen in the dDCO submitted at Deadline 7. The Applicant has now also received the draft framework agreement which is under review. The Applicant hopes to set up a meeting to discuss the outstanding points with Network Rail soon after Deadline 7. The Applicant believe that Heads of Term will be signed after Deadline 7. The Applicant will provide an update to the Examining Authority in due course. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Heads of Terms negotiations ongoing |  | 2026-09-11
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf | [5 empty] | SU and known operational | Agreed and in latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. | 10.2.2026 - Meeting with the Network Rail Agent on the 20 January confirmed that the Heads of Terms are broadly agreed for the Kent section of the project, with the outstanding matter being the OHL Clearance over the active railway crossing. The NR agent confirmed that there was an engineering assessment being undertaken on the Benhall Bridge section of the project, in Suffolk. The NR agent has confirmed that the Framework Agreement between NR and NGET is still in place and that template documents will follow that format. | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 29.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this is being taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. In relation to Protective Provisions, the Applicant is continuing to pursue engagement with the statutory undertaker. It has now received Network Rail’s comments on the Applicant’s proposed protective provisions . Based on those comments, it has made further amendments to the protective provisions which can be seen in the dDCO submitted at Deadline 7. The Applicant has now also received the draft framework agreement which is under review. The Applicant hopes to set up a meeting to discuss the outstanding points with Network Rail soon after Deadline 7. The Applicant believe that Heads of Term will be signed after Deadline 7. The Applicant will provide an update to the Examining Authority in due course. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Heads of Terms negotiations ongoing |  | 2026-09-11
7/26 | Suffolk Sheet 7 | 944 square metres, or thereabouts, of railway, works and land situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf | [5 empty] | SU and known operational | Agreed and in latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. | 10.2.2026 - Meeting with the Network Rail Agent on the 20 January confirmed that the Heads of Terms are broadly agreed for the Kent section of the project, with the outstanding matter being the OHL Clearance over the active railway crossing. The NR agent confirmed that there was an engineering assessment being undertaken on the Benhall Bridge section of the project, in Suffolk. The NR agent has confirmed that the Framework Agreement between NR and NGET is still in place and that template documents will follow that format. | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 29.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this is being taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. In relation to Protective Provisions, the Applicant is continuing to pursue engagement with the statutory undertaker. It has now received Network Rail’s comments on the Applicant’s proposed protective provisions . Based on those comments, it has made further amendments to the protective provisions which can be seen in the dDCO submitted at Deadline 7. The Applicant has now also received the draft framework agreement which is under review. The Applicant hopes to set up a meeting to discuss the outstanding points with Network Rail soon after Deadline 7. The Applicant believe that Heads of Term will be signed after Deadline 7. The Applicant will provide an update to the Examining Authority in due course. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK346948 | Freehold | Subsoil |  | Category 1 |  | Yes | RR-5020 RR-3978 | RR-5020 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001141 RR-3978 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005065 | REP1A-151 | REP1A-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001478-Nicola-(Ning)-Suzanne-Fulford-Written-summaries-of-oral-submissions-made-at-hearings-held-during-w/c-3-and-w/c-10-November-2025.-S55829990.pdf |  |  |  |  | Not SU | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - Heads of Terms are not being issued given the existing rights. | 13.04.2026 - Heads of Terms are not being issued given the existing rights. | 29.04.2026 - Heads of Terms are not being issued given the existing Deed of Easement held over this land. | The Applicant maintains their position that their existing Deed of Easement for the existing infrastructure provides the required rights for the proposed works. The Applicant will continue to engage with the landowner and their agent in relation to the proposed works as required. | No Heads of Terms Required |  | 2026-09-11
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK346948 | Freehold |  |  | Category 1 |  | Yes | RR-5020 RR-3978 | RR-5020 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001141 RR-3978 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005065 | REP1A-151 | REP1A-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001478-Nicola-(Ning)-Suzanne-Fulford-Written-summaries-of-oral-submissions-made-at-hearings-held-during-w/c-3-and-w/c-10-November-2025.-S55829990.pdf |  |  |  |  | Not SU | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - Heads of Terms are not being issued given the existing rights. | 13.04.2026 - Heads of Terms are not being issued given the existing rights. | 29.04.2026 - Heads of Terms are not being issued given the existing Deed of Easement held over this land. | The Applicant maintains their position that their existing Deed of Easement for the existing infrastructure provides the required rights for the proposed works. The Applicant will continue to engage with the landowner and their agent in relation to the proposed works as required. | No Heads of Terms Required |  | 2026-09-11
5/33 | Suffolk Sheet 5 | 1,379 square metres, or thereabouts, of grassland situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicolas Jon Stuchfield | 32 | SK201392 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4009 RR-2471 | RR-4009 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003679 RR-2471 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100002847 | REP1-230 | REP1-230 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001031-Submission%20to%20Planning%20Inspectorate%20F2BF7676B.docx.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to confirm the already agreed terms within the Heads of Terms. A meeting is scheduled with the landowner and their agent on 23rd February 2026 to discuss landowner specific matters for inclusion in the Heads of Terms. It is understood by the Applicant’s Agent that an agreement should be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. The landowners primary concerns are in relation to construction impacts on their adjoining residential property. Whilst it is expected that the Heads of Terms will be agreed in principle by the end of Examination, further detail is required on the programme of the works in proximity to their residential property before Heads of Terms will be signed. | 3.04.2026 - The landowner's agent is part of the Suffolk agents group with whom we are negotiating template Heads of Term, however most of the outstanding points raised in the template are not specifically relevant to this land interest. Whilst the Applicant believes the template Heads of Terms points raised have now been adequately addressed, a number of amends requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is now awaiting comparable evidence for the land values from the landowner's agent. Whilst it is expected that the Heads of Terms will be agreed in principle by the end of Examination, further detail is required on the works programme in this area before Heads of Terms will be signed by this landowner. The rights being sought from this landowner are over a very small plot, they are underground cable rights only and no works are proposed at surface level, however, the landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant acknowledges the concerns and has sought to provide assurances in our response to the relevant reps submitted. REP2-018 4.1.3.3 of Document 9.34.3 : Applicants Response to Relevant Representations from Affected Landowners. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent to mitigate any potential disruption. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence taking place since the previous update in April 2026. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. To facilitate progress, the Applicant’s Agent and the landowner’s agent have also held weekly telephone discussions regarding the Heads of Terms. On 7 July 2026, the Applicant’s Agent met with the landowner’s agent to discuss the remaining outstanding matters. The principal issues yet to be resolved relate to the commercial terms of the agreement and the landowner’s request for further reassurance regarding the potential impacts of construction activities on their property. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point. As set out at Deadline 6, the Applicant remains committed to working collaboratively with the landowner and their agent to identify and implement appropriate accommodation works to minimise disruption wherever reasonably practicable. The Applicant will continue to engage with the landowner and will provide details of the agreed accommodation measures to the Main Works Contractor to support their delivery during construction. The Applicant considers that any residual and demonstrable disturbance, or diminution in value arising from the Project, can be appropriately addressed through the Compensation Code. The Applicant will continue to engage proactively with the landowner and their agent with a view to reaching a voluntary agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nigel Stewart Daw | 1015 | K77907 | Freehold | Subsoil |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pamela Tile | 1205 |  | Freehold | Subsoil |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.205 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing. | The parties are continuing to progress the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms Agreed | No | 2026-09-10
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pauline Trudy Klauber | 396 | SK162921 | Freehold | Subsoil |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pauline Violet Ellis | 2767 |  | Freehold | Subsoil |  | Category 1 |  | No | [9 empty] | Not SU |  |  |  |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  | excluding mines and minerals | Category 1 | [15 empty] | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Personal Representative to the Estate of Andrew William Johnson | 3589 | K839921 | Freehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement. | The Applicant’s Agent has continued to seek clarification from the landowner’s agent regarding the extent of their instructions from the Executors of the Estate of Andrew Johnson. In response to correspondence dated 9 June 2026, the landowner’s agent confirmed that they remain instructed by the Executors of the Estate. On 14 July and 18th August 2026, the Applicant’s Agent followed up to establish whether the landowner’s agent was in a position to provide feedback on the Heads of Terms and progress negotiations. At the time of writing, no response has been received. The Applicant’s Agent will continue to pursue engagement with a view to progressing discussions and reaching agreement. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169 | Freehold | Subsoil |  | Category 1 | Joe Hearnden, BTF Partnership | Yes | RR-5840 | RR-5840 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006506 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. OR This individual has passed away, see update in AP ref 39 | 10.02.2026 – The Applicant's Agent has been engaging with the landowner’s agent regarding the Heads of Terms and has provided additional clarity on the use of the rights being sought on both the 8th January 2026 and the 22nd January 2026. The landowner’s agent hasn’t yet provided any detailed response on any of the other points in the Heads of Terms which remain outstanding. Their focus has been on the proposed use and commercials. The Applicant’s Agent continues to seek this feedback on the remainder of the terms. The Applicant's Agent responded on 9th February 2026 by email providing comparable evidence for the consideration offered. It is believed an agreement can be reached before the end of Examination. | 10.03.2026 - On the 2nd March 2026 the Applicant's Agent emailed the landowner's agent requesting confirmation that the Heads of Terms, commercial elements aside, are agreed. The Applicant's Agent issued further revised Heads of Terms to the landowners agent on 9th March 2026. No response has been received to date. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On the 9th March 2026, the Applicant's Agent emailed the landowner's agent with a revision of the Heads of Terms which further refined the rights sought to reflect the temporary nature of the access provisions. Additionally, the Applicant's Agent sought confirmation that the terms are in agreed form and requested further evidence regarding the commercial terms. On the 31st March 2026, the Applicant's Agent emailed the landowner's agent to confirm that no response has been received to any communications concerning the landowner since the 6th February 2026. It was confirmed by the Applicant's Agent that in order to address any queries or concerns their client may have, it is essential that the Applicant's Agent is provided with information regarding perceived issues with other aspects of the Heads of Terms including an evidenced position relating to commercial terms. On the 8th April 2026, the Applicant's Agent left a voicemail with the landowner's son requesting a call back to discuss the Heads of Terms. It is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On the 14th April 2026, the Applicant's Agent emailed the landowner's agent confirming that they would be contacting the landowner to discuss the Heads of Terms in the absence of a response. The landowner's agent responded on the 14th April 2026 providing a summary of the landowner's position and requesting a response on three points. The Applicant's Agent is working internally to provide responses to these and make adjustments to the Heads of Terms where possible to reflect their concerns. These points are as follows: 1. The duration of the agreement and the timescales for the required works themselves. 2. The nature of the rights granted versus the actual project requirements 3. The basis for the commercial payment The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent with engagement ongoing since the last update in April 2026. Revised Heads of Terms were issued on 29th May 2026 which addressed their queries in relation to the nature of the rights and the proposed works. The Applicant's Agent had a Teams meeting with the landowner's agent on 26th June 2026. The outstanding points for agreement are the duration of rights being sought and the commercial terms. The Applicant's Agent is awaiting further feedback from the landowner's agent on these points. The latest email exchanges between the Applicant's and landowners agents in relation to the Heads of Terms were on 18th August and 2nd September 2026. The Applicant's Agent has provided dates in September for a Teams meeting with the landowner's agent in order to resolve the outstanding points. The Applicant's Agent will continue to engage with the Landowner's Agent to progress agreements. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track, drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169 | Freehold |  |  | Category 1 | Joe Hearnden, BTF Partnership | Yes | RR-5840 | RR-5840 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006506 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. OR This individual has passed away, see update in AP ref 39 | 10.02.2026 – The Applicant's Agent has been engaging with the landowner’s agent regarding the Heads of Terms and has provided additional clarity on the use of the rights being sought on both the 8th January 2026 and the 22nd January 2026. The landowner’s agent hasn’t yet provided any detailed response on any of the other points in the Heads of Terms which remain outstanding. Their focus has been on the proposed use and commercials. The Applicant’s Agent continues to seek this feedback on the remainder of the terms. The Applicant's Agent responded on 9th February 2026 by email providing comparable evidence for the consideration offered. It is believed an agreement can be reached before the end of Examination. | 10.03.2026 - On the 2nd March 2026 the Applicant's Agent emailed the landowner's agent requesting confirmation that the Heads of Terms, commercial elements aside, are agreed. The Applicant's Agent issued further revised Heads of Terms to the landowners agent on 9th March 2026. No response has been received to date. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On the 9th March 2026, the Applicant's Agent emailed the landowner's agent with a revision of the Heads of Terms which further refined the rights sought to reflect the temporary nature of the access provisions. Additionally, the Applicant's Agent sought confirmation that the terms are in agreed form and requested further evidence regarding the commercial terms. On the 31st March 2026, the Applicant's Agent emailed the landowner's agent to confirm that no response has been received to any communications concerning the landowner since the 6th February 2026. It was confirmed by the Applicant's Agent that in order to address any queries or concerns their client may have, it is essential that the Applicant's Agent is provided with information regarding perceived issues with other aspects of the Heads of Terms including an evidenced position relating to commercial terms. On the 8th April 2026, the Applicant's Agent left a voicemail with the landowner's son requesting a call back to discuss the Heads of Terms. It is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On the 14th April 2026, the Applicant's Agent emailed the landowner's agent confirming that they would be contacting the landowner to discuss the Heads of Terms in the absence of a response. The landowner's agent responded on the 14th April 2026 providing a summary of the landowner's position and requesting a response on three points. The Applicant's Agent is working internally to provide responses to these and make adjustments to the Heads of Terms where possible to reflect their concerns. These points are as follows: 1. The duration of the agreement and the timescales for the required works themselves. 2. The nature of the rights granted versus the actual project requirements 3. The basis for the commercial payment The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent with engagement ongoing since the last update in April 2026. Revised Heads of Terms were issued on 29th May 2026 which addressed their queries in relation to the nature of the rights and the proposed works. The Applicant's Agent had a Teams meeting with the landowner's agent on 26th June 2026. The outstanding points for agreement are the duration of rights being sought and the commercial terms. The Applicant's Agent is awaiting further feedback from the landowner's agent on these points. The latest email exchanges between the Applicant's and landowners agents in relation to the Heads of Terms were on 18th August and 2nd September 2026. The Applicant's Agent has provided dates in September for a Teams meeting with the landowner's agent in order to resolve the outstanding points. The Applicant's Agent will continue to engage with the Landowner's Agent to progress agreements. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/85 | Suffolk Sheet 1 | 113 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 15th May 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. Most recently, the Applicant and their agent had a meeting with the landowner's agent on 7th July 2026. The Applicant is however still waiting for confirmation from the landowner and their agent as to which of the two options for acquisition they would prefer to progress with, freehold acquisition or a long-leasehold interest. It is expected that this confirmation will be received by the end of September 2026 and that the terms will be agreed prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Peter Dickinson | 2754 | SK134793 | Freehold | Subsoil |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | RR-5322 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004967 | REP1-290 REP1A-199 REP3-127 REP4- 174 | REP1-290 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001421-TJ%20Haworth-Culf.pdf REP1A-199 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002028-Cllr%20Haworth-Culf%20SCC%20Cllr%20%209th%20January%202026.pdf REP3-127 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001449-T-J%20Haworth-Culf.pdf REP4-174 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002492-T-J%20Haworth.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since significant amendments were made to the terms and reissued to the landowner’s agent in August 2025. A meeting is scheduled with the landowner and their agent on 11th February 2026 to discuss landowner/holding specific terms . On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the overall Heads of Terms as it relates to all of their landowners. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 11th February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. The landowners primary concerns are in relation to construction impacts on their adjoining residential property. Whilst it is expected that the Heads of Terms will be agreed in principle by Deadline 6, further detail is required on the programme of works in proximity to their residential property before Heads of Terms will be signed. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent beyond the close of Examination to mitigate any potential disruption. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence taking place since the previous update in April 2026. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to progress the Heads of Terms and work through outstanding matters. The Applicant’s Agent met with the landowner’s agent on 7 July 2026 to further advance negotiations. The principal matters remaining for agreement relate to the commercial terms and the landowner’s desire for greater certainty regarding the potential impacts of construction activities on their property. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point. As set out at Deadline 6, the Applicant remains committed to ongoing engagement with the landowner and their agent to identify and implement appropriate accommodation works that will, where practicable, mitigate disruption during construction. The Applicant will also provide details of the accommodation measures proposed by the Main Works Contractor to minimise the effects of the Project on the landowner’s property and operations. The Applicant considers that any residual and proven disturbance, or any diminution in value arising from the exercise of the rights sought, can be appropriately addressed through the Compensation Code. The Applicant will continue to engage proactively with the landowner and their agent with a view to reaching a voluntary agreement prior to the DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Edward Howard | 719 | SK97658 | Freehold | Subsoil |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Peter Murray Mann | 508 | SK350290 | Freehold |  | as owner as per current Land Registry title ownership, pending removal | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Peter Murray Mann | 508 | SK350290 | Freehold |  | as owner as per current Land Registry title ownership, pending removal | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | No Agent Known | Yes | RR-4903 | [8 empty] | Not SU |  |  | No Negotiations |  | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold | Subsoil |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | See PIL No. 378 - Church Commissioners for England - for update on Landlord's Negotiations | No Heads of Terms Required |  | 2026-09-11
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard Bruce Bloomfield | 630 | SK216487 | Freehold | Subsoil |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | No Heads of Terms Required |  | 2026-09-11
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richborough Estates Limited | 718 | K518470 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1466 | RR-1466 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005470 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. The landowner’s agent has only provided feedback on the objection clause. Despite this clause being amended to address their concerns, the Applicant’s Agent hasn’t received any further feedback on the latest version of the Heads of Terms issued – this is still awaited. On 22nd January 2026 the Applicant's Agent sent further email correspondence to the landowner’s agent requesting feedback on the Heads of Terms and any concerns held by the landowner. A request has been made to meet with the landowner’s agent and the landowner to discuss the Heads of Terms in more detail. | 10.03.2026 - On the 4th March 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent and on the 24th of March 2026, the Applicant's Agent proposed to hold a meeting with the landowner and their agent to discuss the revised Heads of Terms. At this point it is not envisaged that the landowner's agent will engage sufficiently to agree the Heads of Terms by the end of Examination but, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with the landowner. | 13.04.2026 - On the 31st March 2026, the Applicant's Agent spoke with the landowner's agent on the phone. Their primary concern is around the prohibition of objection clause in the Heads of Terms. The Applicant's Agent confirmed that this particular clause has been extensively updated and the Heads of Terms re-issued. Despite this, the landowner's agent has stated they are not willing to provide any feedback to the Applicant's Agent regarding additional changes required until after the Examination has closed. On the 9th April 2026, the Applicant's Agent sent a letter to the landowner setting out the position adopted by their agent and encouraging the landowner to engage with the Applicant to resolve any other outstanding issues. | 29.04.2026 - No response has been received to the letter issued to the landowner on the 9th April 2026. In line with previous confirmation that the landowner's agent would not be willing to provide feedback on the Heads of Terms until Examination closes, the Applicant's Agent will continue to engage with the landowner's agent after the close of Examination. | The Applicant’s Agent has continued to make efforts to engage with both the landowner and their agent; however, no substantive responses have been received. On 10 June and 2nd September 2026, the Applicant’s Agent wrote to the landowner’s agent requesting a meeting to discuss and progress the outstanding matters. Despite these attempts, meaningful engagement has not been forthcoming. The Applicant will continue to seek engagement and pursue opportunities to reach agreement, although it is not currently anticipated that the landowner or their agent will engage sufficiently to facilitate a negotiated resolution. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Richborough Estates Limited | 718 | K518470 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1466 | RR-1466 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005470 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. The landowner’s agent has only provided feedback on the objection clause. Despite this clause being amended to address their concerns, the Applicant’s Agent hasn’t received any further feedback on the latest version of the Heads of Terms issued – this is still awaited. On 22nd January 2026 the Applicant's Agent sent further email correspondence to the landowner’s agent requesting feedback on the Heads of Terms and any concerns held by the landowner. A request has been made to meet with the landowner’s agent and the landowner to discuss the Heads of Terms in more detail. | 10.03.2026 - On the 4th March 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent and on the 24th of March 2026, the Applicant's Agent proposed to hold a meeting with the landowner and their agent to discuss the revised Heads of Terms. At this point it is not envisaged that the landowner's agent will engage sufficiently to agree the Heads of Terms by the end of Examination but, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with the landowner. | 13.04.2026 - On the 31st March 2026, the Applicant's Agent spoke with the landowner's agent on the phone. Their primary concern is around the prohibition of objection clause in the Heads of Terms. The Applicant's Agent confirmed that this particular clause has been extensively updated and the Heads of Terms re-issued. Despite this, the landowner's agent has stated they are not willing to provide any feedback to the Applicant's Agent regarding additional changes required until after the Examination has closed. On the 9th April 2026, the Applicant's Agent sent a letter to the landowner setting out the position adopted by their agent and encouraging the landowner to engage with the Applicant to resolve any other outstanding issues. | 29.04.2026 - No response has been received to the letter issued to the landowner on the 9th April 2026. In line with previous confirmation that the landowner's agent would not be willing to provide feedback on the Heads of Terms until Examination closes, the Applicant's Agent will continue to engage with the landowner's agent after the close of Examination. | The Applicant’s Agent has continued to make efforts to engage with both the landowner and their agent; however, no substantive responses have been received. On 10 June and 2nd September 2026, the Applicant’s Agent wrote to the landowner’s agent requesting a meeting to discuss and progress the outstanding matters. Despite these attempts, meaningful engagement has not been forthcoming. The Applicant will continue to seek engagement and pursue opportunities to reach agreement, although it is not currently anticipated that the landowner or their agent will engage sufficiently to facilitate a negotiated resolution. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171,K985109 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171 | Freehold | Subsoil |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The parties are now progressing the drafting of the option agreement, which is expected to be finalised imminently. | Heads of Terms agreed |  | 2026-09-11
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK350196 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowners agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. | Heads of Terms agreed |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 | RR-4651 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003786 | REP1-157 REP1-158 REP1-159 REP1-160 REP1-165 REP5-203 | REP1-157 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001402-RSPB%20Summary.pdf REP1-158 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001399-RSPB.pdf REP1-159 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001400-RSPB%20Appendix.pdf REP1-160 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001401-RSPB%20References.pdf REP1-165 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001414-RSPB%20submission%20in%20advance%20of%20ISH1.pdf REP5-203 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002863-RSPB%20response%20to%20ExQ2.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent received further comments on the Heads of Terms from the landowner’s agent on 21st and 28th January 2026. The final points under discussion are practical points around ongoing management of the RSPB reserve and records of condition ahead of works starting. It is expected that these matters can be resolved swiftly and ahead of Deadline 5. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms on 26th February 2026 that addressed the outstanding points raised at previous meetings and correspondence with the landowner and their agent. It is believed that the Heads of Terms are agreed between the Applicant's Agent and the landowner's agent subject to final approval from the landowner. The landowner is working with the Applicant to agree a Statement of Common Ground which addresses their wider concerns around the Proposed Project. A meeting is being arranged with the landowner's agent ahead of Deadline 6 and it is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The landowner's agent provided comments on the Heads of Terms and feedback from the Suffolk Agents meeting by email on 25th March 2026 and the Applicant's Agent responded to this on 26th March 2026 to set out the Applicant's position. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss Heads of Terms and the feedback from the Suffolk agents meeting on 23rd March 2026. The Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from this meeting on 9th April 2026, which included updates on the soil condition surveys, reinstatement provisions and commercial matters. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026.Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst it is anticipated that an agreement will be reached, the landowner has made the Applicant aware of their internal review and sign off process once Heads of Terms are finalised and this is likely to extend beyond the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms and the Statement of Common Ground. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued by the Applicant's agent on 29th April 2026 and a meeting was subsequently held on 2nd July 2026 to discuss the outstanding matters and progress negotiations. The outstanding matters that were under discussion are have now been agreed between the Applicant's Agent and the landowner's agent and the Applicant's Agent issued final Heads of Terms on 2nd September 2026. It is understood that the landowner's agent requires certain sign off from their client and it is expected that signed Heads of Terms will be received prior to a DCO decision being reached. | Heads of Terms negotiations ongoing |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388,SK354374 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 | RR-4651 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003786 | REP1-157 REP1-158 REP1-159 REP1-160 REP1-165 REP5-203 | REP1-157 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001402-RSPB%20Summary.pdf REP1-158 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001399-RSPB.pdf REP1-159 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001400-RSPB%20Appendix.pdf REP1-160 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001401-RSPB%20References.pdf REP1-165 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001414-RSPB%20submission%20in%20advance%20of%20ISH1.pdf REP5-203 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002863-RSPB%20response%20to%20ExQ2.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent received further comments on the Heads of Terms from the landowner’s agent on 21st and 28th January 2026. The final points under discussion are practical points around ongoing management of the RSPB reserve and records of condition ahead of works starting. It is expected that these matters can be resolved swiftly and ahead of Deadline 5. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms on 26th February 2026 that addressed the outstanding points raised at previous meetings and correspondence with the landowner and their agent. It is believed that the Heads of Terms are agreed between the Applicant's Agent and the landowner's agent subject to final approval from the landowner. The landowner is working with the Applicant to agree a Statement of Common Ground which addresses their wider concerns around the Proposed Project. A meeting is being arranged with the landowner's agent ahead of Deadline 6 and it is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The landowner's agent provided comments on the Heads of Terms and feedback from the Suffolk Agents meeting by email on 25th March 2026 and the Applicant's Agent responded to this on 26th March 2026 to set out the Applicant's position. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss Heads of Terms and the feedback from the Suffolk agents meeting on 23rd March 2026. The Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from this meeting on 9th April 2026, which included updates on the soil condition surveys, reinstatement provisions and commercial matters. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026.Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst it is anticipated that an agreement will be reached, the landowner has made the Applicant aware of their internal review and sign off process once Heads of Terms are finalised and this is likely to extend beyond the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms and the Statement of Common Ground. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued by the Applicant's agent on 29th April 2026 and a meeting was subsequently held on 2nd July 2026 to discuss the outstanding matters and progress negotiations. The outstanding matters that were under discussion are have now been agreed between the Applicant's Agent and the landowner's agent and the Applicant's Agent issued final Heads of Terms on 2nd September 2026. It is understood that the landowner's agent requires certain sign off from their client and it is expected that signed Heads of Terms will be received prior to a DCO decision being reached. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 | RR-4651 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003786 | REP1-157 REP1-158 REP1-159 REP1-160 REP1-165 REP5-203 | REP1-157 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001402-RSPB%20Summary.pdf REP1-158 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001399-RSPB.pdf REP1-159 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001400-RSPB%20Appendix.pdf REP1-160 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001401-RSPB%20References.pdf REP1-165 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001414-RSPB%20submission%20in%20advance%20of%20ISH1.pdf REP5-203 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002863-RSPB%20response%20to%20ExQ2.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent received further comments on the Heads of Terms from the landowner’s agent on 21st and 28th January 2026. The final points under discussion are practical points around ongoing management of the RSPB reserve and records of condition ahead of works starting. It is expected that these matters can be resolved swiftly and ahead of Deadline 5. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms on 26th February 2026 that addressed the outstanding points raised at previous meetings and correspondence with the landowner and their agent. It is believed that the Heads of Terms are agreed between the Applicant's Agent and the landowner's agent subject to final approval from the landowner. The landowner is working with the Applicant to agree a Statement of Common Ground which addresses their wider concerns around the Proposed Project. A meeting is being arranged with the landowner's agent ahead of Deadline 6 and it is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The landowner's agent provided comments on the Heads of Terms and feedback from the Suffolk Agents meeting by email on 25th March 2026 and the Applicant's Agent responded to this on 26th March 2026 to set out the Applicant's position. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss Heads of Terms and the feedback from the Suffolk agents meeting on 23rd March 2026. The Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from this meeting on 9th April 2026, which included updates on the soil condition surveys, reinstatement provisions and commercial matters. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026.Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst it is anticipated that an agreement will be reached, the landowner has made the Applicant aware of their internal review and sign off process once Heads of Terms are finalised and this is likely to extend beyond the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms and the Statement of Common Ground. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued by the Applicant's agent on 29th April 2026 and a meeting was subsequently held on 2nd July 2026 to discuss the outstanding matters and progress negotiations. The outstanding matters that were under discussion are have now been agreed between the Applicant's Agent and the landowner's agent and the Applicant's Agent issued final Heads of Terms on 2nd September 2026. It is understood that the landowner's agent requires certain sign off from their client and it is expected that signed Heads of Terms will be received prior to a DCO decision being reached. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 | RR-4651 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003786 | REP1-157 REP1-158 REP1-159 REP1-160 REP1-165 REP5-203 | REP1-157 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001402-RSPB%20Summary.pdf REP1-158 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001399-RSPB.pdf REP1-159 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001400-RSPB%20Appendix.pdf REP1-160 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001401-RSPB%20References.pdf REP1-165 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001414-RSPB%20submission%20in%20advance%20of%20ISH1.pdf REP5-203 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002863-RSPB%20response%20to%20ExQ2.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent received further comments on the Heads of Terms from the landowner’s agent on 21st and 28th January 2026. The final points under discussion are practical points around ongoing management of the RSPB reserve and records of condition ahead of works starting. It is expected that these matters can be resolved swiftly and ahead of Deadline 5. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms on 26th February 2026 that addressed the outstanding points raised at previous meetings and correspondence with the landowner and their agent. It is believed that the Heads of Terms are agreed between the Applicant's Agent and the landowner's agent subject to final approval from the landowner. The landowner is working with the Applicant to agree a Statement of Common Ground which addresses their wider concerns around the Proposed Project. A meeting is being arranged with the landowner's agent ahead of Deadline 6 and it is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The landowner's agent provided comments on the Heads of Terms and feedback from the Suffolk Agents meeting by email on 25th March 2026 and the Applicant's Agent responded to this on 26th March 2026 to set out the Applicant's position. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss Heads of Terms and the feedback from the Suffolk agents meeting on 23rd March 2026. The Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from this meeting on 9th April 2026, which included updates on the soil condition surveys, reinstatement provisions and commercial matters. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026.Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst it is anticipated that an agreement will be reached, the landowner has made the Applicant aware of their internal review and sign off process once Heads of Terms are finalised and this is likely to extend beyond the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms and the Statement of Common Ground. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued by the Applicant's agent on 29th April 2026 and a meeting was subsequently held on 2nd July 2026 to discuss the outstanding matters and progress negotiations. The outstanding matters that were under discussion are have now been agreed between the Applicant's Agent and the landowner's agent and the Applicant's Agent issued final Heads of Terms on 2nd September 2026. It is understood that the landowner's agent requires certain sign off from their client and it is expected that signed Heads of Terms will be received prior to a DCO decision being reached. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel David Price | 2386 | K90346 | Freehold | Subsoil |  | Category 1 | N/A | Yes | RR-4767 | RR-4767 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004980 | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Ann Beeton | 730 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowners' agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impacts of the future restrictions of the easement on their property. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. The Applicant's Agent had a meeting with the landowner's agent on 7th July 2026. The only outstanding point for agreement is the commercial terms and the Applicant's Agent remains in regular discussions with landowners agent in relation to this point, the Applicant is currently review comparable land value evidence provided by the landowner's agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Ann Beeton | 730 | SK382238 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowners' agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impacts of the future restrictions of the easement on their property. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. The Applicant's Agent had a meeting with the landowner's agent on 7th July 2026. The only outstanding point for agreement is the commercial terms and the Applicant's Agent remains in regular discussions with landowners agent in relation to this point, the Applicant is currently review comparable land value evidence provided by the landowner's agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Ann Beeton | 730 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowners' agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impacts of the future restrictions of the easement on their property. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. The Applicant's Agent had a meeting with the landowner's agent on 7th July 2026. The only outstanding point for agreement is the commercial terms and the Applicant's Agent remains in regular discussions with landowners agent in relation to this point, the Applicant is currently review comparable land value evidence provided by the landowner's agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Ann Beeton | 730 | SK382238 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowners' agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impacts of the future restrictions of the easement on their property. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence since the last update in April 2026. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group and the landowner's agent and the Applicant's agent have had weekly phone calls to discuss the Heads of Terms. The Applicant's Agent had a meeting with the landowner's agent on 7th July 2026. The only outstanding point for agreement is the commercial terms and the Applicant's Agent remains in regular discussions with landowners agent in relation to this point, the Applicant is currently review comparable land value evidence provided by the landowner's agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307035 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold | Subsoil |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent remains engaged in ongoing negotiations with the landowner's agent regarding the Heads of Terms. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. A Teams meeting between the Applicant's Agent and the landowner's agent took place on 7 July 2026 to discuss the remaining matters. The principal outstanding issue relates to the commercial terms, and the Applicant's Agent continues to engage regularly with the landowner's agent to seek agreement on this point. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Younger | 2748 | SK176970 | Freehold | Subsoil |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/78 | Suffolk Sheet 2 | 1,611 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK432967 | Freehold |  |  | Category 1 | In-house | Yes | RR-4903 | RR-4903 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005920 | REP1-139 REP3A-014 REP4-113 | REP1-139 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001105-Scottish-Power-Renewables-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S5AA6A0E0.pdf REP3A-014 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002217-Deadline%203A%20Submission.pdf REP4-113 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002542-Appendix%201%20-%20EA1NL_EA2L_SPR(UK)%20Ltd%20-%20DL4%20submission%20-%20Written%20Summary%20of%20Oral%20Case%20-%20CAH1.pdf | [5 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | 10.02.2026 - Negotiations are positively ongoing with SPR in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. | 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and SPR's representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that SPR intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge SPR's interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with SPR to understand their land interests. The Applicant proposes to issue Heads of Term to SPR following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with SPR/EA1N/EA2 and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/79a | Suffolk Sheet 2 | 133 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK432967 | Freehold |  |  | Category 1 | In-house | Yes | RR-4903 | RR-4903 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005920 | REP1-139 REP3A-014 REP4-113 | REP1-139 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001105-Scottish-Power-Renewables-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S5AA6A0E0.pdf REP3A-014 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002217-Deadline%203A%20Submission.pdf REP4-113 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002542-Appendix%201%20-%20EA1NL_EA2L_SPR(UK)%20Ltd%20-%20DL4%20submission%20-%20Written%20Summary%20of%20Oral%20Case%20-%20CAH1.pdf | [5 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | 10.02.2026 - Negotiations are positively ongoing with SPR in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. | 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and SPR's representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that SPR intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge SPR's interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with SPR to understand their land interests. The Applicant proposes to issue Heads of Term to SPR following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with SPR/EA1N/EA2 and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK346948 | Freehold | Subsoil |  | Category 1 |  | Yes | RR-5020 RR-3978 | RR-5020 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001141 RR-3978 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005065 | REP1A-151 | REP1A-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001478-Nicola-(Ning)-Suzanne-Fulford-Written-summaries-of-oral-submissions-made-at-hearings-held-during-w/c-3-and-w/c-10-November-2025.-S55829990.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - Heads of Terms are not being issued given the existing rights. | 13.04.2026 - Heads of Terms are not being issued given the existing rights. | 29.04.2026 - Heads of Terms are not being issued given the existing Deed of Easement held over this land. | The Applicant maintains their position that their existing Deed of Easement for the existing infrastructure provides the required rights for the proposed works. The Applicant will continue to engage with the landowner and their agent in relation to the proposed works as required. | No Heads of Terms Required |  | 2026-09-11
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK346948 | Freehold |  |  | Category 1 |  | Yes | RR-5020 RR-3978 | RR-5020 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001141 RR-3978 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005065 | REP1A-151 | REP1A-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001478-Nicola-(Ning)-Suzanne-Fulford-Written-summaries-of-oral-submissions-made-at-hearings-held-during-w/c-3-and-w/c-10-November-2025.-S55829990.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - Heads of Terms are not being issued given the existing rights. | 13.04.2026 - Heads of Terms are not being issued given the existing rights. | 29.04.2026 - Heads of Terms are not being issued given the existing Deed of Easement held over this land. | The Applicant maintains their position that their existing Deed of Easement for the existing infrastructure provides the required rights for the proposed works. The Applicant will continue to engage with the landowner and their agent in relation to the proposed works as required. | No Heads of Terms Required |  | 2026-09-11
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophie Clare Langmead | 2286 | SK418441 | Freehold | Subsoil |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | See PIL No.508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold | Subsoil |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Following a Teams meeting with the landowner’s agent on 24 June 2026, revised Heads of Terms were issued on 14 July 2026. The sole outstanding issue relates to the golf club’s ability to undertake future development above the proposed cable easement. The landowner is seeking prior agreement to raise ground levels by up to 4 metres over the cable corridor at some point in the future. However, in the absence of any development proposals, plans or supporting drawings, the Applicant is unable to agree to such an arrangement at this stage, as the potential impact on the installed cable cannot be properly assessed. The Applicant remains willing to consider proposals for changes to ground levels once the cable has been installed and sufficient information is available to enable a detailed technical assessment of the likely effects on the asset. This position was confirmed by the Applicant’s Agent in correspondence to the landowner’s agent on 14 July 2026, which accompanied the revised Heads of Terms. The Applicant's Agent had a subsequent Teams meeting with the landowner's agent on 11th August 2026 to confirm the position in relation to future development. The Applicant's Agent issued final Heads of Terms to the landowner's Agent on 20th August 2026. The Applicant’s Agent understands that the Heads of Terms are otherwise agreed between the parties. Subject to resolution of the above matter, the Applicant remains confident that a voluntary agreement can be reached prior to a DCO decision. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | See PiL No. 654- Robert John Chapman | No Heads of Terms Required |  | 2026-09-11
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K834466 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | Subsoil |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No |  |  | REP5-222 | REP5-222 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002999-Summary%20of%20Changes%20to%20Sea%20Link%20Project%20Deadline%205%20documents%20-%209.16%20(F)%20Lands%20Rights%20Tracker%20and%204.2.2%20(F)%20SoR%20Appendix%20B%20Schedule%20of%20Negotiations%20with%20Land%20Interests.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial postion and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. The Applicant and their agent met with the landowner's agent on 6th May and 6th July 2026. Revised Heads of Terms were issued on 11th June 2026 with further revisions shared with the landowner’s agent on 23th June 2026. The outstanding matters discussed at the meeting on 6th July 2026 relate to retained rights of access post construction and practical matters including accommodation works during construction. The Heads of Terms were updated based on the feedback received at the meeting on 6th July 2026 and these were reissued on 20th July 2026. The Applicant's Agent had a Teams meeting with the landowner's agent on 11th August 2026, following which, the Applicant's Agent issued updated Heads of Terms and clarifications in relation to the proposed works to the landowner's Agent on 28th August 2026 and a further Teams meeting was held on 10th September 2026. The landowner's Agent has confirmed that the landowner is willing to reach an agreement with the Applicant as soon as possible and it is expected that the Heads of Terms will be signed shortly after the final version is issued w/c 14th September 2026. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/31 | Suffolk Sheet 7 | 1,362 square metres, or thereabouts, of public adopted highways (B1121 and A12, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406 | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/31 | Suffolk Sheet 7 | 1,362 square metres, or thereabouts, of public adopted highways (B1121 and A12, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold | bridge | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | bridge | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/24 | Suffolk Sheet 7 | 31 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK351168 | Freehold |  |  | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/25 | Suffolk Sheet 7 | 21 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406 | Freehold |  |  | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 | SK254614,SK329337 | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK254614,SK329337 | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406,SK351168 | Freehold | Subsoil |  | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 REP5-178 REP5-179 REP5-180 REP5-181 REP5-204 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf REP5-178 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%204.pdf REP5-179 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20A%20(Alternative%20Access%20Route%20to%20Saxmundham%20Converter%20Station)%20with%20Maps.pdf REP5-180 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002941-Suffolk%20County%20Council%20-%20Appendix%20B%20(Guidance%20on%20Hedgrows%20and%20Trees).pdf REP5-181 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002942-Suffolk%20County%20Council%20-%20Appendix%20C%20-%20Comments%20on%20differences%20between%20the%20DCOs%20for%20East%20Anglia%20One%20North,%20East%20Anglia%20Two%20and%20Sea%20Link%20.pdf REP5-204 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002943-Suffolk%20County%20Council%20-%20Answers%20to%20ExQ2.pdf | [5 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 10.03.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold | Subsoil |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 REP5-186 REP5-207 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf REP5-207 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-ExQ2%20TDC%20Response.pdf REP5-186 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002859-Thanet%20DC%20-%20Principal%20Areas%20of%20Disagreement%20Summary%20Statement%20-%20D5.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.26 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant and their Agent met with the landowner's new agent on 6th May to discuss the project proposals and Heads of Terms. The landowner's agent confirmed at this meeting they were still waiting for instruction from their client and they would provide further comments on the Heads of Terms in due course. The Applicant and their agent had a further meeting with the landowner's agent on 6th July 2026 and revised Heads of Terms were issued to the landowner's agent on 15th July 2026 to align with the latest template terms renegotiated with other agents. Additional information was also provided in relation to the Applicant's proposed use of the Hoverport. The Applicant's Agent had a further Teams meeting with the landowner's agent on 11th August 2026 to discuss the revised Heads of Terms and additional information provided. The outstanding points to agree are the commercials and the proposed access requirements over the Hoverport site. The next meeting with the landowner's agent is scheduled for 9th September 2026. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [5 empty] | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/91 | Kent Sheet 2 | 114 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/98 | Kent Sheet 2 | 889 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
5/14 | Kent Sheet 5 | 4,138 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
5/15 | Kent Sheet 5 | 94,015 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
5/16 | Kent Sheet 5 | 2,940 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
5/11 | Kent Sheet 5 | 9,032 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 |  | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
5/12 | Kent Sheet 5 | 14,198 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 |  | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [6 empty] | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/105 | Kent Sheet 2 | 1,603 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [5 empty] | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
6/7 | Suffolk Sheet 6 | 6,923 square metres, or thereabouts, of foreshore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | SK298665 | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 | [5 empty] | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing. | The Applicant’s Agent and the landowner’s agent have been engaged in discussions to resolve a small number of remaining points relating to the wider rights required. On 13 July 2026, the Applicant’s Agent confirmed the Applicant’s position regarding the additional rights associated with the existing overheadlines and offered a meeting to facilitate the conclusion of negotiations. The Applicant’s Agent has also requested an update from the landowner’s in-house legal team regarding the section 135 matter and is awaiting a response. Heads of Terms are agreed and legal drafting will commence to document the terms agreed. The Applicant remains confident that these outstanding matters will be resolved in the near term and well in advance of the DCO decision being made. | Heads of Terms agreed |  | 2026-09-11
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 |  |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 | K535742 | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 | K535742 | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/92 | Kent Sheet 2 | 109 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/100 | Kent Sheet 2 | 962 square metres, or thereabouts, of drain, river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/103 | Kent Sheet 2 | 55 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
2/106 | Kent Sheet 2 | 1,539 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 |  |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to complications with probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled. | The Applicant’s Agent contacted the landowner’s agent on 12 June and 2nd September 2026 to seek confirmation as to whether probate had been concluded. At the time of writing, no confirmation has been received that probate has been finalised, which remains necessary before the parties can proceed to the signing of the Heads of Terms. The Applicant’s Agent will continue to engage with the landowner’s agent to progress matters and secure agreement at the earliest opportunity. | Heads of Terms negotiations ongoing |  | 2026-09-11
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Mark Wernet, Ardent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 | REP5-161 REP5-176 REP5-198 | REP5-161 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-176 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002869-National%20Trust%20response%20update%20on%20Heads%20of%20Terms_.pdf REP5-198 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002868-National%20Trust%20responses%20to%20ExQ2%20and%20other%20matters.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Constructive engagement with the landowner’s agent has continued since the previous update in April 2026, resulting in Heads of Terms being agreed on 5 May 2026. The Option agreement legally completed on 5th August 2026 and the landowner has subsequently withdrawn their objection to the Project. | Heads of Terms agreed |  | 2026-09-11
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Public Trustee | 825 | SK134793 | Freehold | Subsoil | as Personal Representative to the Estate of Peter Dickinson | Category 1 | No Agent Known | No | [9 empty] | Not SU |  |  | No Negotiations |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The Public Trustee | 825 | SK254614 | Freehold |  | as Personal Representative to the Estate of Terence James Martin Haworth | Category 1 | N/A | Yes | RR-5322 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 831 - Personal Representative to the Estate of Terence James Martin Haworth | See PIL No. 831 - Personal Representative to the Estate of Terence James Martin Haworth | See PIL No. 831 - Personal Representative to the Estate of Terence James Martin Haworth | See PIL No. 831 - Personal Representative to the Estate of Terence James Martin Haworth | See PIL No. 831 - Personal Representative to the Estate of Terence James Martin Haworth | Heads of Terms negotiations ongoing |  | 2026-09-11
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [8 empty] | Not SU |  |  | No Negotiations | See PIL No. 2520 - Andrew Johnson (as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals) | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | See PIL No. 3589 -Personal Representative to the Estate of Andrew William Johnson | Heads of Terms negotiations ongoing |  | 2026-09-11
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
4/9 | Kent Sheet 4 | 88 square metres, or thereabouts, of drain situated to the east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/135 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
2/136 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [8 empty] | SU | Not required |  | No Negotiations |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 29.04.2026- No voluntary rights are being sought in relation to this PiL | No voluntary rights are being sought in relation to this PiL | No Heads of Terms Required |  | 2026-09-11
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustine's Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | Heads of Terms negotiations ongoing |  | 2026-09-11
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustine's Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | Heads of Terms negotiations ongoing |  | 2026-09-11
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustine's Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | Heads of Terms negotiations ongoing |  | 2026-09-11
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustine's Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | Heads of Terms negotiations ongoing |  | 2026-09-11
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustine's Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  | No Negotiations | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | See PIL No. 553 - St. Augustine's Golf Club (Ramsgate) Limited | Heads of Terms negotiations ongoing |  | 2026-09-11
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Timothy Peter Singleton | 588 | SK314433 | Freehold | Subsoil |  | Category 1 |  | No | [9 empty] | Not SU |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | 10.02.2026 – On the 9th January 2026, the landowner confirmed that they would provide feedback on the Heads of Terms during the week commencing 19th January 2026. The Applicant's Agent emailed the landowner on 22nd January 2026 to confirm if feedback was still expected. On 5th February 2026, the Applicant’s Agent called the landowner who confirmed that they require further internal reviews before feedback on the Heads of Terms can be provided. The Applicant’s Agent will continue to engage with the landowner and it is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 23rd February 2026, the Applicant's Agent emailed the landowner requesting feedback on the Heads of Terms and inquired as to whether any further information could be provided to facilitate a response. On the 6th March 2026 the Applicant's Agent emailed the landowner with revised Heads of Terms for review and proposed a meeting for the week commencing 23rd March 2026. It is understood that there are no in principle concerns from the landowner and the Applicant's Agent expects that an agreement can be reached by the end of Examination once the landowner has had time to consider the proposed terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent called the landowner to discuss Heads of Terms and project timescales. The landowner confirmed that they would provide written feedback on the documentation ahead of the Easter break. To date written feedback has not been received, and Applicant's Agent sent a follow up email on the 9th April 2026. Given the delays from the landowner it is not expected that an agreement will be reached by the end of Examination. | 29.04.2026 - On the 20th April 2026, the Applicant's Agent emailed the landowner requesting written feedback on the Heads of Terms and offering a meeting. The Applicant's Agent attended a Teams meeting with the landowner on the 22nd April 2026 to discuss the Heads of Terms and the landowner sent a follow up email with the marked up documentation. The main points that they have provided feedback on are in relation to restrictions within the option area, ancillary rights for utilities and third party interests. The Applicant is currently reviewing the landowner's feedback on the Heads of Terms and the Applicant will respond with their position as soon as practicable. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner. Revised Heads of Terms were issued on 29th May 2026 which addressed their queries in relation to the ancillary rights for utilities, third party rights and the restrictions within the option area. The Applicant's Agent is awaiting feedback on these revised terms from the landowner, follow up emails were issued to the landowner on 22nd June, 14th July and 2nd September 2026, the most recent offering a Teams meeting. The Applicant's Agent will continue to engage with the landowner, it is not believed there are any substantial matters outstanding but the landowner has not always been quick to engage on this matter. | Heads of Terms negotiations ongoing |  | 2026-09-11
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  | excluding mines and minerals | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | 10.02.2026 – On the 9th January 2026, the landowner confirmed that they would provide feedback on the Heads of Terms during the week commencing 19th January 2026. The Applicant's Agent emailed the landowner on 22nd January 2026 to confirm if feedback was still expected. On 5th February 2026, the Applicant’s Agent called the landowner who confirmed that they require further internal reviews before feedback on the Heads of Terms can be provided. The Applicant’s Agent will continue to engage with the landowner and it is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 23rd February 2026, the Applicant's Agent emailed the landowner requesting feedback on the Heads of Terms and inquired as to whether any further information could be provided to facilitate a response. On the 6th March 2026 the Applicant's Agent emailed the landowner with revised Heads of Terms for review and proposed a meeting for the week commencing 23rd March 2026. It is understood that there are no in principle concerns from the landowner and the Applicant's Agent expects that an agreement can be reached by the end of Examination once the landowner has had time to consider the proposed terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent called the landowner to discuss Heads of Terms and project timescales. The landowner confirmed that they would provide written feedback on the documentation ahead of the Easter break. To date written feedback has not been received, and Applicant's Agent sent a follow up email on the 9th April 2026. Given the delays from the landowner it is not expected that an agreement will be reached by the end of Examination. | 29.04.2026 - On the 20th April 2026, the Applicant's Agent emailed the landowner requesting written feedback on the Heads of Terms and offering a meeting. The Applicant's Agent attended a Teams meeting with the landowner on the 22nd April 2026 to discuss the Heads of Terms and the landowner sent a follow up email with the marked up documentation. The main points that they have provided feedback on are in relation to restrictions within the option area, ancillary rights for utilities and third party interests. The Applicant is currently reviewing the landowner's feedback on the Heads of Terms and the Applicant will respond with their position as soon as practicable. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner. Revised Heads of Terms were issued on 29th May 2026 which addressed their queries in relation to the ancillary rights for utilities, third party rights and the restrictions within the option area. The Applicant's Agent is awaiting feedback on these revised terms from the landowner, follow up emails were issued to the landowner on 22nd June, 14th July and 2nd September 2026, the most recent offering a Teams meeting. The Applicant's Agent will continue to engage with the landowner, it is not believed there are any substantial matters outstanding but the landowner has not always been quick to engage on this matter. | Heads of Terms negotiations ongoing |  | 2026-09-11
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  |  | Category 1 | N/A | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | 10.02.2026 – On the 9th January 2026, the landowner confirmed that they would provide feedback on the Heads of Terms during the week commencing 19th January 2026. The Applicant's Agent emailed the landowner on 22nd January 2026 to confirm if feedback was still expected. On 5th February 2026, the Applicant’s Agent called the landowner who confirmed that they require further internal reviews before feedback on the Heads of Terms can be provided. The Applicant’s Agent will continue to engage with the landowner and it is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 23rd February 2026, the Applicant's Agent emailed the landowner requesting feedback on the Heads of Terms and inquired as to whether any further information could be provided to facilitate a response. On the 6th March 2026 the Applicant's Agent emailed the landowner with revised Heads of Terms for review and proposed a meeting for the week commencing 23rd March 2026. It is understood that there are no in principle concerns from the landowner and the Applicant's Agent expects that an agreement can be reached by the end of Examination once the landowner has had time to consider the proposed terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent called the landowner to discuss Heads of Terms and project timescales. The landowner confirmed that they would provide written feedback on the documentation ahead of the Easter break. To date written feedback has not been received, and Applicant's Agent sent a follow up email on the 9th April 2026. Given the delays from the landowner it is not expected that an agreement will be reached by the end of Examination. | 29.04.2026 - On the 20th April 2026, the Applicant's Agent emailed the landowner requesting written feedback on the Heads of Terms and offering a meeting. The Applicant's Agent attended a Teams meeting with the landowner on the 22nd April 2026 to discuss the Heads of Terms and the landowner sent a follow up email with the marked up documentation. The main points that they have provided feedback on are in relation to restrictions within the option area, ancillary rights for utilities and third party interests. The Applicant is currently reviewing the landowner's feedback on the Heads of Terms and the Applicant will respond with their position as soon as practicable. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner. Revised Heads of Terms were issued on 29th May 2026 which addressed their queries in relation to the ancillary rights for utilities, third party rights and the restrictions within the option area. The Applicant's Agent is awaiting feedback on these revised terms from the landowner, follow up emails were issued to the landowner on 22nd June, 14th July and 2nd September 2026, the most recent offering a Teams meeting. The Applicant's Agent will continue to engage with the landowner, it is not believed there are any substantial matters outstanding but the landowner has not always been quick to engage on this matter. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/20b | Suffolk Sheet 3 | 158 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wallace John Wilson-Haffenden | 3258 | K273192 | Freehold |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  |  |  | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the Landowner's Agent requesting both comparable evidence supporting their commercial position, and commentary on the Heads of Terms. On the 2nd March 2026, the Applicant's Agent phoned and emailed the Landowner's Agent to request the aforementioned comparable evidence and feedback on the Heads of Terms. The Landowner's Agent confirmed that they would look to provide this information by 6th March 2026. To date, no response has been received but the Applicant's agent remains positive Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. Further discussion is ongoing in relation to the impact on the retained holding. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - On 14th April 2026, The Applicant's Agent emailed the landowner's agent to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is currently engaging with the landowner's agent to reach an agreement in relation to the commercial elements of the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th May 2026 with further revisions issued on 10th June 2026. The revisions included amendments to ancillary rights for utilities and enabling works which were discussed with he landowner's agent at the previous meeting. The Applicant's Agent had further Teams meetings with the landowners agent on 24th June and 11th August 2026 to discuss the outstanding points. All clauses in the Heads of Terms have been agreed with the landowner's Agent however the Applicant's Agent is currently awaiting for further details of the Telecoms Mast adjacent to the Order limits. Once this information has been received it is expected that the Applicant's Agent will be in a position to issue final Heads of Terms for signing. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/21a | Suffolk Sheet 3 | 3,051 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/21a | Suffolk Sheet 3 | 3,051 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/21b | Suffolk Sheet 3 | 4,248 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Southern Water Services Limited | 411 | K708841 | Freehold |  |  | Category 1 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf | [5 empty] | SU rights in land | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Southern Water Services Limited | 411 | K708841 | Occupation |  |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf | [5 empty] | SU rights in land | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [5 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [5 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [5 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [5 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [5 empty] | Open Space |  |  | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 2 | No Agent Known | Yes | tbc | [8 empty] | SU | Standard PPs as set out in the dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - At this stage the Applicant maintains its expectation that Thanet OFTO Limited will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Thanet OFTO Limited has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/35 | Kent Sheet 2 | 87 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/42 | Kent Sheet 3 | 78 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/43 | Kent Sheet 3 | 248 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/45 | Kent Sheet 2 | 968 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/48 | Kent Sheet 3 | 189 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/84 | Kent Sheet 3 | 19 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track, drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [6 empty] | Open Space |  |  | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/10 | Suffolk Sheet 2 | 1,388 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/10a | Suffolk Sheet 2 | 1,975square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/11b | Suffolk Sheet 2 | 860 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/11 | Suffolk Sheet 2 | 619 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/11a | Suffolk Sheet 2 | 1,970 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/15 | Suffolk Sheet 2 | 21,961 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/15a | Suffolk Sheet 2 | 18,731 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/15b | Suffolk Sheet 2 | 9324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/42 | Suffolk Sheet 2 | 28,055 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | electricity substation |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/42a | Suffolk Sheet 2 | 11 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/46 | Suffolk Sheet 2 | 264 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/27 | Suffolk Sheet 4 | 134,639 square metres, or thereabouts, of grass land, scrubland, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Ash Covert, Suffolk Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/7 | Suffolk Sheet 2 | 12,621 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/8 | Suffolk Sheet 2 | 12,352 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/8a | Suffolk Sheet 2 | 7,285 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Unknown Occupier of Caravan | 3546 |  | Occupation |  |  | Category 2 | [11 empty] | Not SU |  |  |  |  | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | No Heads of Terms Required |  | 2026-09-11
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Unknown Occupier of Caravan | 3546 |  | Occupation |  |  | Category 2 | [11 empty] | Not SU |  |  |  |  | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | See PiL 494- Struan Gordon Robertson | No Heads of Terms Required |  | 2026-09-11
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Wallace John Wilson-Haffenden | 3258 | K273192 | Freehold |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [9 empty] | Not SU |  |  |  |  | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the Landowner's Agent requesting both comparable evidence supporting their commercial position, and commentary on the Heads of Terms. On the 2nd March 2026, the Applicant's Agent phoned and emailed the Landowner's Agent to request the aforementioned comparable evidence and feedback on the Heads of Terms. The Landowner's Agent confirmed that they would look to provide this information by 6th March 2026. To date, no response has been received but the Applicant's agent remains positive Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. Further discussion is ongoing in relation to the impact on the retained holding. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - On 14th April 2026, The Applicant's Agent emailed the landowner's agent to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is currently engaging with the landowner's agent to reach an agreement in relation to the commercial elements of the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th May 2026 with further revisions issued on 10th June 2026. The revisions included amendments to ancillary rights for utilities and enabling works which were discussed with he landowner's agent at the previous meeting. The Applicant's Agent had further Teams meetings with the landowners agent on 24th June and 11th August 2026 to discuss the outstanding points. All clauses in the Heads of Terms have been agreed with the landowner's Agent however the Applicant's Agent is currently awaiting for further details of the Telecoms Mast adjacent to the Order limits. Once this information has been received it is expected that the Applicant's Agent will be in a position to issue final Heads of Terms for signing. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf | [5 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/22a | Suffolk Sheet 3 | 220 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/22a | Suffolk Sheet 3 | 220 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [9 empty] | SU | Agreed and in latest version of dDCO |  |  |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | No Heads of Terms Required |  | 2026-09-18
3/20a | Suffolk Sheet 3 | 2,350 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [9 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Revised Heads of Terms were issued on 1st May 2026 which addressed the points raised by the Suffolk Agents group. The Applicants Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and meetings held to progress discussions on the Heads of Terms. Meetings were held on 19th May 2026 and 18th June 2026 to discuss the outstanding points, being provisions for crop loss and compensation, the ancillary rights for access and drainage and how these overlap with third party development proposals and ensuring that the farms irrigation infrastructure remains viable during construction. These points have been addressed and Heads of Terms which were issued on 20th July 2026. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points have since been agreed. The Applicant issued final Heads of Terms on 10th September 2026 and the landowners agent has confirmed that these are in an agreed format. The Applicant is waiting for signed Heads of Terms to be returned. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK346463 | Occupation |  | As tenant of Wood Farm | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landonwer's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent has continued to engage with the landowners agent since the last update in April 2026. The Applicants Agent had meetings with the landowners agent on 14th May 2026, 19th June 2026 and 7th July 2026 to discuss the Heads of Terms for freehold acquisition and revisions to the Heads of Terms were issued on 21st May 2026, 24th June 2026 and 3rd July 2026. Heads of Terms were agreed on 7th July 2026 and the drafting of the legal documents are progressing well which should allow this to conclude ahead of a DCO decision. The Heads of Terms include a clause to provide vacant posession upon completion of the Option Agreement. This terminates Mr Nichol's tenancy agreement on completion on a voluntary basis. | Heads of Terms agreed |  | 2026-09-11

## Category 1 Unknowns
Sea Link: Detailed Land and Rights Negotiations Tracker - Category 1 Unknowns
Note: Green highlight indicates identified claimants or reputed owners of unregistered plots
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | Party Name | PartyID | Interest Type | Interest Description | LR SIM | Highway Authority | September 2023 Site Notice | October 2023 Site Notices | July 2024 Site Notice | November 2024 Site Notice | March 2025 Site Notices | May 2025 Site Notice | September 2025 Site Notices | January 2026 Site Notices | March 2026 Site Notices | Additional Information
[10 empty] | Unknown Site Notices | s.47 & s.48 Notices | General/ Unknown Site Notices | Targeted Consultation Site Notices | Reg 8 Change Request Notices | s.56 Notices and Unknown Site Notices | Change Control s.56 Notices & Unknown Site Notices | Hearing Notice | Hearing Notice
2/100 | Kent Sheet 2 | 962 square metres, or thereabouts, of drain, river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/101 | Kent Sheet 2 | 24 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Prior to submission this plot was believed to be part of a watercourse Site notices were not placed for the purposes for consultation for plots believed to be watercourses, however for s56 these plots were included in unknown notice posting
2/102 | Kent Sheet 2 | 184 square metres, or thereabouts, of agricultural land and drain situated to the north west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Prior to submission this plot was believed to be part of a watercourse Site notices were not placed for the purposes for consultation for plots believed to be watercourses, however for s56 these plots were included in unknown notice posting
2/103 | Kent Sheet 2 | 55 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/106 | Kent Sheet 2 | 1,539 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2246 | Freehold | Railway | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | South Eastern & Chatham Railway line in use. Ownership evidenced by whoownsegnland and supported by Network Rail underground utilities data. Network Rail down as reputed owner in the BoR
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2246 | Freehold | Railway | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | South Eastern & Chatham Railway line in use. Ownership evidenced by whoownsegnland and supported by Network Rail underground utilities data. Network Rail down as reputed owner in the BoR
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 | Freehold | Railway | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | South Eastern & Chatham Railway line in use. Ownership evidenced by whoownsegnland and supported by Network Rail underground utilities data. Network Rail down as reputed owner in the BoR
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 | Freehold | Railway | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | South Eastern & Chatham Railway line in use. Ownership evidenced by whoownsegnland and supported by Network Rail underground utilities data. Network Rail down as reputed owner in the BoR
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1544 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/131 | Kent Sheet 2 | 1,038 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1557 | Freehold | Drain | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/135 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1545 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/136 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1545 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/17 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/18 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1559 | Freehold | Private Road | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1559 | Freehold | Private Road | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/185 | Kent Sheet 2 | 633 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1630 | Freehold | Drain | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1559 | Freehold | Private Road | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/188 | Kent Sheet 2 | 105 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 | Freehold | Scrubland | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified. Network Rail down as reputed owner in the BoR
2/19 | Kent Sheet 2 | 68 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/20 | Kent Sheet 2 | 44 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/22 | Kent Sheet 2 | 190 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/25 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/26 | Kent Sheet 2 | 582 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/31 | Kent Sheet 2 | 290 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/33 | Kent Sheet 2 | 152 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/34 | Kent Sheet 2 | 88 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/35 | Kent Sheet 2 | 87 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/37 | Kent Sheet 2 | 73 square metres, or thereabouts, of drain, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/38 | Kent Sheet 2 | 60 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/43 | Kent Sheet 2 | 14 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/44 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/45 | Kent Sheet 2 | 968 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/46 | Kent Sheet 2 | 26 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/48 | Kent Sheet 2 | 11 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/77 | Kent Sheet 2 | 288 square metres, or thereabouts, of track and scrubland situated to the south west of Boxlees Hill, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1556 | Freehold | Track | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Prior to submission this plot was believed to be part of a Highway Site notices were not placed for the purposes for consultation for plots believed to be highways however for s56 these plots were included in unknown notice posting Caution against first registration in favour of NGET
2/80 | Kent Sheet 2 | 113 square metres, or thereabouts, of scrubland and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1556 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1897 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Prior to submission this plot was believed to be part of a Highway Site notices were not placed for the purposes for consultation for plots believed to be highways however for s56 these plots were included in unknown notice posting Caution against first registration in favour of NGET
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1555 | Freehold | Scrubland | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Prior to submission this plot was believed to be part of a Highway Site notices were not placed for the purposes for consultation for plots believed to be highways however for s56 these plots were included in unknown notice posting
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/87 | Kent Sheet 2 | 43 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/89 | Kent Sheet 2 | 29 square metres, or thereabouts, of sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/92 | Kent Sheet 2 | 109 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 | Freehold | Riperian | Y | N | Yes | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Email correspondence with the Crown Estate and CW Gooch Ltd detailed the interests claimed to be held by the Marquess Conyngham over the River Stour area The Heads of Terms are in agreed form with the Marquess of Conyngham, however, due to probate it is unlikely they will be signed before the end of Examination.
2/97 | Kent Sheet 2 | 20 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1559 | Freehold | Private Road | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3285 | Freehold | Pond | Y | N | Yes | Yes | Yes | N/A | Yes | Yes | Yes | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified. Change of plot number for Targeted Consultation in March 2025
3/18 | Kent Sheet 3 | 104 square metres, or thereabouts, of private road (Jutes Lane) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3429 | Freehold | Private Road | Y | Y | No | Yes | N/A | Yes | N/A | N/A | N/A | Yes | Yes | After investigation this should be maintained by the Highway Authority (Kent County Council)
3/42 | Kent Sheet 3 | 78 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/43 | Kent Sheet 3 | 248 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/48 | Kent Sheet 3 | 189 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1552 | Freehold | Track | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1549 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1549 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1549 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3283 | Freehold | Golf Course | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified. St Augustine's Golf Course down as Reputed Owner in the BoR
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1552 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2251 | Freehold | Scrubland | Y | N | Yes | Yes | N/A | Yes | N/A | N/A | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3283 | Freehold | Golf Course | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified. St Augustine's Golf Course down as Reputed Owner in the BoR
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3283 | Freehold | Golf Course | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified. St Augustine's Golf Course down as Reputed Owner in the BoR
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3263 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 | Freehold | Agricultural Land | Y | N | Yes | Yes | Yes | Yes | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
4/9 | Kent Sheet 4 | 88 square metres, or thereabouts, of drain situated to the east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1549 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3549 | Freehold | Footpath | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/39 | Suffolk Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3414 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3553 | Freehold | Footpath | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3554 | Freehold | Footpath | Y | N | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3555 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/80 | Suffolk Sheet 2 | 2 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2577 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
2/82 | Suffolk Sheet 2 | 49 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2577 | Freehold | Agricultural Land | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were erected to identify and notify relevant landowners. As no further response was given the owner of the land still remains unidentified.
6/2 | Suffolk Sheet 6 | 1,436 square metres, or thereabouts, of drain and scrubland situated to the south west of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1041 | Freehold | Drain | Y | N | No | Yes | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Site notices were not placed for the purposes for consultation for plots believed to be highways/watercourses, however for s56 these plots were included in unknown notice posting
7/21 | Suffolk Sheet 7 | 719 square metres, or thereabouts, of railway, works and land situated to the east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3451 | Freehold | Railway | Y | N | N/A | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Yes | East Suffolk Railway line in use. Ownership evidenced by whoownsegnland Network Rail down as reputed Owner in the BoR
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3449 | Freehold | Railway | Y | Y | N/A | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Yes | Enquiries were made to the relevant highway authorities to determine the adoption status of highway. Any unregistered land and adopted highway followed subsoil presumptions through the ad medium filum rule. Network Rail down as reputed Owner in the BoR
7/26 | Suffolk Sheet 7 | 944 square metres, or thereabouts, of railway, works and land situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3451 | Freehold | Railway | Y | N | N/A | N/A | N/A | N/A | Yes | N/A | Yes | Yes | Yes | East Suffolk Railway line in use. Ownership evidenced by whoownsegnland Network Rail down as reputed Owner in the BoR

## Category 2
Sea Link: Detailed Land and Rights Negotiations Tracker - Category 2 interests
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | PIL Name | PIL Reference/Land Referencing PartyID | Title Number(s) | Interest Type | Interest Description | Party Interest capacity | Category | Agent/ representative (if any) | Relevant Representation | When available Relevant representation reference number | When available Written representation reference number | Other document reference number | Applicant's response references | Special category (allotment, National Trust etc) (Select from drop down list) | Crown | Special category - other information including confirmation of status | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of Negotiation | Status of Negotiation - Deadline 6 | Status of Negotiation - Deadline 7 | Status of Negotiation - Current (SoS Update) 11/09/2026 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK379333,SK407557 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK379333,SK407557 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11