1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement At this stage the Applicant maintains the expectation anticipates that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement At this stage the Applicant maintains the expectation anticipates that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement At this stage the Applicant maintains the expectation anticipates that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker as necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant will continue to pursued engagement with the statutory undertaker throughout examination but had no response from OCU Group Limited indicating that bespoke protective provisions or a side agreement is requiredas necessary on an ongoing basis. In the absence of further engagement the Applicant maintains the expectation that tThe statutory undertaker will therefore rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/18 | Kent Sheet 3 | 104 square metres, or thereabouts, of private road (Jutes Lane) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/28 | Kent Sheet 4 | 408 square metres, or thereabouts, of public adopted highway (Ramsgate Road) situated to the north east of Ebbsfleet House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [6 empty] | Open Space | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [6 empty] | Open Space | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/27 | Suffolk Sheet 4 | 134,639 square metres, or thereabouts, of grass land, scrubland, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Ash Covert, Suffolk Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
6/6 | Suffolk Sheet 6 | 143 square metres, or thereabouts, of car park, scrubland and path situated to the east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this Pil, however, The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker. In the absence of further engagement the Applicant maintains the expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant pursued engagement with the statutory undertaker throughout examination but had no response from Openreach Limited. In the absence of further engagement the the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 2 | No Agent Known | Yes | RR-5066 | [6 empty] | SU | Agreed and in latest version of DCO |  | 04.03.2026-No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached on these before the end of the examination process as well as on a separate side agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/81 | Kent Sheet 3 | 430 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation |  |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU and disputed operational | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track, drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  | Open Space | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  | Open Space | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 2 | N/A | No |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf |  |  |  | SU kit and apparatus | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant received bespoke protective provisions from Southern Water on 03/03/2026. The Applicant has reviewed the draft protective provisions and has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed. The Applicant will continue to engage with the statutory undertaker | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | Protective Provisions have been agreed and completed. These provide the security to Southern Water that their operations will not be interrupted | No Heads of Terms Required |  | 2026-09-11
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wallace John Wilson-Haffenden | 3258 | K273192 | Occupation |  |  | Category 2 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the Landowner's Agent requesting both comparable evidence supporting their commercial position, and commentary on the Heads of Terms. On the 2nd March 2026, the Applicant's Agent phoned and emailed the Landowner's Agent to request the aforementioned comparable evidence and feedback on the Heads of Terms. The Landowner's Agent confirmed that they would look to provide this information by 6th March 2026. To date, no response has been received but the Applicant's agent remains positive Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. Further discussion is ongoing in relation to the impact on the retained holding. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - On 14th April 2026, The Applicant's Agent emailed the landowner's agent to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is currently engaging with the landowner's agent to reach an agreement in relation to the commercial elements of the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th May 2026 with further revisions issued on 10th June 2026. The revisions included amendments to ancillary rights for utilities and enabling works which were discussed with he landowner's agent at the previous meeting. The Applicant's Agent had further Teams meetings with the landowners agent on 24th June and 11th August 2026 to discuss the outstanding points. All clauses in the Heads of Terms have been agreed with the landowner's Agent however the Applicant's Agent is currently awaiting for further details of the Telecoms Mast adjacent to the Order limits. Once this information has been received it is expected that the Applicant's Agent will be in a position to issue final Heads of Terms for signing. The Applicant's Agent will continue negotiations with the landowner's agent and expect that agreement will be reached prior to the DCO decision being made. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | See PIL No. 508 - Peter Murray Mann | Heads of Terms negotiations ongoing |  | 2026-09-11
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold | Subsoil |  | Category 2 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf |  |  |  | Not SU |  |  | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 2 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf |  |  |  | Not SU |  |  | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | William Notcutt Estates Limited | 132 | SK336019 | Freehold | Subsoil |  | Category 2 | William Mitcham, Wilson Wraight | No |  |  | REP1-291 REP5-210 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf REP5-210 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002831-William-Notcutt-Estates-Limited-Responses-to-ExQ2-(if-required).-SD75EAB07.pdf |  |  |  | Not SU |  |  | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent, landowner and the landowner's agent have continued to engage constructively in negotiations, with ongoing correspondence and a series of meetings held to progress discussions on the Heads of Terms. Meetings were held on 13th May 2026, 2nd June 2026, 9th July 2026 and 20th July 2026, during which the parties reviewed the remaining commercial and technical matters requiring agreement. The discussions have been positive and the parties have made good progress, with the number of outstanding matters continuing to reduce. The principal matters requiring further consideration relate to commercial provisions associated with impacts on land outside the areas proposed to be purchased or leased, agreement of the soil survey requirements and methodology, and arrangements for the ongoing management of the land. The Applicant's Agent remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching voluntary agreement by DCO decision. The landowner provided a detailed response to the latest Heads of Terms on 2 September 2026. Whilst a number of drafting comments and clarifications have been requested, the majority of these appear to relate to the wording and implementation of principles that are broadly agreed between the parties, rather than introducing new commercial positions. The remaining comments principally seek to ensure that the agreed commercial and operational arrangements are accurately reflected within the documentation and that appropriate protections are secured for the landowner. The Applicant's Agent is reviewing these points with the expectation that they can be addressed through continued negotiation with a meeting to be held imminently. | Heads of Terms negotiations ongoing |  | 2026-09-11
3/21b | Suffolk Sheet 3 | 4,248 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | Draft under discussion |  | 2026-09-18
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU | Agreed and in latest version of dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. | 13.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of protective provisions. It is expected that agreement will be finalised and the bespoke protective provisions included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cityfibre Holdings Limited | 3299 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will continue to pursue engagement with the statutory undertaker, however, to date there has been no response from City Fibre Holdings Limited. | 13.04.2026 - The Applicant will continue to pursue engagement with the statutory undertaker, however, to date there has been no response from City Fibre Holdings Limited. The Applicant therefore maintains its expectation that the statutory undertaker will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | 29.04.2026 - The Applicant will continue to pursued engagement with the statutory undertaker throughout examination, however, to date there has been no response from City Fibre Holdings Limited indicating that bespoke protective provisions or a side agreement is required. The statutory undertaker will Applicant therefore maintains its expectation that the statutory undertaker will rely onbenefit from the standard protective provisions set out in Schedule 15 of the dDCO. | The Applicant will continue to pursued engagement with the statutory undertaker throughout examination, however, to date there has been no response from City Fibre Holdings Limited indicating that bespoke protective provisions or a side agreement is required. The statutory undertaker will Applicant therefore maintains its expectation that the statutory undertaker will rely onbenefit from the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/20b | Suffolk Sheet 3 | 158 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | Draft under discussion |  | 2026-09-18
3/20b | Suffolk Sheet 3 | 158 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | Draft under discussion |  | 2026-09-18
3/20a | Suffolk Sheet 3 | 2,350 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | Draft under discussion |  | 2026-09-18
3/20a | Suffolk Sheet 3 | 2,350 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Agreed and in latest version of DCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL | 13.04.2026 - The Applicant received a side agreement from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | 29.04.2026 - The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement in principle in relation to the Protective Provisions included for UKPN’s benefit at Schedule 15 to the DCO.The Applicant is awaiting bespoke protective provisions from the statutory undertaker, who have indicated that these will be issued imminently. Upon receipt the Applicant will review the proposed protective provisions and continue to engage with the statutory undertaker. It is anticipated that bespoke protective provisions will be submitted at Deadline 7. The Applicant is considering a side agreement received from UKPN on 10/04/2026 seeking a Deed of Grant and an Asset Protection Agreement. | The Applicant is in ongoing discussions with UKPN regarding the DCO application and has reached agreement of bespoke protective provisions from the statutory undertaker. Bespoke protective provisions were submitted at Deadline 7. | Draft under discussion |  | 2026-09-18
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL. however, The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL. however, The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL. however, The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL. however, The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL. however, The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - The Applicant will continue to engage with the statutory undertaker on an ongoing basis. At this stage and based on discussions with the statutory undertaker including in relation to the draft SoCG [REP1-098] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | Virgin Media has not indicated a requirement for bespoke protective provisions and will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant will continue to engage with the Vodafone, the outcomes of which will be reflected in the next version of the draft SoCG [REP1-099] between the parties. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026 - Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant will continue to engage with the Vodafone, the outcomes of which will be reflected in the next version of the draft SoCG [REP1-099] between the parties. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026 - Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant will continue to engage with the Vodafone, the outcomes of which will be reflected in the next version of the draft SoCG [REP1-099] between the parties. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026 - Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant will continue to engage with the Vodafone, the outcomes of which will be reflected in the next version of the draft SoCG [REP1-099] between the parties. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026 - Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- No voluntary rights are being sought in relation to this PiL, however, The Applicant will continue to engage with the Vodafone, the outcomes of which will be reflected in the next version of the draft SoCG [REP1-099] between the parties. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026 - Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | Vodafone has not indicated a requirement for bespoke protective provisions and will rely on the standard protective provisions set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown Land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO
| Open space | SU kit and apparatus | No agreement on final version
| National Trust and Open Space | SU rights in land
Crown Land and Marquess Conyngham (reputed ownership)
Open Space and Crown Land
Other