## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - response to the Deadline 7 documents and the All Interested Parties - Invitation to Comment
For:
The construction and operation of Sea Link Energy Cable.
Planning Inspectorate Reference ENO20026
21 October 2026

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Sea Link examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - Suffolk Onshore B - Kent Onshore C- Development Consents Order D - Physical Environment E - Benthic Ecology F - Marine Mammals G - Marine Ornithology H - Sufolk and Essex Coast & Heaths DL The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## N. Addressing Risk and Issues
Progress on Resolving Risks and Issues at RFI 2 - October 2026
Other than the submissions relating to the updated DCO/dML uploaded to the Planning Inspectorate website on 19 October 2026, Natural England has reviewed and provided advice on all updated documents submitted by the Applicant and, where possible, identified potential pathways for resolving outstanding issues and risks.
Engagement with the Applicant
The volume of material submitted at Deadline 7 and in response to the Request for Further Information (18 September 2026), together with the extent of revisions made to key documents at a late stage in the Examination, has required substantial review by our specilaists across a wide range of technical topics. Given the timescales available, opportunities for detailed engagement on all updates have necessarily been limited. Nevertheless, Natural England offered and attended an update call with the Applicant on 20 October 2026 to discuss its position at a high level in advance of this submission.
It is important to recognise when considering progress towards issue resolution that the Examination has been characterised by a continually evolving evidence base, including revisions to aspects of the project, methodologies, assessments and supporting technical documentation. This has required Interested Parties, including statutory consultees, to undertake repeated reviews of updated information and, where appropriate, reconsider earlier positions in light of new evidence.
Against that background, there will inevitably be occasions where written submissions do not fully reflect the most recent iteration of a document or proposal. This is a practical consequence of assessing substantial volumes of amended material within the statutory Examination timetable and should not be interpreted as a lack of engagement with the issues under consideration.
Equally, the resolution of outstanding matters should not be viewed primarily through the lens of attendance at hearings. The key consideration is whether sufficient information has been provided to enable the relevant assessments to be completed and robust conclusions reached with the necessary degree of confidence. Where information remains uncertain, incomplete or subject to ongoing refinement, some matters have remained under discussion despite constructive engagement by all parties.
More generally, earlier maturity and stability of key environmental information, assessments, mitigation proposals and supporting evidence prior to submission would have provided a firmer basis for Examination and supported earlier issue resolution. In these circumstances, it would not be accurate to attribute the emergence or continuation of outstanding issues principally to consultee engagement during Examination, particularly where such issues have arisen in the context of an evidence base that has continued to develop throughout the process.

## PADSS
Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG rating | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 4a | Consultation, actions, progression | RAG Deadline 4b | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
Suffolk Onshore
NE1 | The HDD landfall works have not been sufficiently considered. | For the Suffolk landfall location, Natural England is concerned that: - no detailed botanical surveys have been carried out at Leiston-Aldeburgh SSSI, - the impact on protected coastal habitats should be assessed, - the effects of dewatering to the Leiston-Aldeburgh SSSI have not been fully considered, - further Ground Investigation surveys may be required, and - further clarifications are needed on the proposed measures to minimise potential frac-outs. | For the Suffolk landfall location, Natural England advises that further information is required to inform a Horizontal Directional Drilling (HDD) management plan | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. | [5 empty] | We note the inclusion of measures B59 and B60 in [REP3-077] and these post-consent measures are welcomed. However, concerns remain and outline information is needed at the consent stage to inform decision making. Please see Points A11 and A12 of the R&I log and REP3-116 for more information. |  | No change. Whilst NE considers that this information should have been provided pre consent, we note the commitment to provide it post consent. However, we consider that an HDD Management Plan is required at the consent stage to inform decision making. Natural England highlights that this may cause delay to construction and advises that the timeframes for the provision of documents prior to construction is extended to take account of any outstanding issues which may arise |  | No change. Whilst Natural England considers that this information should have been provided pre consent, we note the commitment to provide it post consent. However, we consider that an HDD Management Plan is required at the consent stage to inform decision making. Natural England highlights that this may cause delay to construction and advises that the timeframes for the provision of documents prior to construction is extended to take account of any outstanding issues which may arise. |  | No | No change.
NE2 | Insufficient information to determine the extent of loss of land. | Natural England is concerned that there is insufficient information to determine the extent of loss of Best and Most Versatile land. | Natural England advises that further assessment work is provided to inform a robust soil management plan, which should be submitted into examination. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. | [5 empty] | No Change. This remains Amber as we are awaiting the updated Outline Soil Mgt Plan to be submitted during the course of examination |  | No change although Natural England understand that a Soil Management Plan will be submitted into the examination process, noting the time constaints of the Examination process |  | Natural England welcomes that ALC survey data has been provided and incorporated into the updated Outline Soil Management Plan. Due to the submission at this late stage of the examination period, we have not been able to review this with our specialists to provide specific advice. |  | No | Part Progressed. Please see Suffolk Onshore tab which sets out what further detail is required
NE3 | No letters of no impediment for bats | Natural England has not reviewed any draft licence documents for this project. The Applicant has not sought any Letters Of No Impediment from Natural England for bats. | We advise that the Applicant contacts Natural England’s licensing service | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. | [5 empty] | The Applicant has contacted NE's Wildlife Licensing Service in line with our earlier advice. However, concerns remain that potential impacts on Barbastelle bats remain from artificial lighting and advise the Applicant to further engage on mitigation measures with NEWLS regarding these impacts. |  | No Change. NE considers that the significance for bats should be considered national and not regional. Further engagement NEWLs is recommended. |  | No Change. Natural England considers that the significance for bats should be considered national and not regional. Further engagement NEWLs is recommended. |  | No | No Change. Natural England considers that the significance for bats should be considered national and not regional. Further engagement NEWLs is recommended.
Kent Onshore
NE4 | Feasibility of Horizontal Directional Drilling (HDD). | Natural England is concerned that the Applicant has not considered all potential impacts to designated sites as a result of HDD installation, including impacts to designated saltmarsh habitats and hydrology. The access route used by contractors to facilitate HDD installation remains unclear. | Further assessment would be required post-consent to determine the viability of HDD installation. Relevant documents should also be updated to include commitment to access routes and to provide a full consideration of the hydrological impacts of HDD. | Uncertain |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, please see Appendix J3a [REP3A-028] to our Deadline 3a submissions |  | No change, please see Appendix J4 to our Deadline 4 submission | [5 empty] | Please see response to ExQ2 ECOL6. Risks remain to the Applicant if it is found post consent that HDD is not a viable option. Therefore, we advice that the level of comfort on the feasiblity of HDD is not going to be available at the time of consent. | [5 empty] | N/A
NE5 | In-combination assessment of Air Quality impacts. | Natural England advises that in combination impacts need to be considered within the DCO if in combination impacts are likely. It is not clear from the information provided if this is the case. | Natural England advises that in order to provide clarity to the ExA regarding potential air quality impact pathways on designated site the applicant provides updated information on impacts and on the use of Non-Road Mobile Machinery. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change. | [5 empty] | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. Please see standard advice submitted previously. | [5 empty] | N/A
NE6 | Impacts to breeding bird assemblages | Natural England has outstanding concerns on impacts to breeding bird assemblages in Sandwich Bay to Hacklinge Marshes SSSI. | We recommend the implementation of a seasonal restriction on works likely to cause disturbance to breeding bird assemblages for which the site is designated. These measures should be secured within the REAC. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. | [5 empty] | Natural England refer the Applicant to our previous advice in [REP4-068] re. avoiding construction during the breeding bird season where practicable, securing an ECoW to oversee all relevant works and updating your REAC measures to reflect this. It remains Natural England’s advice that the bird breeding season should be considered to be March to September inclusive, and that any works which are likely to disturb breeding birds should preferably be timed to avoid these months. [REP4-068] section 1.6.1 has been updated to include the appointment of an ECoW, and Natural England ask that the REAC is updated to include reference to this measure under B45, B50 and B65 (similarly to how B02 has been worded under REP4-234 9.84 (B) REAC February 2026. Provided that these commitments are secured within a named plan/document, Natural England will be satisfied there will be no likely significant impact upon Sandwich Bay to Hacklinge Marshes SSSI due to construction disturbance. |  | Natural England has discussed with the developer and expect information to be submitted at Deadline 6 that will allow resolution of this Issue. |  | The expected information was not included at D6. Natural England has further discussed with the developer and expect information to be submitted at Deadline 7 that will allow resolution of this Issue. |  | No | No Change. The REAC (Doc.9.84, version F) states the breeding bird season covers March to September (inclusive) and should work be undertaken during this time it will be overseen by an EnvCoW with appropriate protection measures put in place where necessary. This requirement is secured in the outline landscape and ecology management docs for Kent and Suffolk and through DCO 3 schedule, requirement 6 LEMP. Resolved. However, please see cover letter in regards to impacts at Sandwich Bay and Hacklinge which are not resolved
NE28 | Release of contaminants and debris from degraded hoverport | Natural England has become aware of evidence relating to the potential release of contaminants and debris from further degradation of the hover port. If this is the case then we would advise against the use of the hoverport | We advise that further clarification and assessment of this issue is required. | It is possible this issue could be progressed with further provision of information. |  | New Issue |  | New Issue |  | New Issue |  | New issue raised at Deadline 4 | [5 empty] | No change. Please see our additional advice provided in Appendix D5. Natural England also notes that the applicant responded to this when it was raised by the ExA during ISH2 as summarised in REP4-085, Table 2.1. We acknowlegde that condition surveys will be undertaken for all work areas, including the hoverport, and protective measures such as track matting and structures will be used to protect both vehicles and the surface condition. Natural England advises that the commitment to condition surveys and protective measures are described and secured in a named plan/document - Natural England continue to advise that further assessment on the impacts are required in order to know the full extent of impact including the types of contaminants and condition of the concrete apron. Please see response to the ExA's Q2 ECOL52 in Appendix K5 to our Deadline 5 submission. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. |  | Whilst Natural England welcomes management measure W37 [REP6-135] to prepare a hoverport condition monitoring plan post-consent to monitor the condition of the hoverport during construction, including identifying and managing any potential contamination risk, we consider that the condition assessment should commence as soon as possible to inform understanding of the potential environmental risks and mitigation measures. |  | No | No change. Natural England will welcome the opportunity to be consulted on the Hoverport Condition Monitoring Plan post-consent [REP7-160], including the necessary measures for identifying and managing any potential contamination risk. However, we highlight that currently there is insufficient information to inform understanding of the potential implications for the coastal/marine environment due to use of the hoverport for access during construction and operation.
Draft Development Consent Order
NE7 | The definition of commence within the draft consent. | The definition of commence within both the Development Consent Order (DCO) and Deemed Marine Licence (dML) allow for damaging works to be conducted prior to agreement on the pre commencement mitigation documents. | The definition should be updated. | It is possible this issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Partially resolved. A query remains on pre-lay grapnel runs. |  | No change. | [5 empty] | No change. The Applicant has advised updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | Natural England has raised new concerns within our Deadline 6 cover letter due to the changes. Specificially the exclusion of trial trenches implies some trenching may be undertaken prior to any monitoring or agreements on final mitigation plans. The removal of pre lay cable acitivites is appreciated and resolves the original issue raised. |  | No changes have been made, our concern remains. |  | No | No change. The Applicant has included wording to define trial trenching. However, the wording still would allow trial trenching within the sensitive intertidal habitats. Therefore, this issue remains unresolved.
NE8 | Arbitration | Article 62 includes that decisions made by the Secretary of State, Trinity House and the MMO may be subject to arbitration. The Secretary of State has determined on several occasions this was not appropriate. | The arbitration article should be appropriately updated. | It is possible this issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Resolved. The wording has been appropriately updated. | [13 empty] | Yes
NE9 | Lack of monitoring requirements within the deemed Marine Licence(dML) | The dML does not include any provisions requiring monitoring, either pre commencement or post works. It is a standard approach to undertake surveys prior to works to identify features of conservation importance and, where possible, micro-site around them and where not possible to monitor their recovery. In addition, monitoring may be required where there remains residual concerns. | Natural England advises that conditions to secure pre and post works monitoring as required and set out in an In Principle Monitoring Plan (IPMP). | It is possible the issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. | [5 empty] | No Change, Natural England has reviewed all upated DCOs and our position has not changed. In additiion, Natural England has advised in several Appendices to our Deadline 5 response that further requirements/conditions are required in relation to monitoring. |  | No change. Natural England has reviewed the updated DCO documents and raised concerns in our Deadline 6 Cover letter and Appendices E6, K6 and M6 with regard to the REAC and the need to secure monitoring and mitigation. |  | Updated, an IPMP condition is now in place. However, the lack of pre and post construction monitoring conditions remain. If the ExA schedule of changes for monitoring conditions and updates to condition 4 are included then this issue would be resolved. |  | No | Partially resolved. The applicant has secured pre construction benthic monitoring using appropriate wording. However, post construction monitoring has not been secured, therefore our concerns partially remain.
Physical Environment
NE10 | Cable Protection adjacent to Goodwin Sands MCZ | It is not stated whether cable protection measures may be required directly adjacent to Goodwin Sands MCZ. Therefore, we are concerned that the potential presence of cable protection measures adjacent to the MCZ, over the lifetime of the Project, could affect sediment transport processes/pathways operating on and around the MCZ and in turn lead to morphological change at the MCZ. | Natural England advises that the Applicant should clarify whether cable protection measures may be required adjacent to Goodwin Sands MCZ. The WCS parameters for cable protection measures near/at the MCZ should be provided, and potential impacts to supporting sediment transport processes should be considered for the lifetime of the project. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change. Please see Appendix D3 [REP3-118] to our Deadline 3 submissions and Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. Please see our detailed comments on indirect impacts to Goodwin Sands MCZ in Appendix D4 of our Deadline 4 submission. |  | No change. |  | No change. |  | No change. Please see our advice in Appendix D5 and E5 of our Deadline 5 submission. |  | Our concerns remain regarding the potential for morphological and sedimentary change due to the placement of cable protection adjacent to Goodwin Sands MCZ. We advise that this issue may be resolved, and understanding increased, with additional assessment of the geomorphology, morphodynamics, sediment transport pathways, scour potential etc. This should be achievable using the data available to the Applicant. Please also see Appendix D6. |  | No change. We advise that the Applicant should either (a) assess indirect effects on Goodwin Sands MCZ due to the placement of WCS 3.2km cable protection measures adjacent to the MCZ boundary, or (b) commit to not allowing the placement of cable protection measures adjacent to the MCZ based on a high-level of confidence that successful cable burial will be achieved through the lifetime of the Proposed Project. |  | No | Not resolved. Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
NE11 | Need for more detailed analysis of morphological change. | Natural England highlights significant morphological change within Pegwell Bay including beach profile elevation at Pegwell Bay, progradation of Shell Ness and migration of the River Stour channel. | Natural England advises that a more detailed analysis of the longer-term morphological trends through the lifetime of the Project should be carried out to inform the cable burial and asset integrity assessment. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change Please see Appendix D3 [REP3-118] to our Deadline 3 submissions and Appendix J3a [REP3A-028] to our Deadline 3a submission. |  | Concerns remain regarding coastal evolution at the Kent landfall. Need to establish a more robust baseline characterisation prior to installation to assess impacts against - Please also see our advice in Appendix D4. |  | No change. |  | No change. |  | Issue progressed. We note and welcome the Applicant's commitment MPE08 [REP4-234] to carry out further analysis to consider the potential for coastal erosion over the lifetime of the project which will inform detailed design. However, our concerns remain regarding cable exposure risk due to ongoing migration of the River Stour channel towards the cable route coupled with climate change effects such as increased storminess, increased erosional potential, mean sea level rise and shoreline response. These factors also need to be considered in the contact of the shoreline management plans. Please also see our advice in Appendix D5. |  | No change. We advise that further detailed analysis is needed to increase understanding of the current and future River Stour mouth/low water channel elevation level relative to cable route and also the likely depth of the buried cable. Additional mitigation measures also need to be explored such as a deeper burial depth and/or potentially moving the cable route further north. Please also see Appendix D6. |  | Issue progressed. The Applicant has proposed monitoring of the RIver Stour Channel through the operational life of the asset, which is welcomed, however we advise this monitoring should commence as soon as possible. The Applicant also proposes contingency actions and a trigger point, which are also welcomed. However, we advise further assessment should be carried out to more fully understand the long-term development of the River Stour channel in Pegwell Bay relative to the cable route. |  | No | Progressed. The risk remains that a migrating Stour channel could interact with the installed cable. However, we welcome the update to the IPMP [REP7-168] in which the Applicant has committed to monitoring the River Stour Channel post-consent through pre-installation surveys and throughout the operational life of the asset. A trigger for consultation with the EA has also been included if the Channel migrates to within 50m of the cable. This is welcomed. However, the monitoring proposed to assess impacts to coastal erosion at Pegwell Bay is restricted to the trenchless technique construction areas associated with the exit pit and does not consider potential impacts to coastal receptors due to cable installation and operation. We continue to advise that monitoring at landfall should encompass the full extent of the nearshore/intertidal areas that may be affected by cable installation/operation. Further advice is provided in Appendix D8.
NE12 | Missing information | Appendix 4.1.A misses several important information: - There is no mention of information on the dispersion model validation. - No detailed information of the hydrodynamic modelling and model that provided the tidal conditions. | Natural England advises that the Environmental Statement (ES) should be updated to include relevant information as described | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change. Please see Appendix D3 [REP3-118] to our Deadline 3 submissions. |  | No change. |  | No change. |  | No change |  | No change. Please see Appendix D5 to our deadline 5 submission for more detailed comments |  | Issue progressed. We note in [REP5-132] that [APP-195] suspended sediment modelling will be updated in preparation for ISH3. This is welcomed. We look forward to reviewing the updated modelling report and will update our advice as appropriate. |  | Natural England welcomes the additional modelling [REP6-120] carried out by the Applicant for both landfalls. We also note the Applicant's signpost to Appendix 4.1.A in [APP-195] which details the hydrodynamic model calibration, which is welcomed. We also note the Applicant's response [REP1A-043] that there is no known precedent of the requirement to demonstrate validation of a particle-tracking model used to simulate sediment dispersion, which is acknowledged but does not address our original request. However, if the Applicant can commit to the monitoring we have recommended in Appendix D7, then this should provide evidence to support and validate the ES conclusions derived from the hydrodynamic and sediment dispersion modelling, and resolve this issue. |  | No | No change.
Benthic Ecology
NE13 | Worst case scenario | There are a number of potential impacts on both intertidal and subtidal benthic habitats which have not been adequately considered or assessed within the Environmental Statement. | The Environmental Statement and relevant assessments are updated to consider all potential pathways of effects on intertidal and subtidal benthic habitats. Until resolved Natural England is unable to accept the conclusions within the MCZ assessment. | It is possible the issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. |  | Please see Appendix D7 and Appendix E7 of our Deadline 7 submission where further information where is requested on activites to reduce WCS. |  | No | Unresolved. Please see covering letter on changes to landfall technique
NE14 | Maximum design cable protection | Natural England has concerns that the Maximum Depth parameter figures for cable protection are ambiguous and lack of rationale. | Review of all relevant application documents once ambiguities in the maximum design / worst case scenario have been addressed. | It is possible the issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix D3 [REP-118] to our Deadline 3 submissions and Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | No Change. Please see Appendix D5, E5 and K5 to our deadline 5 submission for more detail on our outstanding concerns in relation to cable protection. |  | No Change: Please see Appendix D6 and E6 to our Deadline 6 submission which discuss cable protection in more detail. |  | No change. Please see our advice in Appendix D7 of our Deadline 7 response. |  | No | No change. The potential for changes to the hydrodynamic regime or sediment transport pathways and in turn morphological change within the MCZ, needs to be fully considered and further evidence provided to support ES conclusions. See also our detailed comments in Appendix D8.
NE15 | Mitigation | Natural England notes that the Applicant has made no strong benthic mitigation commitments to avoid or reduce impacts to Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats. | Natural England advises that impacts to Section 41 NERC Habitats are avoided and due consideration is demonstrated. | It is possible this could be progressed with further commitments and information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats. |  | No Change: Please see Appendix D6 and E6 to our Deadline 6 submission which discuss mitigation measures in more detail. |  | Please see Appendix D7 and Appendix E7 of our Deadline 7 submission where further information is provided on the provison of strengthened mitigation measures. |  | No | Resolved. Please see cover letter comments on commitments BE05, BE06, BE07
NE16 | Permanent loss of benthic habitats | Natural England is concerned that the Applicant has not committed to the removal of cable and scour protection at the point of decommissioning. | Due consideration should be given to the nature of the cable protection used and should favour engineering options with the greatest likelihood of successful removal at the Project’s end of life. A commitment to removal of all infrastructure associated with the development at decommissioning is secured within the DCO and an Outline Decommissioning Plan should also be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | In progress. We welcome the submission of [REP4-091] 9.93 (A) Offshore Decommissioning Technical Note . However, it hasn't addressed our concerns. Please see Appendix E Point E.19 to our Deadline 5 submissions. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. |  | Please see Appendix E7 of our Deadline 7 submission in relation to further consideration to NERC Section 41 Habitats with are also irreplacable habitats. |  | No | No Change in relation to loss of irreplacable habitats
NE17 | Inappropriate assessment of benthic receptors | Natural England disagree with the Applicant’s assessment of the sensitivity of a number of benthic receptors. | The Environmental Statement requires revisiting and updating with an appropriately considered and evidenced assessment of the sensitivity of receptors, including those identified within the Zone of Influence (ZoI). | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | Part Resolved. While we welome updates to the Benthic Chapter on the sensitivity of some receptors. Please see Apendix E5 to our Deadline 5 submission where we advise that assessments are updated. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. |  | Please see Appendix D7 of our Deadline 7 submission in relation to indirect impacts to features of Goodwin Sands MCZ and Appendix E7 in relation to further consideration to NERC Section 41 Habitats with are also irreplacable habitats. |  | No | No Change
NE18 | Assessment on Benthic Receptors incomplete. | Natural England advises that the Applicants Environmental Impact Assessment (EIA) has not considered potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures” (A4.23 – Communities on soft circalittoral rock) which were recorded throughout the Offshore Scheme site specific surveys. | Natural England is unable to agree with the conclusions of the EIA, Report to inform Appropriate Assessment (RIAA) and Marine Conservation Zone (MCZ) assessment until a transparent and comprehensive assessment of all impacts upon all benthic receptors has been provided for review. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. | [5 empty] | In addition to our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission, Natural England advises that commitments to avoid impacts to Section 41 habitats by micro-siting should be secured, please see Appendix E5 to our Deadline 5 sumission. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. |  | Please see Appendix D7 of our Deadline 7 submission in relation to indirect impacts to features of Goodwin Sands MCZ and Appendix E7 in relation to further consideration to NERC Section 41 Habitats with are also irreplacable habitats. |  | No | No Change
NE19 | Sandwave Levelling | Natural England considers that further assessment of impacts from sandwave levelling on benthic receptors is required. | Natural England advises that the ES, and where relevant, RIAA and MCZ assessments, are updated to consider all potential pathways of effect on features of conservation importance from sandwave levelling and deposition of sediment | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix C3a [REP3A-026] to our Deadline 3a submission and Appendix B3 [REP3-117] to our Deadline 3 submission. |  | No change. Please see our detailed comments in Appendix D4. | [5 empty] | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix D5, E5 and J5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection. |  | No Change: Please see Appendix D6 and E6 to our Deadline 6 submission which discuss sandwave levelling in more detail. |  | Part Resolved. Please see our advice in Appendix D7 of our Deadline 7 submission where we highlight further mitigation requirements. |  | No | Resolved. Please see cover letter comments on commitments BE05, BE06, BE07
Marine Mammals
NE20 | Worst Case Scenario | While it is mentioned that a precautionary approach to estimating marine mammal abundances was recommended at the Statutory Consultation phase, it remains unclear if precautionary estimates have been considered. | Clarity is needed in the wording to demonstrate how a precautionary approach has been adopted in addition to use of updated survey data. | Potentially resolved with updated information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No Change. Please refer to our advice in Appendix F5. |  | No change. |  | No change. | [5 empty] | No change. |  | The Applicant has sent information to address this issue, however, it was received on 12 April and therefore Natural England has not had sufficient time to review ahead of Deadline 6, we will update our position at Deadline 7. |  | Resolved - agree with the Applicant's updated text in REP5-133 9.121.1 that there is now sufficient information in Part 4 Marine Chapter 4 Marine Mammals+O4O4O2:O3O2:O5O2:O6O2:O7O2:O5 |  | Yes
NE21 | Use of summer months as WCS | Harbour porpoise are known to occupy the southern region of Southern North Sea (SNS) Special Area of Conservation (SAC) in which they are designated in winter months (October – March), therefore it cannot be assumed that SCANS survey data conducted in July is representative of the greatest abundance of all cetaceans likely to be encountered. | The assessment should be updated to consider peak abundances for each species as representative of the WCS. | Potentially resolved with updated information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. | [5 empty] | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. |  | Issue Resolved, additional SCANS data in Version E of the MM Chapter has allowed sufficient confidence that the correct winter data was used. |  |  |  | Yes
NE22 | Sufficiency of EIA | Natural England cannot currently agree with the conclusions of the EIA for the reasons outlined in Appendix F [REP3-119]. | Updated assessment should be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | Natural England notes that only minimal changes have been made in the EIA followowing our advice, thus we maintain our original advice. | [5 empty] | No change. Please see our advice in Appendix F5. |  | Reduced risk as some information has been provided. However, In-combination and cumulative issues still require resolutions. |  | It is unclear to Natural England why Carter et al (2025) has been used to inform the assessment for SeaLink as this paper relates solely to seals in Scottish waters. We welcome the methodology that has been used however we would seek further clarification on the numbers used to undertake the calculations. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
NE23 | Sufficiency of HRA | Natural England cannot currently agree with the conclusions of the HRA for the reasons outlined in Appendix F [REP3-119]. | Updated assessment should be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England do not see any evidence of the changes in the assessment. In-combination assestment is particularly poor and has not been improved at all. Specifically, to assess whether there will be significant noise disturbance within a harbour porpoise SAC, the applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. Please consulate the Guidance for assessing the significance of noise disturbance against Conservation Objectives of harbour porpoise SACs (England, Wales & Northern Ireland). |  | There has been insufficent updates to assessments, particularly the In-combination assessment. Key concerns remain significant noise disturbance within a harbour porpoise SAC. The Applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. |  | No change. | [5 empty] | No change. Please see our advice in Appendix F5. |  | The Applicant has sent information to address this issue, however, it was received on 12 April and therefore Natural England has not had sufficient time to review ahead of Deadline 6, we will update our position at Deadline 7. |  | Natural England welcome the updated information provided by the Applicant with regard to the in-combination assessment and the commitment to participate in the Developers Co-ordination Forum (DCF). Although these changes do not resolve our outstanding issues with the methodology for undertaking the in-combination assessment, we are satisfied that the commitment to the DCF will ensure that there is no AEoI tot he SNS SAC, provided that comitment is conditioned in the DCO/dML. |  | Yes
Marine Ornithology
NE24 | Seasonal restrictions for Red Throated Diver in the Outer Thames Estuary SPA. | Natural England considers that an AEOI on the red-throated diver (RTD) feature of the Outer Thames Estuary SPA cannot currently be ruled out. Further, given the existing levels of disturbance/displacement and those associated with consented and proposed projects, even if AEOI can be ruled alone, any additional disturbance/ displacement would add to cumulative/in-combination impacts. | We request that the November to March timing restriction on cable construction works is widened in scope, for example to include pre-construction clearance activities, in line with advice provided in Appendix G4: Marine Ornithology. In order to understand the appropriate level of mitigation for different project phases, a more detailed spatio-temporal assessment is needed. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, Deadline 1A, change requests and Deadline 2. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, Deadline 1A, change requests and Deadline 2. |  | No change please see Appendix G4 to Natural England's Deadline 4 submission. |  | No change |  | No change |  | At a cumulative assessment level Natural England is now content with the Applicant's commitment to adhere to the seasonal restriction regardless of other plans/projects proceeding follwoing recent updates. However our concerns still remain the same regarding the pre-lay grapnel run works not being limited to the full seasonal restriction. |  | Following a meeting with the Applicant on the 1st April and further correspondence the following has been discussed: a) PLGR: The Applicant has been provided guidance on how to assess the impact using the 'bird days lost approach and has indicated they will present an assessment at D6. Following further discussions at the meeting on the 1st April and further correspondence on the 2nd April Natural England understand that the Applicant will be applying the seasonal restrictions to all activities. Providing that the commitment is submitted by the Applicant at D6 Natural England will consider this issue to be resolved. b) O&M and Decommisioning: Note the Applicant has pledged to mitigate decommisioning in the same way as construction and conduct O&M activities (except emergencies) outside the seasonally restricted period. Natural England consider this issue resolved. c) Emergency works: Following a meeting on the 1st April Natural England have proposed wording/conditions to ensure emergency works are securely captured and mitigated. Providing that the conditions are provided by the Applicant at D6 this issue will be resolved. |  | Natural England welcome the updates submitted at Deadline 6 and the steps the Applicant has taken to secure conditions in relation to the points below. Natural England now consider these issues resolved, a) PLGR: A condition to commit the Applicant to a full seasonal restriction to all activities; b) O&M and Decommisioning: A condition to commit the Applicant to mitigate decommisioning in the same way as construction and conduct O&M activities (except emergencies) outside the seasonally restricted period. c) Emergency works: A condition to ensure emergency works are securely captured and mitigated. But it should be recognised that the definition of emergency work is yet to be agreed with MMO. |  | Yes
NE27 | 2km buffer around the Outer Thames Estuary SPA | Natural England would note that the seasonal restriction at the moment only applies within the SPA itself. Natural England’s guidance on recent projects involving cable installation works is to include a 2km buffer from the seaward boundary of the OTE SPA, as vessels may disturb RTD up to 2km away. We would propose that this be included within an updated restriction and see this as an important component of any strategy to avoid AEoI. | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. | Uncertain. |  | New Issue |  | New Issue |  | New Issue |  | New issue raised at Deadline 4 |  | No change |  | No change |  | No change. Please see response to ExQ2 MO3. |  | Following review of the Issue Specific Hearing (ISH) recordings from 26th of March [EV9-009] and further confirmation with the Applicant at a meeting on the 1st April, Natural England acknowledges and welcomes the inclusion of the 2km buffer for the proposed mitigation for RTD in the OTE SPA. Provided that this is confirmed and secured within named plans/documents within the Applicants submission at Deadline 6 Natural England would welcome this commitment and consider this issue resolved. |  | Issue progressed. Natural England welcome the Applicants commitment of a seasonal restricton for cable installation to include a 2km buffer around the OTE SPA. Please see comment in DCO Appendix C7 in relation to securing this mitigation Please see Appendix G7 to our Deadline 7 submission for mitigation suggestions to minimise impacts on RTD further. |  | No | Resolved. The latest REAC states the 2km buffer is included in the DCO/dML as Condition 4(1)(b) of the DML/DCO Schedule 3, Requirement 6 Offshore Construction Environmental Management Plan Condition 4(1) of the DML Red Throated Diver Protocol. This suggests the commitment to include the PLGR run within the seasonally restricted period and apply this condition to the SPA and its 2km buffer has been secured and the matter is resolved.
Suffolk LVIA
NE25 | Further information needed to support impact assessment | Natural England is concerned that the project may have a significant impact (in EIA terms) on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and the Suffolk Heritage Coast. | Please see Table 2 of Appendix H3 [REP3-120] for our detailed comments, and the further information required. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change |  | No change |  | No change | [5 empty] | No Change. Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled however at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and concludes that we must agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change
NE26 | Significant cumulative impact assessment | Natural England is concerned about the significant (in EIA terms) cumulative impact that the project’s construction phase will have on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. | Natural England advise that information is required on how this significant adverse effect will be addressed. | Uncertain. | Red | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. | Red | No change |  | No change please see Appendix H3 [REP3-120] to Natural England's Deadline 3 submission. |  | No change please see Appendix H3 [REP3-120] to Natural England's Deadline 3 submission. | [5 empty] | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled however at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and concludes that we must agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change

## A - Suffolk Onshore
Point | Point Number(s) from Appendix A RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix A - Suffolk Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | A1 | Further information is required to inform a Horizontal Directional Drilling (HDD) management plan; in terms of access requirements at the landfall site to facilitate HDD; and to inform the feasibility of the HDD proposals. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. We note the inclusion of measures B59 and B60 in [REP3-077] and these post-consent measures are welcomed. However, this point highlights that outline information is needed at the consent stage to inform decision making. |  | No change. Whilst NE considers that this information should have been provided pre consent, we note the commitment to provide it post consent. Natural England highlights that this may cause delay to construction and advises that the timeframes for the provision of documents prior to construction is extended to take account of any outstanding issues which may arise. |  | No change. This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Natural England believes that this could be resolved through the development of a tranchless management plan prior to construction which is signed of and agreed by the relevant regulator and SNCB
2 | A2, A16 | Further assessment work should be provided to inform a robust soil management plan. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. This remains Amber as we are awaiting the updated Outline Soil Mgt Plan to be submitted during the course of examination. |  | Natural England understands that a Soil Management Plan will be submitted into the examination process |  | Issue progressed. Natural England welcomes the ALC survey data that has been provided at Deadline 6 and incorporated into the updated Outline Soil Management Plan. Due to submission at this late stage of examination, we have not been able to review this with our specialists to provide specific advice. |  | No | Issue progressed. ALC survey data has been reviewed and comments provided to SoS (18/09/26). Issues not fully resolved due to continued use of predicitve data (Suffolk). ALC results need to be linked to the soil management plan.
3 | A3, A17 | The Suffolk onshore scheme includes areas that appear to be of national significance for bats, due to the assemblage of species identified including Annex II Barbastelle Species. Given the prevalence of Barbastelles and other species in the area, we encourage the applicant to contact Natural England about potential impacts to bats, their roosts and/or their habitats for commuting/foraging/ dispersal. The removal of hedgerows could disrupt key commuting routes for bats. The Applicant has not sought any Letters Of No Impediment from Natural England for bats. We advise that the Applicant contacts Natural England’s licensing service |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. The Applicant has contacted NE's Wildlife Licensing Service in line with our earlier advice. However, concerns remain that potential impacts to Barbastelle bats remain from artificial lighting and advise the Applicant to further engage on mitigation measures with NEWLS regarding these impacts. |  | No Change. NE considers that the significance for bats should be considered national and not regional. Further engagement NEWLs is recommended. |  | No change. This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | No change. Natural England maintains our advice that the area is of national significance for bats. We have continued concerns regarding the impact to bats from lighting. Please see Appendix A for detailed comments.
4 | A1, A4 | Post consent botanical surveys should be secured and undertaken on the areas of Leiston-Aldeburgh SSSI within the development boundary, including the area intended for HDD. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at pre-Deadline, Deadlines 1 and 1A - this issue is resolved. | [11 empty] | Yes
5 | A5 | Detailed vegetation surveys (following the NVC survey method) will need to be undertaken to support any change in proposed methodology or future variations undertaken along the cable route to provide baseline information. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. Natural England advises that to resolve this issue commitments are made to undertake the necessary surveys and consultations regulators and relevant SNCB should methodologies require modification. |  | No change expected in examination. Any future changes to methodology will need to conside further NVC surveys. No further comment will be made unless the applicant provides information. |  | No change. Any future changes to methodology will need to conside further NVC surveys. |  | N/A
6 | A6 | An assessment of potential impacts to the protected coastal habitats should be undertaken including access along the trenchless cable route or to the exit pits be required by vehicles/ construction equipment during works. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | Resolved. The Applicant has committed in [REP3-078] that there will be no vehicle access to shiingle habitats. | [5 empty] | Yes
7 | A7 | Dewatering impacts should be assessed in relation to sensitive shingle habitats if additional GI boreholes are needed or if the additional GI surveys determine that a change in the depth of drilling is needed |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. Further evidence is required. See Appendix A3 [REP3-116] for detailed comments |  | No change |  | No change |  | Part Resolved. We advise that reference to "groundwater investigation surveys" should be "ground investigation surveys" for measure B63 in [REP3-077]. |  | Part resolved, minor correction needed. |  | Part resolved, minor correction needed. |  | No | This has been amended and issue resolved though Commitment GH09
8 | A8 | Any references to avoiding the Woodlark breeding season should read from September to January inclusive and any (noise) mitigation should be secured for this time period. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at Deadline 1 and 1A this issue is resolved. We note that in sections Ex1.5.3 and 7.2.17 the references to the woodlark breeding season have been changed from ‘March-August’ to ‘February-August’ inclusive, in line with our advice. | [11 empty] | Yes
9 | A9 | The ES chapters and methodology should be amended to provide clarity that ‘nationally designated ecological sites with dust sensitive features’ should be classified as a high sensitivity air quality receptor only. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | Resolved. We note that, while being in both high and medium categories, nationally designated sites where features may be affected by dust soiling have been assessed using the worst case scenario, i.e. they have been treated as high sensitivity in the assessment. | [5 empty] | Yes
10 | A7, A10 | Further information is required on the location and methods of any additional GI works which may be required prior to construction along the proposed cable alignment. An outline trenchless crossing (and associated works) method statement will be needed at the consent stage to inform decision making, with the submission and agreement of a final method statement by the LPA/MMO, secured as part of the DCO/dML prior to construction. Mitigation measures to avoid, reduce and mitigate impacts to shingle vegetation, shingle sediment matrix, and groundwater should be included within the method statement |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. We note the inclusion of measures B59 and B60 in [REP3-077] and these post-consent measure are welcomed. However, this point highlights that outline information is needed at the consent stage to inform decision making. |  | No Change, risk remains if further GI works are needed then further assessment and mitigation will be required under additional consents. |  | No change. This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Natural England believes that this could be resolved through the development of a tranchless management plan prior to construction which is signed of and agreed by the relevant regulator and SNCB.
11 | A11 | There are potential ecological risks if drilling equipment becomes stuck due to unknown London Clay depth or gravel/cobble layers. Further detail is required on how equipment would be retrieved without surface excavation. An outline method statement should be provided at the consenting stage to ensure that appropriate mitigation is available and can be implemented. In addition, a condition should secure submission and agreement of the final method statement prior to construction. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Further information provided at Deadlines 1 and 1A have been welcomed, however further information is required, in particular regarding the HDD in the event of it getting stuck. We also advise that a condition is needed to secure agreement of the method statement. For detailed comments please see Appendix A3 [REP3-116]. |  | No change |  | No change |  | No change. We note the inclusion of measures B59 and B60 in [REP3-077] and these post-consent measure are welcomed. However this point highlights that outline information is needed at the consent stage to inform decision making. |  | This point now highlights that outline information is needed at the consent stage to inform decision making and that a condition should secure submission and agreement of the final method statement prior to construction. |  | No change. This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Please see main letter in relation to trenchless techniques, are concerns remain relevant and applicable for the suffolk onshore scheme
12 | A12 | An outline HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Further information provided at Deadlines 1 and 1A have been welcomed, however further information is required and a condition needs to be secured for the final HDD management plan to be agreed in consultation with the relevant SNCB prior to construction. For detailed comments please see Appendix A3 [REP3-116]. |  | No change |  | No change |  | No Change. We note the inclusion of measures B59 and B60 in [REP3-077] and these post-consent measure are welcomed. However, this point highlights that outline information is needed at the consent stage to inform decision making. |  | This point highlights that outline information is needed at the consent stage to inform decision making. |  | No change. This matter remains outstanding and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Natural England believes that this could be resolved through the development of a tranchless management plan prior to construction which is signed of and agreed by the relevant regulator and SNCB.
13 | A13 | In relation to designated features of Sandlings SPA, the “March to August” period should be amended to read “February to August” and mitigation measures secured (in line with previous comments on Woodlarks) |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at Deadline 1 and 1A this issue is resolved. We note that in sections Ex1.5.3 and 7.2.17 the references to the woodlark breeding season have been changed from ‘March-August’ to ‘February-August’ inclusive, in line with our advice. | [11 empty] | Yes
14 | Appendix A1 [REP1-154] Submitted D1. NE Ref 1 | Overarching comment on HRA Impacts to acid grassland, a key supporting habitat within the SPA and FLL are not clearly assessed within the HRA. This advice replaces comment A14 within Natural England’s relevant and written representations |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. Our advice remains that the assessment in [REP3-064], paragraphs 7.2.4 to 7.2.9, lacks sufficient clarity to be able to rule out an adverse effect on integrity. |  | No Change. Our advice remains that the assessment in [REP3-064], paragraphs 7.2.4 to 7.2.9, lacks sufficient clarity regarding impact and mitigtaion to be able to rule out an adverse effect on integrity. |  | Issue resolved. Please see our Deadline 7 Appendix A7 for detailed comments. |  | Yes
15 | A15 | There should be a commitment to keeping the King Charles III England Coast Path (KCIIIECP) open and available during the construction period, where possible, through the use of management measures, such as controlled crossings and signage. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | Resolved. We note that the King Charles III England Coast path will remain open, as the crossing will be by HDD. | [5 empty] | Yes
16 | A16 | An outline soil management plan supported by relevant ALC survey data should be provided to address consenting risks and issues associated with disturbance/changes to agricultural land grade, raised in our relevant/written reps. [RR-3920] with a comment to submit and agree a final soil management plan in consultation with relevant SNCB prior to construction |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No Change. This remains Amber as we are awaiting the updated Outline Soil Mgt Plan to be submitted during the course of examination. |  | Natural England understands that a Soil Management Plan will be submitted into the examination process |  | Natural England welcomes the ALC survey data that has been provided at Deadline 6 and incorporated into the updated Outline Soil Management Plan. Due to submission at this late stage of examination, we have not been able to review this with our specialists to provide specific advice. |  | No | Issue Progressed. Natural England's updated position is as follows Subject to the incorporation of advice given in Table 2 Appendix A 22 Oct Natural England's position is the advice given within the Suffolk and Kent oSMPs can be accepted as suitable outline frameworks. They now contain the principal components expected by the Defra Construction Code of Practice and respond positively to the earlier request for clearer soil handling, supervision, monitoring and aftercare provisions. However, they should not be treated as demonstrating successful soil protection or restoration in themselves. Their acceptability depends on securing comprehensive, site-specific final SMPs, completing the outstanding soil-resource information and establishing measurable restoration and aftercare criteria before soil-disturbing works commence.
17 | Appendix A1 [REP1-154] Submitted D1. NE Ref 2 | AS-007 - Habitats Regulations Assessment. The Applicants assessment (7.2.9) states that although breeding birds have not been recorded the compound field is “very likely” to be functionally linked land. Natural England agrees with this assessment. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | Natural England recognises that the Applicant is not relying on acid grassland enhancement for loss of functionally linked land. However, acid grassland enhancement is used in the report as justification for the conclusion of no AEoI. We advise that the need for clearer information regarding the indirect impacts of noise and lighting on the FLL and clear audit trail of the temporary nature of the impact in order to substantiate conclusions, and that impacts to nightjar are more clearly incorporated. |  | We advise that the need for clearer information regarding the indirect impacts of noise and lighting on the FLL and clear audit trail of the temporary nature of the impact in order to substantiate conclusions, and that impacts to nightjar are more clearly incorporated. |  | Issue Resolved. Please see our Deadline 7 Appendix A7 for detailed comments. |  | Yes
18 | Appendix A1 [REP1-154] Submitted D1. NE Ref 3 | AS-007 - Habitats Regulations Assessment. Natural regeneration is proposed to restore acid grassland after disturbance within the construction phase (Paragraph 4.2.4 of the Outline Landscape and Ecological Management Plan). Natural England supports this proposal but advises that it is essential to understand soil fertility and pH for successful restoration. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | No change Impacts to the proposed enhancement area via cultivation, pH remain outstanding. |  | No change. We advise a clear Management Plan including baseline status and objectives should be provided in relation to the 6ha mitigation/compensation area. It appears that the 6ha contains deciduous woodland and additional habitat of biodiversity value, which should not be deleteriously impacted by the proposals. |  | No change. This matter remains outstanding in relationto LVIA impacts and therefore Natural England agrees to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Part Resolved. OLEMP now states that pH testing will be undertaken. It is Natural England’s understanding that the 6ha area was not required to rule out an adverse effect on integrity for the loss of 7.5 ha of foraging habitat for Sandlings SPA; please see clarification in A20 below. We have continued concerns regarding the suitability of the 6Ha area of acid grassland; please see LVIA comments.
19 | Appendix A1 [REP1-154] Submitted D1. NE Ref 4 | AS-007 - Habitats Regulations Assessment. One function of the restoration and enhancement (acid grassland) area appears to focus on providing habitat for bird species particularly Woodlark and Skylark, also invertebrates. It is not clear if the aim is to create priority habitat, because if the focus is habitat for bird species, then the grassland species composition may not be as crucial as the habitat structure. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | We note the Applicant's clarification in [REP3-064], that it is not relying on acid grassland enhancement for loss of functionally linked land. However we continue to advise that clarification is provided of exact impact pathways to the FLL and how these are mitigated. clear audit to provide evidence of the mulitfunctional use of the acid grassland enhancement area remains outstanding. |  | No change. We advise a clear audit trail to provide evidence of the multifunctional use of the acid grassland enhancement area remains outstanding. |  | Part Resolved. It is Natural England's undertsanding that the applicant is not relying on acid grassland enhanced in order to mitigtae for loss of FLL. Please see our Deadline 7 Appendix A7 for detailed comments. Please also see our comments in submisison H7 regarding the acid grassland proposals |  | No | Part resolved. Affected areas expected to be available again as foraging habitat in next nesting season. It is Natural England’s understanding that the 6ha area is not required to rule out an adverse effect on integrity for the loss of 7.5 ha of foraging habitat for Sandlings SPA; please see clarification in A20 below
20 | Appendix A1 [REP1-154] Submitted D1. NE Ref 5 | AS-007 - Habitats Regulations Assessment. The nature, location, quantity, habitat type, timing and duration of possible impacts to acid grassland are clarified and clearly stated in one place. The quantity and location of acid grassland affected differs between documents. These details should be clarified within the oLEMP. Clarification is also needed on: -why the further 8ha of temporarily affected acid grassland is not included in the total amount of acid grassland temporarily affected by the project. -why the acid grassland is not being avoided by HDD as per requirements of the mitigation hierarchy. -which acid grassland parcels are functionally linked to the Sandlings SPA How in-combination impacts with the extension of Aldringham Golf Course, which lies within the red line boundary of the Sea Link project, have been assessed. Clarity on project timescales including maintenance acid grassland (e.g. Paragraph 8.2.6 of HRA) cites 30 years, however all other timescales appear to refer to 10 years. -The report concludes a temporary impact but this relies on successful reinstatement which, if it fails would become a long-term impact. Contingency is required should habitats fail to reinstate during the expected timeframes. The intended function of the 6ha area and how it would benefit both woodlark and nightjar in order to clarify the conclusions of the HRA |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | In Section 8.2.5 of Document 6.6 (D) Habitats Regulations Assessment Report (Tracked), the timescale for maintenance of the acid grassland creation/enhancement area has been updated from 30 years to 10 years. This is now consistent with other application documents which state a 10 years maintenance timescale. This clarifies one of the queries we raised within this point, but other queries are not yet resolved. Please refer to NE advice in Appendix A1 [REP1-154] submitted at Deadline 1, NE Ref 5. |  | No Change |  | We continue to advise that the location, quantity, timing and duration of possible impacts to acid grassland are clarified and clearly stated in one place. |  | Part Resolved. The HRA contained inconsistent data regardng the area and quantum of acid grassland loss. Although we understand that the enhancement of acid grassland is no longer required for mitigation we maintain that further justification for not employing HDD methologlogy and thereofore avoiding impactsto this important habitat remains outstanding. Please see our comments in relation to this matter in Appendix H7. Natural England agrees to disagree with the Applicant regarding the qaulity and importance of acid graassland. this issue following review of all submitted material. Please see our Deadline 7 Appendix A7 for detailed comments. |  | No | Part Resolved. Loss Of Functionally Linked Land for Sandlings SPA. We note that the HRA has been updated to include the correct quantum of FLL lost for the Suffolk Onshore Scheme for Sandlings SPA. The scheme will affect 7.5 ha of foraging habitat. Clarification is required on the following matters: The updated tracked changes refer to a Natural England IRZ guidance document which is incorrectly quoted. This notes that heathland birds generally forage within 2km of a site boundary, but nightjars can forage up to 4km. If nightjars are absent within the 4km foraging zone that overlaps with Lion Link it is unlikely to change the conclusion regarding Lion Link, however this error should be corrected. It is Natural England’s understanding that the 6ha area was not required to rule out an adverse effect on integrity for the loss of 7.5 ha of foraging habitat for Sandlings SPA for impacts alone. However it remains induded in 8.2.4.
21 | Appendix A1 [REP1-154] Submitted D1. NE Ref 6 | AS-007 - Habitats Regulations Assessment. Impacts from the construction compound (Suffolk). Assessment of the impact of light spilling into the SPA and surrounding areas used by nightjars and woodlark is required as this would extend into the breeding season whilst the compounds are in operation. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change |  | Part resolved: While we acknowledge that the construction compound S10 lighting has now been included in the appropriate assessment, and we welcome that illumination of boundary features will be avoided, we do not accept that the addition to paragraph 7.2.17 constitutes a robust assessment of potential impacts. We advise there is insufficient evidence for the conclusion that there will be no significant impacts to the designated features of Sandlings SPA arising from the HDD construction compound. |  | We advise that the need for clearer information regarding the indirect impacts of noise and lighting on the FLL and clear audit trail of the temporary nature of the impact in order to substantiate conclusions, and that impacts to nightjar are more clearly incorporated. |  | Part resolved. Please see Appendix A7 to our Deadline 7 response. |  | No | Resolved. Based on the additional information provided, we consider that the proposed commitments B23 and B38 to construct a fence of at least 3m arond the compound to shield the SPA from accoustic and light disturbance should be sufficient to address this matter. We note that effectiveness will be monitored
22 | Appendix A1 [REP1-154] Submitted D1. NE Ref 7 | AS-007 - Habitats Regulations Assessment. Noise assessment Natural England advise that the noise contour map included in Appendix E Figure 3 requires additional clarification. This is because it appears to show noise as a uniform contour throughout the working corridor regardless of proposed activity. It is unclear how the impact of HDD for example or construction compounds has been considered in this assessment as it is likely that noise impacts would vary between these activities and this does not appear to be illustrated on the map presented. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadline 3. |  | No change, pending review of documents submitted at Deadline 3. |  | We note the Applicant has included further clarity about the noise contour map in Appendix E figure 3. They have clarified that the extent of the constour shown represents the expected extent of the noise from the noisiest of the proposed activities. This resolves our issue in Appendix A1 submitted at Deadline 1, NE Ref 7. | [5 empty] | Yes
23 | New Issue | REP6-051 - 6.6 (H) Habitats Regulations Assessment Report - in relation to the discharges, as Alde-Ore Estuary designated sites are approximately 6km downstream, we would expect there to be a robust monitoring programme to ensure that runoff does not result in impacts, and we would recommend that a monitoring programme is implemented, including measurement of biological and chemical parameters for any discharged water, to ensure this is the case. | [13 empty] | New issue identified following review of documents submitted at Deadline 6. As this matter has come to light late in the Examination, we advise that an appropriately worded commitment should be added to the REAC detailing the chemical and biological parameters that the discharged water will meet and how this will be monitored and managed throughout the lifetime of the project. Please see our advice in Appendix A7 in our Deadline 7 response. |  | No | Unresolved. No new commitment has been included within REAC GH09, However, this doesn't address requirements to monitor potential impacts
24 | New Issue | REP6-051 - 6.6 (H) Habitats Regulations Assessment Report - Unexploded Ordnance (UXO) investigation will be needed at the proposed trenchless launch pit and along the route of the trenchless installation in North Warren RSPB Reserve and Leiston-Aldeburgh SSSI. We also note that detonation of UXO in situ may be required. | [13 empty] | New issue identified following review of documents submitted at Deadline 6. As this matter has come to light late in the Examination, we advise that the measures discussed are secured through an appropriately worded REAC commitment, please see our advice in Appendix A7 in our Deadline 7 response. |  | No | Unresolved. This was responded to via SoS response (18/09/2026). If the proposed wording is used then this should be resolved.

## B - Kent Onshore
Point | Point Number(s) from Appendix B RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix B - Kent Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | B1, B6 | Further assessment work is required to determine whether Horizontal Directional Drilling (HDD) is a viable mitigation method to avoid direct loss of Thanet Coast and Sandwich Bay Special Protection Area (SPA)/Ramsar site and Sandwich Bay Special Area of Conservation (SAC). Natural England strongly advises that geotechnical investigations should be provided to inform the consenting phase to give the Secretary of State the level of comfort required on the feasibility of this installation technique. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
2 | B1, B5, B11 | An outline intertidal and HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
3 | B1, B30-33 | Full consideration should be given to hydrological impacts of HDD, particularly upon the humid dune slacks feature of the Sandwich Bay SAC. The assessments should be updated. With groundwater investigations used to determine location of habitat mapped in relation to the two aquifers, and dewatering zones of influence to assess potential for impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
4 | B1, B28 | The likely impacts of the drilling equipment becoming stuck and subsequently requiring excavation needs to be considered in full in the HRA and discussed in detail in an outline contingency plan within an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied with the Applicant’s response confirming that in the event that equipment should become stuck no excavation to recover stuck equipment would be undertaken along the Kent HDD route beneath areas of saltmarsh or shallow lagoon. | [11 empty] | Moved to Tab J
5 | B2, B14, B16 | In order to provide sufficient detail to the ExA regarding potential air quality impact pathways, it should be clarified if in-combination impacts are likely. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter. | [11 empty] | Moved to Tab J
6 | B2, B14, B16 | Clarity should be provided regarding the length of time that Non-Road Mobile Machinery (NRMM) will be used and the screening distance applied. Where NRMM is below 20MW, the screening distance should be 500m. Where use of NRMM is only to be used for periods of under a year within an impact risk zone, then impacts are less likely as AQ is considered on an annual average basis. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter. | [11 empty] | Moved to Tab J
7 | B3, B38 | Percussive and disturbing works (e.g. piling) to install pylons either side of Sandwich Bay to Hacklinge Marshes SSSI should be undertaken outside of the breeding bird season to avoid a significant impact upon the SSSI. In addition, the required operational works should also be undertaken outside of the breeding bird season. These measures should be secured within the Register of Environmental Actions and Commitments (REAC). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Commitments B45 and B50 in the REAC have been updated so that any works >60dB at the SSSI boundary will take place outside of breeding bird season. In addition, percussive and disturbing works (e.g. piling) will take place outside of breeding bird season. Operational works - have queried why restriction on works can't cover the entirety of breeding bird season. |  | No Change |  | No Change |  | No Change. Natural England refer the Applicant to our previous advice in [REP4-068] re. avoiding construction during the breeding bird season where practicable, securing an ECoW to oversee all relevant works and updating your REAC measures to reflect this It remains Natural England’s advice that the bird breeding season should be considered to be March to September inclusive, and that any works which are likely to disturb breeding birds should preferably be timed to avoid these months. [REP4-068] section 1.6.1 has been updated to include the appointment of an ECoW, and Natural England ask that the REAC is updated to include reference to this measure under B45, B50 and B65 (similarly to how B02 has been worded under REP4-234 9.84 (B) REAC February 2026. Provided that these commitments are secured within a named plan/document, Natural England will be satisfied there will be no likely significant impact upon Sandwich Bay to Hacklinge Marshes SSSI due to construction disturbance. |  | It remains Natural England’s advice that the bird breeding season should be considered to be March to September inclusive, and that any works which are likely to disturb breeding birds should be timed to avoid these months wherever practicable. Please refer to Appendix B6, Table 1 submitted at Deadline 6 for more information about resolving this issue. Natural England has discussed with the developer and expect information to be submitted at Deadline 6 that will allow resolution of this Issue. |  | Natural England advises that this point could be resolved by updating all references to the Breeding season to March - September, inclusive, OR by including reference to securing an ECOW in the relevant REAC commitments (B45 and B65). Please refer to Appendix B7, Table 1, Point 1; Table 4, Point 1; Table 5, Point 1 and; Table 7 Points 1, 2 and 4, as submitted at Deadline 7 for the specific locations that need updating. Following further conversations with the Applicant on 27th Apr, Natural England would consider this issue resolved, if the agreed changes have been made at D7. |  | No | Additional Wording has been added to clarify that the breeding bird season is March through September inclusive, that any works causing noise levels above 60dB Lamax at the boundary of the SSSI will take place outside March through August, and that where such works are to be undertaken during September, an Ecological Clerk of Works will check the area to confirm the absence of qualifying nesting bird features of the SSSI. Natural England welcome these changes and consider this issue (R&I Log Point 7) to be resolved.
8 | B4 | The Phase 1 maps should be updated to indicate whether standing water is freshwater, saline or brackish as per the JNCC 2010 guidance. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. Please Appendix B3 [REP3-117]. | [11 empty] | Yes
9 | B6 | Geotechnical investigations should be provided to confirm whether HDD installation methods are suitable/feasible at the Pegwell Bay cable landfall location. If a trenchless technique is found not to be valid then there is a high risk of an Adverse Effect on Integrity and that a full derogations case would need to be presented including appropriate compensation measures |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
10 | B7 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
11 | B8 | The definitions for moderate adverse (negative) impact and major adverse (negative) impact should be reviewed to ensure there is a clear difference between the two effects and consideration should be given by the Applicant as to whether this changes to the conclusions of the assessments. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. Please see Appendix B3 [REP3-117]. | [11 empty] | Yes
12 | B9 | Table 2.12 should demonstrate the pathway for consideration of LSE at individual site feature level, including a column identifying the habitat/species receptors being considered in each case. This should include screening in the potential pathway for hydrological impacts of construction (HDD) upon groundwater dependent H2190 Humid Dune Slack feature of Sandwich Bay Special Area of Conservation (SAC). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Applicant directed to a table provided in Appendix A of the HRA which provides this level of detail and Natural England agree it is unnecessary to repeat this. Please see Appendix J3A [REP3A-028] to our Deadline 3a response | [11 empty] | Yes
13 | B10 | The hoverport site should be subject to a management program to remove target invasive plant species before any work commences and comprehensive biosecurity measures during construction and O&M to reduce the risk of spread. This should be secured in the DCO/dML and/or within a named plan. The Non-native Species Management Plan (7.5.12) should be updated to include the hoverport site and route of access as a pathway for potential spread. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied that the risk of INNS introduction at the former hoverport has been considered and the appropriate controls put in place to manage this risk. Please see Appendix J3A [REP3A-028] to our Deadline 3a response | [11 empty] | Yes
14 | B12 | Confirmation should be provided that the written scheme of decommissioning will consider impacts to ecological receptors (including designated sites) in consultation with relevant stakeholders and statutory bodies. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Recommendation that commitment GG31 is strengthened in line with the Applicant’s response to our Relevant Representations comment B12, to read: ‘A written scheme of decommissioning will be submitted for approval to the relevant planning authority at least six months prior to any decommissioning works. This would consider environmental impacts as required at that point in time, including to ecological receptors and designated sites’ |  | No Change |  | No Change |  | Resolved: Natural England notes that this measure, proposed to address environmental impacts associated with decommissioning works, has been updated to reflect our previous advice, and consideres the issue resolved for onshore matters. |  | Natural England have accepted the changes made for REAC committment GG31 and consider this resolved |  |  |  | Yes
15 | B13 | Nationally designated sites should be considered a highly sensitive receptor to dust impacts, given their national importance, and ES chapters and assessments should be updated to reflect this. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change |  | No Change |  | No Change |  | Resolved following review of document [REP2-014] and further signposting provided by Applicant. | [5 empty] | Yes
16 | B17 | The Applicant should confirm the relevant pollutants emitted by the NRMM that could interact with ecological receptors |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter. | [11 empty] | N/A
17 | B19 | All references to loss of functionally linked land for golden plover should be updated from an operational phase impact to a construction phase impact and assessments updated accordingly. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | While the change is not essential to the outcome of the assessment, as the impact has still been considered and satisfactorily mitigated, it should be made for completeness. |  | No Change |  | No Change |  | Part Resolved: References to loss of functionally linked land have not been updated to show as a construction phase impact rather than an operational phase impact. Natural England note that the Applicant has questioned whether this change is essential in their response to our Relevant Representations comment B19, and advise that while the change is not essential to the outcome of the assessment, as the impact has still been considered and satisfactorily mitigated, it should be made for completeness. |  | No Change, see previous advice; all references to functionally linked land should be updated to a construction phase impact. |  | No Change, see previous advice; all references to functionally linked land should be updated to a construction phase impact. |  | No | No Change
18 | B20 | The list of features of Sandwich Bay SAC in Paragraph 3.73 is incomplete and should be updated to include the missed features, with the assessment updated accordingly. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. | [11 empty] | Yes
19 | B22 | The Conservation Objectives listed for Thanet Coast SAC are incorrect and should be updated. The assessment should be updated to determine if these conservations objectives are likely to be hindered by the proposed works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. | [11 empty] | Yes
20 | B23 | The threats and pressures identified in the 2015 Natural England SIP for Thanet Coast should be added into section 3.14.4 and assessments updated to determine if these pressures will hinder the conservations objectives. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. | [11 empty] | Yes
21 | B24 | Natural England advises that [APP-3920] Para. 4.4.33 is updated to included consideration of operation traffic emissions. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Completed [REP1-071] 4.4.36 | [11 empty] | Yes
22 | B25 | Natural England advises that the in-combination assessment for the Kent Onshore Scheme is checked by the Applicant to ensure that all appreciable effects that are not significant alone have been taken into consideration |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied with the proposed avoidance/mitigation measures. While progress is noted, we question why these works cannot be restricted throughout the entire breeding season (March–September inclusive), once this addressed we should be able to agree that there will be no significant impact upon Sandwich Bay to Hacklinge Marshes SSSI as a result of the proposal. |  | No Change |  | No Change |  | We note that the Applicant intends to retain the text and consider that this matter is now for information as it does not materially change Natural England's advice. | [5 empty] | Yes
23 | B29 | Seawater pumps used to flush saltmarsh vegetation should be operated at low pressure (<50psi) to reduce damage to vegetation/foliage and minimise potential for erosion of surface sediment. This should be confirmed in an Outline HDD Management Plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
24 | B38 | The frontal edge of the saltmarsh is exposed and vulnerable to erosion, and sensitive annuals grow from the surface of the mudflat which are easily overlooked and damaged by trampling. Natural England advise implementing a commitment to a minimum stand-off distance for vehicles and machinery at the HDD exit points. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. | [11 empty] | Moved to Tab J
25 | B39 | Any tree height maintenance for the new Over Head Line (OHL), scrub opening for access to Sandwich Bay to Hacklinge Marshes SSSI, or other similar works should be undertaken outside of the breeding bird season to avoid disturbance, and this should be secured within the Register of Environmental Actions and Commitments (REAC). Natural England is currently unable to agree with the Applicant that there is unlikely to be a significant impact upon Sandwich Bay & Hacklinge Marshes SSSI, due to the concerns regarding timing potentially disturbing works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Query why the operational works can't take place completely outside of breeding bird season. |  | No change. |  | No change. |  | No Change. See Response to Point 7 above Provided this approach is appropriately secured in a named plan/document, Natural England is satisfied that any necessary tree works, which we understand are likely to be minimal and infrequent, should be able to avoid impacts on breeding birds. |  | No Change. See Response to Point 7 above Provided this approach is updated in the REAC measures and therefore appropriately secured in the named plan/document, Natural England is satisfied that any necessary tree works, which we understand are likely to be minimal and infrequent, should be able to avoid impacts on breeding birds. Natural England has discussed with the developer and expects information to be submitted at Deadline 6 which will allow resolution of this issue. |  | The REAC submitted at Deadline 6 had not been updated to reflect that works should be untertaken outside of the breeding season (March - September, inclusive) OR by including reference to securing an ECOW in the relevant REAC commitments (B45 and B65). Therefore our advice remains unchanged. Please refer to Appendix B7, Table 7, Point 4 for more the required update. Following further conversations with the Applicant on 27th Apr, Natural England would consider this issue resolved, if the agreed changes have been made at D7. |  | No | Natural England is content with the commitment B55 that the Pylons for the overhead lines will be outside of the SSSI. However, While Natural England welcomes the commitment at B45 to avoid the breeding season where practicable for Sandwich Bay and Hacklinge SSSI, the commitment permits works occurring over any 2 month period in the breeding season. This is on the basis that an Ornithologist will check for active nests. But for this to be sufficient mitigation to avoid damaging impacts we advise the area of search needs to clearly defined based on type of activity, direct area of impact of ‘activities taking place’ and adoption of a suitable disturbance buffer. We also highlight that this commitment should not only apply to notified features of the SSSI, but also all breeding birds under the Wildlife and Country Side Act 1981 (as amended by CROW) and in particular Schedule 1 Species at this location.
26 | B41 | Natural England has been made aware by the Applicant’s ecologist that no Letters of No Impediment will be required. Should this change, we recommend that the Applicant make available draft protected species licences for our wildlife licencing team to review. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 3 |  | No change. |  | No change. |  | Resolved. Natural England acknowledges that this is an advisory comment with no further actions required at this point in time. | [5 empty] | N/A
27 | B45 | The final BNG assessment should incorporate separate accounting lines to ensure a 10% net gain is being achieved. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  |  |  | No change. |  | No change. |  | Resolved following review of document [REP2-014] and further signposting provided by Applicant. | [5 empty] | Yes
28 | New Issue | REP6-051 - 6.6 (H) Habitats Regulations Assessment Report - in relation to the discharges from Minster Converter Station, as Thanet Coast and Sandwich Bay SPA and Ramsar is downstream, we would expect there to be a robust monitoring programme to ensure that runoff does not result in impacts, and we would recommend that a monitoring programme is implemented, including measurement of biological and chemical parameters for any discharged water, to ensure this is the case. | [13 empty] | New issue identified following review of documents submitted at Deadline 6. As this matter has come to light late in the Examination, we advise that an appropriately worded commitment should be added to the REAC detailing the chemical and biological parameters that the discharged water will meet and how this will be monitored and managed throughout the lifetime of the project. |  | No | Part Resolved Natural England welcomes in GG15 the inclusion of a 10m buffer applied to water courses and measures to avoid run off. However, we will differ to the EA on the sufficiency of this. But still require a commitment to monitor this
29 | New Issue | REP6-051 - 6.6 (H) Habitats Regulations Assessment Report - Unexploded Ordnance (UXO) investigation will be needed at the Minster Station and Substation site and other locations close to the Sandwich Bay to Hacklinge Marshes SSSI. We also note that detonation of UXO in situ may be required. | [13 empty] | New issue identified following review of documents submitted at Deadline 6. As this matter has come to light late in the Examination, we advise that the measures above are secured through an appropriately worded REAC commitment, please see our advice in Appendix A7 in our Deadline 7 response. |  | No | Part resolved Natural England welcomes the commitment GG39 to discuss with NE management of impacts from an identified UXO, but it is unclear if this aligns with the MOD’s ‘make safe’ policy. If MOD are in agreement with this then this issue would be resolved. Otherwise we advise the commitment includes the requirement to submit and agree a UXO management plan to the MMO in consultation with relevant SNCB prior to an works commencing
30 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue identified following review of documents submitted at Deadlines 6. Please see the Cover Letter and Appendix G7 to our Deadline 7 submission. |  | No | Resolved Natural England welcomes the inclusion within the commitment to agree Hovercraft egress and routes post consent with ourselves prior to construction and welcome the definition of ‘emergency works’, But feel it could be strengthen by included ‘…make safe’ We consider Hovercraft use now resolved.

## J - Kent Landfall
Point | Point Number(s) from Appendix B RR-3920 or Appendix J3A [REP3A-028] | Taken from Natural England’s Submission to Deadline 3A Sea Link Energy Cable Appendix J - Kent Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
RI_J1 | B1, B6 | Further assessment work is required to determine whether Horizontal Directional Drilling (HDD) is a viable mitigation method to avoid direct loss of Thanet Coast and Sandwich Bay Special Protection Area (SPA)/Ramsar site and Sandwich Bay Special Area of Conservation (SAC). Natural England strongly advises that geotechnical investigations should be provided to inform the consenting phase to give the Secretary of State the level of comfort required on the feasibility of this installation technique. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Please see response to ExQ2 ECOL6. Risks remain to the Applicant if it is found post consent that HDD is not a viable option. Therefore, we advice that the level of comfort is not going to be available at the time of consent. | [5 empty] | Yes
RI_J2 | B1, B5, B11 | An outline intertidal and HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Please note that at Appendix E5 to our Deadline 5 submission we have both new and outstanding issues. Where we have made reference to the Landfall Method Statement, Drill Fluid Management Plan and Landfall CSIP this would resolve the second part of our R&I point. Once these have been addressed we would consider this matter satisfactorily resolved for the consenting phase. |  | See Appendix D6, this issue remains unresolved appropriate conditions are required. | Alan- Noted a landfall method statement is now secured within the Applicant;s draft DCO. Within the ExA draft DCO | Natural England notes at B59 of REAC [REP6135] a landfall method statement is now secured |  | Yes
RI_J3 | B1, B30-33 | Full consideration should be given to hydrological impacts of HDD, particularly upon the humid dune slacks feature of the Sandwich Bay SAC. The assessments should be updated. With groundwater investigations used to determine location of habitat mapped in relation to the two aquifers, and dewatering zones of influence to assess potential for impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | This was tranposed over from Tab B in error and was resolved at Deadline 3 | [5 empty] | Yes
RI_J4 | B6 | Geotechnical investigations should be provided to confirm whether HDD installation methods are suitable/feasible at the Pegwell Bay cable landfall location. If a trenchless technique is found not to be valid then there is a high risk of an Adverse Effect on Integrity and that a full derogations case would need to be presented including appropriate compensation measures |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Natural England welcomes the commitment to undertake trenchless cable installation under the saltmarsh, any deviation from this post consent will require a DCO/DML change request. Please see response to ExQ2 ECOL6. Risks remain to the Applicant if it is found post consent that HDD is not a viable option. Therefore, we advise that the level of comfort required is not going to be available at the time of consent. | [5 empty] | Yes
RI_J5 | B7 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Please see response to ExQ2 ECOL6. Risks remain to the Applicant if it is found post consent that HDD is not a viable option. Therefore, we advise that the level of comfort required is not going to be available at the time of consent. Natural England also advises in Appendix E5 or our Deadline 5 submission that the commitment for the Landfall Method Statement (LMS) and Drill Fluid Management Plan (DFMP) is updated to reflect our regulatory advice |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 and E7 where concerns with access on to intertidal are raised |  | No | No Change. Please see cover letter
RI_J6 | B29 | Seawater pumps used to flush saltmarsh vegetation should be operated at low pressure (<50psi) to reduce damage to vegetation/foliage and minimise potential for erosion of surface sediment. This should be confirmed in an Outline HDD Management Plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Natural England welcomes at B61 [REP4-234] that the REAC has been updated to include handheld equipment only. If this is updated to limit water pressure to <50psi this issue would be resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Resolved. This is address within B61 of the REAC [REP6-135] |  | Yes
RI_J7 | B38 | The frontal edge of the saltmarsh is exposed and vulnerable to erosion, and sensitive annuals grow from the surface of the mudflat which are easily overlooked and damaged by trampling. Natural England advises implementing a commitment to a minimum stand-off distance for vehicles and machinery at the HDD exit points. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change |  | Natural England welcomes the commitment to ensure a minimum stand-off distance for vehicles and machinery at the HDD exit pitts and the saltmarsh. Commitment B69 from the Applicants REAC states: Trenchless crossing exit pits in Pegwell Bay will be at least 105 m seaward from the edge of the saltmarsh. The temporary working area will be located at a minimum distance of 50 m from the edge of the saltmarsh. However, we advise to resolve this issue that 'the edge of the saltmarsh' must be agreed with the regulators in consultation with the relevant SNCB as part of LMS/CSIP prior to the commencement of works. Also please see further comments in relation to the location of the exit pits, cofferdams and potential implications of saltmarsh from their presence. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | While we welcome securing the commitment of a buffer around saltmarsh habitats in the DCO, Natural England has raised concerns in Appendix D7 in relation to the exit pit loations and the current edge of the saltmarsh |  | No | No Change. Please see cover letter in relation to trenchless techniques and commitment B43.
RI_J8 | [REP3A-028] Table 2, point 10 - ref 7.3.68; Table 3, points 4 (ref table 3) & 5 (ref 4.3.42) | Based on the current information provided we cannot agree with the HRA conclusion on the significance of temporary disturbance. Full assessment of all protected site features and the potential impact pathways over the lifetime of the project is required and consideration given to how to reduce impacts wherever possible. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | Please see Appendix J4 to our Deadline 4 submission |  | Natural England wishes to highlight that there are still outstanding impacts that have not been considered (please see Appendices D5 & E5) including: - impacts to peat and clay exposures and subtidal chalk, - phased approach to the CSIP, - sediment disposal, suspended sediment concentrations and boulder clearance, - the MDS for temporary rock bags/concrete mattresses at the HDD exit pits/ducts, - disturbance of intertidal mud/sand flats, - potential contamination risk from disused hoverport, - recoverability of the intertidal mud/sand flats and saltmarsh habitats to pre-construction conditions, Please also see responses to the ExA's Q2 GEN3, ExQ2 MO5 and ExQ2 PE4 in Appendix K5 to our Deadline 5 submissions. |  | See Appendix D6, we still consider that there are outstanding impacts that have not been considered. |  | Part Ressolved. Please see Appendix D7 and E7 where we highlight our remaining concerns with access on to intertidal |  | No | No Change
RI_J9 | [REP3A-028] Table 2, point 6 - ref 5.3.8; Table 5, point 4 - ref B68 | It is the view of Natural England that AEoI on SPA/Ramsar or significant impacts to the SSSI can not currently be excluded. Further commitments are required at the consenting phase to mitigate impacts. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | As above - no change. |  | As above, no change. |  | Part Ressolved. Please see Appendix D7 and E7 where we highlight our remaining concerns with access on to intertidal |  | No | No Change
RI_J10 | [REP3A-028] Table 3, point 8 - ref 7.4.13; Table 5, point 4 - ref B68; and Table 6, point 1 and point 15 | A requirement/condition should be included within the DCO/dML to ensure that the final Landfall Construction Method Statement (LCMS) and Drilling Fluid Management Plan (DFMP), is agreed with the regulators in consultation with the relevant SNCB prior to construction. Within which it must demonstrate that the potential impacts are no greater than predicted and any divergence will need a further assessment prior to construction and where necessary further permissions sought. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England weclomes the commitment to provide a LMS (REAC 68) [REP4-234]. However, we note that both this and the REAC 59 do not include the correct wording in relation to "agreed with MMO in consultation with the relevant SNCB". Please see Appendix E5 to our Deadline 5 response for more detail. |  | See Appendices D6 and E6 to our Deadline 6 submissions. Natural England still advises that appropriate conditions are provided to secure mitigation and monitoring, along with a condition to secure remediation should monitoring be required. |  | Resolved. This is address within B59 of the REAC [REP6-135] and is included with the CEMP which is a named plan |  | Yes
RI_J11 | [REP3A-028]: Table 2, point 5 - ref 4.4.2 and Table 2, points 1 & 2 ref (3.7.1); Table 6, point 13 (table 5.1)and point 4 - ref 2.2.7 | The potential impacts from vehicles transiting the intertidal area need to be fully assessed in terms of cable installation and/or repair/ replacement of cables to assess potential changes to habitat features and protected species over the lifetime of the project. Particularly in relation to impact pathways to intertidal habitats and SPA features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No Change |  | No change. The Applicant has advised updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | See Appendix D6, queries remain on the MDS including for the vehicle access especially from the hoverport. |  | Part Ressolved. Please see Appendix D7 and E7 where we highlight our remaining concerns with access on to intertidal |  | No | Partilally resolved as agreement will be sought for construction
RI_J12 | [REP3A-028] Table 5, point 3 - ref B67 and Table 6, point 2 - ref 2.2.5 | Further mitigation measures should be considered to reduce the impacts to intertidal habitats and compaction of sediment. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England welcomes the commitment to use Low Ground Pressure (LGP) vehicles, but we note that the parameters are not provided. Natural advises that this commitment is updated to reflect our regulatory advice from our previous submission at Deadline 3A [REP3A-028] Deadline 4 [REP4-191] and [REP4-195] and secured in a named plan/document. In addition, LGP vehicles should have a pressure lower than a human footprint and mitigation measures to minimise impacts from rollers etc should be provided. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Part Ressolved. Please see Appendix E7 where we highlight our remaining concerns with access on to intertidal |  | No | No Change
RI_J13 | [REP3A-028] Table 5, point 6 - Ref B70 | A commitment should be made to only undertake cable repairs/replacement activities where it can be demonstrated that there will be no significant impacts to intertidal saltmarsh at the exit pit or along intertidal transit route. Where this is not possible a separate marine licence and updated assessment of impacts will be required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | No Change |  | No | Partilally resolved as the assessment and agreement on the routes is committed to prior to construction. However the avoidance of signifcant impacts is not committed to
RI_J14 | [REP3A-028]: Table 2, point 3 - ref 4.3.4; Table 2, point 7 - ref 7.3.10; Table 3, point 4 - ref 3.1 and Table 5, point 5 - ref B69; Table 6, point 7 (table 2.1) and point 14 (section 7) | The importance of the saltmarsh environment. It is unclear what the potential impacts to the saltmarsh would be and further consideration and evidence is required in relation to potential impacts from changes in coastal processes from the presence of infrastructure (such as the cofferdams) during installation and possibility of changes in extent of interest features over time. Further evidence should be presented to demonstrated that impacts can be avoided during installation and operation. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix E3a J3A [REP3A-028] to our Deadline 3a submission. |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 where we discuss changes to marine process being minimal. To resolve this issue appropriate monitoring must be secured |  | No | No Change. Please see RFI2 covering letter
RI_J15 | [REP3A-028] Table 5, point 2 - ref B66 [AS-138], [CR1-055] | A commitment should be made to avoid access on to the south-west corner of the hoverport due to the presence of fragmented saltmarsh vegetation. Further clarification is also required regarding impacts to the saltmarsh should the extent of vegetation change both temporally and spatially. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England welcome the inclusion of commitment B67 and B68 in the Applicants REAC, but recommend that our advice provided at Deadline 3A [REP3A-028] Deadline 4 [REP4-191] and [REP4-195] is used to inform mitigation around the use of the hoverport. Namely, in relation to increased damage to the site from its use, and disturbance buffers/separation distances not being sufficient (Appendix D5, Table 1, point 6 and Appendix E5, Point B5-26). Of particular note is the advice to avoid the south-west corner of the hoverport due to the presence of fragmented saltmarsh vegetation. In addition we advise that the commitment to condition surveys and protective measures are described and secured in a named plan/document. Please also see reponse to the ExA's Q2s in Appendix K5 to our Deadline 5 submissions and RI-J10. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | While we welcome securing the commitment of a buffer around saltmarsh habitats in the DCO, Natural England has raised concerns in Appendix D7 in relation to the exit pit loations and the current edge of the saltmarsh |  | No | No Change
RI_J16 | [REP3A-028]: Table 2. point 4 - ref 4.3.41 and Table 5, point 8 - ref MPE04 | It is unclear what the Maximum Design Scenario (MDS) is for cable protection (both temporary and permanent) at the exit pit locations. Information should be updated to provide justification and inform the HRA for the proposed cable protection, clarification regarding the MDS and location, and consider all impact pathways to all protected site features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | See Appendix D6 to our Deadline 6 submision, queries remain on the MDS. |  | Please see Appendix D7 where we request further information and assessment |  | No | No Change
RI_J17 | [REP3A-028] Table 5, point 7 - ref MPE02 | Further evidence on coastal processes is required to support the proposed mitigation measure for seabed lowering at this location. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 where monitoring is discussed in more detail |  | No | No Change
RI_J18 | [REP3A-028] Table 2, point 5 - ref 4.4.2; Table 2, point 9 - ref 7.3.68 and Table 6, point 3, ref - 2.2.6 | Further consideration of disturbance impacts on SPA birds and intertidal habitats from vehicle movement from cable installation and operational activities within the intertidal area is required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England advises that further assessment of the potential for disturbance of intertidal mud/sand flats due to the movement of heavy construction vehicles/plant across the access route from the former hoverport to the HDD working area (see Appendix D5 point 6 for detailed advice). And also ExQ2 GEN3, ExQ2 MO5 and ExQ2 PE4 in our Appendix K5 to our Deadline 5 submission. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Part Ressolved. Please see Appendix D7 and E7 where we highlight our remaining concerns with access on to intertidal |  | No | No Change
RI_J19 | [REP3A-028] Table 2, point 8 - ref 7.3.12, Table 6, point 9 - ref 3.4.3 and point 10 - ref 3.4.7 | The potential for bentonite frac-out needs to be considered and the impact pathways to SPA features need to be assessed, including the likely duration of bentonite remaining on the seabed and the implications for the wider ecosystem with particular note to the smothering of saltmarsh vegetation. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | While this has not been provided we note that there is a commitment at B59 of the REAC [REP6-135] to provide a plan and this could be extended to provide the necessary assessment |  | No | Please see RFI 2 cover letter where the potential change in technique is likely to change the associated risks
RI_J20 | [REP3A-028] Table 5, point 1 - ref B61 | The commitment to remove bentonite where necessary within saltmarsh feature should include "by only using handheld equipment" to ensure there will be no vehicle access onto the saltmarsh. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England welcomes at B61 [REP4-234] that the REAC has been updated to include handheld equipment only. If this is updated to limit water pressure to <50psi this issue would be resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Resolved. This is address within B61 of the REAC [REP6-135] |  | Yes
RI_J21 | [REP3A-028] Table 2, point 1 and table 3, point 7 - ref 4.4.2 | Further clarity is required on the potential impacts at all locations and features where HDD is proposed. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | No change. The Applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | While this has not been provided we note that there is a commitment at B59 of the REAC [REP6-135] to provide a plan and this could be extended to provide the necessary assessment |  | No | Please see RFI 2 cover letter where the potential change in technique is likely to change the associated risks
RI_J22 | [REP3A-028] Table 2, point 11 - ref 7.4.3 | It is unclear with a likely depth of 15-18m for HDD cable installation whether the required HDD installation distance will be achieved. Further assurance is is needed to demonstrate that the depth of installation will not hinder achieving the HDD distance required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3[REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | Natural England welcome the further clarification provided by the Applicant and signposting to [APP-321] regarding the proposed installation parameters and consider this point resolved. | [5 empty] | Yes
RI_J23 | [REP3A-028] Table 3, point 8 - ref 7.4.13 and Table 5, point 4 - ref B68 | The HRA should be informed by an outline HDD/landfall construction management plan which will need to be provided in full at the time of consent in consultation with the relevant organisations. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118]on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | Natural England weclomes the commitment to provide a LMS (REAC 68) [REP4-234]. However, we note that both this and REAC 59 do not include the correct wording in relation to "agreed with MMO in consultation with the relevant SNCB". Please see Appendix E5 to our Deadline 5 response for more detail. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | No Change. This has been pushed to post consent by the Applicant's commiments in REAC [REP6-135] |  | No | No change
RI_J24 | [REP3A-028] Table 3, point 6 - ref 3.47 and point 8 - ref 7.4.13 | Assessment of the direct and indirect impacts from the use of concrete mattresses for landfall works is required, including consideration of any scouring. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | Please see Point 5 of Appendix D5 to our Deadline 5 submissions. Further consideration and assessment of MDS is required to resolve this issue. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 where we request further information and assessment |  | No | No Change
RI_J25 | [REP3A-028] Table 6, point 5 - ref 2.3.3 | Further consideration is required of potential impacts of the proposed large cofferdams being in situ for 120 days. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change |  | Natural England welcomes the further clarification provided by the Applicant regarding the duration of the cofferdams being in situ. However we still have outstanding concerns regarding the impacst from the presence of cofferdams within the marine intertidal, please see Appendix D5 for Marine Processes Table 1, for further detailed comments. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 where we request further information through real time monitoring and redial works |  | No | Please see RFI 2 cover letter where the potential change in technique is likely to change the associated risks
RI_J26 | [REP3A-028] Table 6, point 6 - ref 2.3.3 | The proposed lighting of the cofferdams and associated working area around them needs further assessment in terms of disturbance impacts to Annex I birds (foraging, roosting and nesting) and foraging bat species is required in relation to both temporary habitat loss and impacts from lighting and installation works. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Please see response to the ExA's Q2 ECOL27 in Appendix K5 to our Deadline 5 submission. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix L7 where lighting of cofferdams is considered |  | No | No Change
RI_J27 | [REP3A-028] Table 6, point 8 - ref 3.3.1 | The parameters of the proposed rollers and their associated transportation and installation methods is unclear. A more detailed assessment is required and where possible these should be transported by sea to the intertidal on a barge which can bottom out with ramps so that installation equipment can access intertidal direct from there. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change as there are currently no commitments to manage down the impacts through adoption of appropriate mitigation measures. |  | See Appendix D6 our Deadline 6 submission, Natural England still has queries regarding the MDS for Rollers and no commitments have been made to manage down the impacts through appropriately secured mitigation plans. |  | We have spoken with the Applicant on 16th April and we believe that further information on this and assessment will be provided at Deadline 7 which is likely to address this issue |  | No | Please see RFI 2 cover letter where the potential change in technique is likely to change the associated risks
RI_J28 | [REP3A-028] Table 6, point 11 (table 3.1) | Further consideration to the use of a jack up barge for the construction of the cofferdam is required and the use of the supporting vessels in order to reduce the impacts to the marine environment. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No change. Natural England advises that impacts should be assessed at the time of consent. If that is not possible then it must be demonstrted that mitigation measures will be adopted to avoid significant impacts and hinderance of conservation objectives. |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | Please see Appendix D7 and Annex A to that where impacts from JUB is discussed in more detail |  | No | Please see RFI 2 cover letter where the potential change in technique is likely to change the associated risks
RI_J29 | [REP3A-028] Table 6, point 12 (table 3.1) | Further information is required on the intended use of ballast bags and impacts assessments undertaken accordingly. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Natural England wish to clarify that in terms of oustanding issues of ballast bags - it is the impact assessment of using these in or adjacent to protected areas that needs further clarification. In particular we advise that cable protection which is most readily removable e.g., concrete mattresses and rock bags should be used within and adjacent to MPAs, especially where the risk of sediment transport disruption and changes to marine processes is high (see Appendix E5 table 3&4, and Appendix D5 table 1). |  | No Change: The Applicant's submission up to and at Deadline 5 have not sufficiently addressed our concerns. However, it is anticipated that our position on some issues my change following a meeting with the Applicant on 16th April |  | No Change. This has been pushed to post consent by the Applicant's commiments in REAC [REP6-135]. |  | No | No Change
RI_J30 | Appendix J4 - point 6 | Clarification as to what is meant by 'ponds' is required and how impacts will be reduced | [7 empty] | New issue identified - further to our comments provided at J4 to our Deadline 4 submission. |  | Natural England has received clarification that while included within commitments relating to landfall, commitment B64 in relation to ponds is not relevant to landfall. Therefore, this issue is resolved. | [5 empty] | Yes
RI_J31 | Appendix D4: Table 7. point 2. | Contamination Risk at Kent Landfall - there is evidence relating to the potential release of contaminants and debris from further degradation of the Hover Port. We advise that further clarification and assessment of this issue is required. | [7 empty] | New issue identified - further to our comments provided at J4 to our Deadline 4 submission. |  | No change. Please see our additional advice provided in Appendix D5. Natural England also notes that the applicant responded to this when it was raised by the ExA during ISH2 as summarised in REP4-085, Table 2.1. We acknowlegde that condition surveys will be undertaken for all work areas, including the hoverport, and protective measures such as track matting and structures will be used to protect both vehicles and the surface condition. Natural England advises that the commitment to condition surveys and protective measures are described and secured in a named plan/document - Natural England continue to advise that further assessment on the impacts are required in order to know the full extent of impact including the types of contaminants and condition of the concrete apron. Please see response to the ExA's Q2 ECOL52 in Appendix K5 to our Deadline 5 submission. |  | See Appendix D6, Natural England continues to advise that management, mitigation and monitoring commitments should be appropriately secured through condition, with a further condition securing remediation should monitoring highlight the need. |  | Please see Appendix D7 and E7 where the risks are considered in more detail |  | No | No change. Natural England will welcome the opportunity to be consulted on the Hoverport Condition Monitoring Plan post-consent [REP7-160], including the necessary measures for identifying and managing any potential contamination risk. However, we highlight that currently there is insufficient information to inform understanding of the potential implications for the coastal/marine environment due to use of the hoverport for access during construction and operation.
RI_J32 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue identified following review of documents submitted at Deadlines 6. Please see the Cover Letter and Appendix G7 to our Deadline 7 submission. |  | No | Resolved Natural England welcomes the inclusion within the commitment to agree Hovercraft egress and routes post consent with ourselves prior to construction and welcome the definition of ‘emergency works’, But feel it could be strengthen by included ‘…make safe’ We consider Hovercraft use now resolved.

## C - DCO
Point | Point Number(s) from Appendix C RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix C - Draft Development Consent Order | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | C1, C3 | The definition of commencement within the DCO and dML should be updated to include a separate definition of offshore commencement |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Concerns remain regarding the pre-lay grapnel run. See Deadline 3A Appendix C3a [REP3A-026]. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | No change. The Applicant has advised updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | Natural England has raised new concerns within our Deadline 6 cover letter due to the changes made. Specificially the exclusion of trial trenches implies some trenching may be undertaken prior to any monitoring or agreements on final mitigation plans. The removal of pre lay cable acitivites is appreciated and resolves the original issue raised. |  | No change, see Deadline 6 cover letter. |  | No | No Change. The Applicant's wording does not resolve the issue as the provision of an interpretation of Trial Trenching confirms Trenching may happen within order limits that includes the sensitive intertidal areas, prior to agreement of monitoring or mitigation plans.
2 | C2, C5 | The arbitration article should be appropriately updated |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Resolved. The arbitration Article has been appropriately updated. | [9 empty] | Yes
3 | C4 | The definition of maintain within the DCO / dML should be amended to remove decommissioning and to link to the extent of the work assessed in the ES and consented |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | Partially resolved. Decommissioning has been removed from the DML wording, but no link to the ES is included. |  | No Change. |  | Progressed. The current wording does have some link to the ES, but would still allow for some works that were not originally assessed . |  | No | No change.
4 | C6 | Requirement 6 should be amended to require consultation with relevant SCNB. Consider moving marine only plans to the appropriate section of the dML. Consider including a requirement for an OLEM |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially Resolved. Requirements have been split between requirements and DML, however consultation with SNCB has not been secured. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | Partiall resolved. Natural England is noted as consentee. However, it should be the Relevant SNCB. |  | No Change, several references to Natural England throughout the DCO should be amended to the relevant Statutory Nature Conservation Body. |  | No change, amendments still required. |  | No | Resolved. Natural England are now appropriately included as relevant SNCB.
5 | C7 | Include requirement to secure protection of European Protected Species or required Biodiversity Net Gain (standard requirements in DCOs) |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | No change. Natural England reviewed up to DCO submitted at Deadline 4 our concern remains. |  | No change within the Deadline 5 DCO. |  | No change. |  | No | No Change.
6 | C8 | Schedule 4 should be updated to consider the requirements to consult with relevant SCNBs |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | Resolved. Natural England notes the updates to include requirement to consult.
7 | C9 | The definition of commence within the DCO excludes offshore preparation works. The definition of Offshore preparation works, or/and commence should be amended to remove works significantly impactful to the marine environment |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Concerns remain regarding the pre-lay grapnel run. See Deadline 3A Appendix C3a [REP3A-026]. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | No change. The applicant has advised an updated wording will be submitted at Deadline 5. Natural England will advise at Deadline 6 if this issue is resolved. |  | Natural England has raised new concerns within our Deadline 6 cover letter due to the changes. Specificially the exclusion of trial trenches implies some trenching may be undertaken prior to any monitoring or agreements on final mitigation plans. The removal of pre lay cable acitivites is appreciated and resolves the original issue raised. |  | No change. See Deadline 6 cover letter. |  | No | No Change. The inclusion of a definition of Trial Trenching has not excluded the possibility that trial trenching may occur within sensitive habitats prior to approval of any monitoring or mitigation plans.
8 | C10 | The DCO should be amended to include the requirement to micro-site around any features of conservation importance, in particular those listed under Section 40 and 41 of NERC 2006. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | No Change, Natural England has reviewed the Deadline 4 DCO and no micro siting requirement has been secured. |  | No Change, Natural England still requires these conditions, see appendnix E6 and L6. |  | No change. Risk upgraded as no progress has been made and this is a key concern. Natural England generally supports the wording the ExA proposed, but has suggested some amendments. If included this would resolve this issue. |  | No | Updated, there is now a requirement to mitigate where necessary. However, this wording is vague and should include some detail as to what to micro-site around. Such as around benthic features of conservation or ecological importance.
9 | C11 | The dML should include conditions to secure pre and post works monitoring as required and set out in an In Principle Monitoring Plan (IPMP). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5. |  | No Change, Natural England has reviewed the Deadline 4 DCO and the monitoring requirements have not been secured. Our position remains that the monitoring should be secured via appropriate condition such as those used for OWF DCOs and provision of an Offshore In Principle Monitoring Plan. |  | No Change, Natural England still requires these conditions, see appendnix E6. Risk rating increased due to the lack of progress on this issue and the likelyhood of resolution prior to the end of examination. |  | Progressed. DML now includes requirement for an In Priciple Monitoring Plan. However, does not incldue appropriate monitoring conditions. NE supports the ExA proposed wording for monitoring conditions and note this wording would resolve our concerns. |  | No | Partially resolved. Pre construction monitoring has been appropriately secured. However, no post construction monitoring has been secured.
10 | C12 | The Applicant should provide an Outline Offshore Operations and Maintenance Plan (OOMP) and the DCO should be appropriately updated to note this as a certified document, and the interpretation of maintain within the DMLs should be updated to reflect that the extent of maintain is as detailed within the Outline OOMP. Raised at Deadline 4 see Appendix G4 for details. |  | New issue |  | New issue |  | New issue |  | Raised at this Deadline. |  | No Change. Natural England is aware the Applicant is updating the Outline Cable Specification and Installation plan to address maintenance. We will review the document expected at Deadline 5 and provide an update at Deadline 6 |  | No change, Natural England reviewed the outline Cable and Installation plan but this has not changed our opiion on the need for an OOMP. |  | No change. |  | No | No change.
11 | C13 | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. |  | New issue |  | New issue |  | New issue |  | Raised at this Deadline. |  | No change, Natural England has reviewed the Deadline 4 DCO and this has not been addressed. We will review future versions of the DCO for any change in position. |  | No change, however at meeting 1st April the Applicant indicated they would be willing to accept the 2km buffer. We expect the DCO to be updated. |  | Natural England notes the 2km buffer has not been included. We support the wording of the ExA schedule of changes for securing the 2km buffer, if included this would resolve this issue. |  | No | Resolved. The condition now includes the 2km buffer and that this applies to monitoring and maintenance.
12 | C14 | Natural England notes that a number of issues have been addressed by inclusion of mitigation plans within the REAC. However, the REAC is not secured through condition under the DML, therefore, we question if this is appropriately secured. We note these provisions do not allow for updated plans to be submitted to and approved by the MMO as regulator, in consultation with the relevant SNCB. This is a standard approach for securing mitigation. We would question if the MMO supports the proposed approach. Please also see Natural England's advice provided at Deadline 5 submission in Appendix K5 ExA 2nd Written Questions point 2GEN26; 2ECOL51 and 2ECOL52, in addition to the advice provided in Appendix E5 point E5.18, E5.24, E5.25 and E5.31. Also the Risks and Issues log point 9 (C11) above. |  | New issue |  | New issue |  | New issue |  | New issue |  | Raised at this deadline. |  | Natural England notes the Offshore mitigation is secured through requirement 6 and a reference to a offshore construction and environmental management plan, this plan is not detailed in requirement 6 and should be secured within Schedule 16. |  | Progressed. The plan now links to Schedule 16 Part 2 Condition 4. However, our other conerns with regard to the REAC and the provisions within remain. We consider points 24-31 of the ExA Schedule of Changes would significantly advance and resolve several of our issues. See Appendix C7. |  | No | No change

## D - Physical Environment
Point | Point Number(s) from Appendix D RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix D - Physical Environment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | D1, D32 | The Applicant should clarify whether cable protection measures are required adjacent to Goodwin Sands MCZ, with WCS parameters for cable protection measures provided, and potential impacts to supporting sediment transport processes assessed for the lifetime of the project. The Applicant should also consider the potential indirect effect of placing cable protection measures adjacent to the MCZ in terms of influencing sediment transport and seabed morphological change. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. |  | No change, Please refer to Appendix D5 for our latest advice. |  | No Change: Natural England welcomes the information provided by the Applicant in [REP5-020] on the High Court of Justice (2019) report and MMO Stage 3 Assessment for Goodwin Sands MPA. However, these do not address our concerns regarding the potential for morphological and sedimentary change due to the placement of cable protection adjacent to the MCZ. We advise that this issue may be resolved, and understanding increased, with additional assessment of the geomorphology, morphodynamics, sediment transport pathways, scour potential etc. This should be achievable using the data available to the Applicant. Please also see Appendix D6. |  | No change. We advise that the Applicant should either (a) assess indirect effects on Goodwin Sands MCZ due to the placement of WCS 3.2km cable protection measures adjacent to the MCZ boundary, or (b) commit to not allowing the placement of cable protection measures adjacent to the MCZ based on a high-level of confidence that successful cable burial will be achieved through the lifetime of the Proposed Project. We also signpost to Appendix D7. |  | No | Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
2 | D2, D10 | A more detailed analysis of the longer-term morphological trends through the lifetime of the Project should be provided to inform the cable burial and asset integrity assessment and assess potential for significant morphological change within Pegwell Bay including beach profile elevation at Pegwell Bay, progradation of Shell Ness and migration of the River Stour channel |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Issue progressed but not resolved. Adequately managing the risks and uncertainties for cable exposure and landfall infrastructure vulnerability is of vital importance. Further assurance is needed to demonstrate that landfall infrastructure and construction activities will not be affected by morphological change over the project lifetime (i.e. 40-60 years) or vice versa, by altering coastal processes and affect coastal morphology and/or sensitive benthic/supporting habitats. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | No change. We advise that further detailed analysis is needed to increase understanding of the current and future River Stour mouth/channel elevation level relative to cable route and also the likely depth of the buried cable. Additional mitigation measures also need to be explored such as a deeper burial depth and/or potentially moving the cable route further north. Please also see Appendix D6. |  | Issue progressed. We advise that the Applicant should commit to monitoring of the River Stour Channel as soon as possible to inform the baseline, impact assessment, and detailed engineering. We also advise further assessment of the low water channel/river mouth topography and morphodynamics and migration of the spit to the south. The trigger point (distance of cable from migrating river channel/mouth) and contingency actions should be defined within MPE09. |  | No | Progressed. The risk remains that a migrating Stour channel could interact with the installed cable. However, we welcome the update to the IPMP [REP7-168] in which the Applicant has committed to monitoring the River Stour Channel post-consent through pre-installation surveys and throughout the operational life of the asset. A trigger for consultation with the EA has also been included if the Channel migrates to within 50m of the cable. This is welcomed. The monitoring proposed to assess impacts to coastal erosion at Pegwell Bay is restricted to the trenchless technique construction areas associated with the exit pit and does not consider potential impacts to coastal receptors due to cable installation and operation. We continue to advise that monitoring at landfall should encompass the full extent of the nearshore/intertidal areas that may be affected by cable installation/operation. Further advice is provided in Appendix D8.
3 | D3, D13 | The Environmental Statement (ES) should be updated to include relevant information, including: Dispersion model validation Hydrodynamic modelling and model that provided the tidal conditions (Appendix 4.1A) |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 1A, Change Request, and Deadline 2. We advise that this information should be provided to support Document 6.3.4.1.A ES Appendix 4.1.A [APP-195]. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission |  | Issue progressed. Natural England notes and welcomes the Applicant's signpost to the hydrodynamic model calibration details provided in Appendix 4.1 to [APP195]. However, with regards to the validation of the sediment dispersion model, in [APP-195] the Applicant identified an offset between model sediment release location and survey grab sample locations. For two locations this offset is almost 1km. We are, therefore, concerned that model release locations may not be representative of site conditions. Furthermore, the Applicant stated that sediment properties for the model sediment release locations would be checked against the latest sediment sample data, when this information becomes available, to assess the validity of results at the sediment release locations. We, therefore, advise that this validation analysis should be provided for all sediment release locations and submitted into Examination. |  | Issue progressed. We note in [REP5-132] that [APP-195] suspended sediment modelling will be updated in preparation for ISH3. This is welcomed. We look forward to reviewing the updated modelling report and will update our advice as appropriate. |  | Natural England welcomes the additional modelling [REP6-120] carried out by the Applicant for both landfalls. We also note the Applicant's signpost to Appendix 4.1.A in [APP-195] which details the hydrodynamic model calibration, which is welcomed. We also note the Applicant's response [REP1A-043] that there is no known precedent of the requirement to demonstrate validation of a particle-tracking model used to simulate sediment dispersion, which is acknowledged but does not address our original request. However, if the Applicant can commit to the monitoring we have recommended in Appendix D7, then this should provide evidence to support and validate the ES conclusions derived from the hydrodynamic and sediment dispersion modelling, and resolve this issue. |  | No | No change.
4 | D4 | Sites for Trenchless cable installation crossings should be listed, rather than mentioning the trenchless installation generically as an option for cable installation anywhere. The Project Description and relevant ES chapters should be updated |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Natural England advises that the Applicant should signpost (in the Description of the Proposed Project document) to the relevant document(s) detailing the location of trenchless crossings, including at landfall. A figure should also be provided showing the location of the landfall trenchless crossings. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission |  | No Change. Our advice at Deadline 3 remains unchanged. We advise that in the Description of the Proposed Project document, the Applicant should signpost to the relevant plan/document that identifies the location of trenchless crossings, including landfall. |  | No change. Please see our advice at Deadline 5, Appendix D [REP5-217]. |  | Natural England is content that the in-service and future cable crossings have been listed in [REP1A-004] including the proposed trenchless crossings with Nemo Link and Thanet OWF cables at the Kent landfall. This issue is resolved. |  | Yes
5 | D6 | An updated assessment to include consideration of the HDD hydrodynamic impacts including (but not exclusively) from the use of any cofferdam, cable protection etc. should be provided to assess whether any ground preparations may affect hydrodynamics and morphodynamics at the Suffolk landfall. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England welcome confirmation that there is no requirement for use of a cofferdam at the Suffolk landfall, can the Applicant signpost/confirm where this commitment is secured? |  | No change |  | No change. |  | We note in [REP4-028] Marine Physical Environment ES Chapter that the Applicant has confirmed that there will be no cofferdams used at the Suffolk landfall. This is welcomed. However, we advise that this commitment should be captured in all relevant documents/plans (e.g. the REAC). |  | Resolved: We welcome the Applicant's confirmation in [REP5-118] that cofferdams at the Suffolk Landfall are not included within the Proposed Project. This issue is resolved. |  |  |  | Yes
6 | D7 | Figure 11 Offshore Seabed Surficial Geology should be updated to include distribution of bedforms at each KP to help consideration of potential environmental impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | We note the updated figures in [REP1-009] which now includes KP markers and the distribution of bedforms. This resolves the issue. | [7 empty] | Yes
7 | D8 | Sandbanks MCZ is not a recognised designated site and is not acknowledged in the Channel Coast Observatory Southeast Regional Coastal Monitoring Programme as a monitoring point. Clarity is needed on which monitoring station was used to obtain the data. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England suggest that this monitoring station is at Goodwin Sands (i.e. the Goodwin Sands waverider buoy). If the Applicant can provide confirmation then this issue will be resolved. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change, awaiting confirmation from the Applicant. |  | No change. We refer the Applicant to our advice at Deadline 3 and advise that, if needed, the Marine Physical Environment chapter should be updated accordingly. This will resolve this issue. |  | Resolved: We note that [REP5-020] still refers to Sandbanks MCZ. However, we note that the relevant waverider buoy has been confirmed as Goodwin Sands Directional Waverider Buoy, which is welcomed. We are content that this issue has been sufficiently clarified. |  |  |  | Yes
8 | D9 | The ES chapter should be updated to include all designated sites relevant to the Offshore Scheme, including figures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 2. All designated sites relevant to the Offshore Scheme should be identified on the relevant maps and figures in the ES Chapter to inform the impact assessment. Figure 6.4.4.1.12 Marine Designated Sites currently only shows designated sites at/close to landfall. |  | No change |  | The Applicant has now included Thanet Coast & Sandwich Bay SPA and Thanet Coast & Ramsar Site in the ES Chapter [REP3-021] which resolves this issue. | [7 empty] | Yes
9 | D11 | Provide the reports and an appendix to respond to the comment: ABPmer. (2024a). Landfall Assessment at Aldeburgh. Sea Link Project – Landfalls sediment modelling. ABPmer. (2024b). Landfall Assessment at Pegwell Bay, Sea Link Project |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. | [11 empty] | Yes
10 | D12 | Clarity is needed on what references were used to determine the expected bedrock geology in the Offshore Scheme. It is also unclear if any sediment dispersion release from the different cable installation methods was modelled assuming sediment in each location has the same composition. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 2. Natural England advises that the Applicant needs to provide the relevant reference or source of evidence upon which their assumption is made regarding the nature of the sub-surface geology, its consolidation, dispersion and amount released during cable installation. We also seek clarification on whether the sediment size fractions modelled were uniform for the different release locations, or representative of the varying sediment composition along the cable route. |  | No change |  | No change. |  | This issue is resolved. The Applicant has clarified that information on sub-surface geology was based on interpretation of the Integrated Geotechnical and Geophysical Survey report [REP2-035]. The Applicant has also confirmed that Particle Size Distribution data for each specific location was used in the sediment dispersion modelling. | [5 empty] | Yes
11 | D15 | To inform the impact assessment, further consideration should be given to potential changes to the wave regime and seabed/nearshore morphology due to the presence of cofferdams during construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The EIA should be updated accordingly, taking into account the larger cofferdam size proposed, seabed disturbance area and volume, blockage potential, and scour potential. Duration and timing of the cofferdam installation and presence should be taken into account. The implications of the larger cofferdam dimensions to the EIA conclusions should be considered and evaluated, in terms of the scale and duration of seabed morphological impacts. This should also include the WCS predicted nearshore seabed recovery time |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No Change. Whilst the Applicant has given further consideration [REP4-028] to the impact on the intertidal morphology due to wave/current effects associated with the presence of cofferdams during construction, we consider it important to provide supporting evidence to demonstrate the recoverability of the intertidal mud/sand flats to pre-construction conditions. Moreover, we advise that the Applicant should commit to post-installation surveys to demonstrate recovery of the intertidal mud/sand flats. We also advise that the Applicant should consider the sensitivity of the saltmarsh to potential blockage effects due to the close proximity of the cofferdams. Please see our advice in Appendix D5. |  | Issue progressed. The Applicant has committed to reinstatement of the excavation pits through both natural and, if required, mechanical backfill within the intertidal mudflats following removal of the cofferdams. However, we advise that the Applicant should commit to post-installation surveys to demonstrate recovery of the intertidal mud/sand flats and to validate predictions of intertidal recovery. We also advise that the Applicant should consider the sensitivity of the saltmarsh to potential blockage effects due to the close proximity of the cofferdams. Please see Appendices D6 and E6 to our Deadline 6 submissions |  | Natural England welcomes the additional modelling carried out by the Applicant [REP6-120] including consideration of the potential for changes to waves and seabed morphology due to the presence of cofferdams at the Kent landfall. In addition, we welcome the Applicant's intention to undertake monitoring at the Kent landfall. This resolves this particular issue, however, please see our advice in Appendix D7 regarding the need to include and provide more specific details of this monitoring. |  | Yes
12 | D16 | Consideration should be given to potential construction and operational impacts to the sandwave-sandbank system present at the approach to Pegwell Bay. |  | Natural England highlighted this issue as 'green' during Rel Reps in error. D16 included from Deadline 3 with the corrected RAG status of 'amber' |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding their resilience and sensitivity to cable protection measures placed on/adjacent to them. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | No change. We advise that further detailed analysis is needed to increase understanding of the sandbank systems. Please also see Appendix D6. |  | No change. Natural England advises that construction- and operational-related impacts on these sandbanks at the approach to Pegwell Bay have not been adequately considered or assessed. Further information/assessment is needed regarding, for example, potential placement of cable protection on/in the vicinity of these important sandbanks, and the scale and extent of construction-related changes to their morphology. Please also see our advice in Appendix D7. |  | No | No change.
13 | D17 | The potential impact to Aldeburgh Napes sandbank morphology due to cable installation have not been clearly stated or assessed. Given the potentially important role played by Aldeburgh Napes in protecting the adjacent coastlines, the potential impact of cable installation on its morphology should be further considered. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The scale/extent of any cable installation and cable protection impacts on the Aldeburgh Napes need to be provided to inform the impact assessment and support the EIA conclusions. Please also see our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice at Deadline 3a [REP3A-027] and Appendix D4 to this Deadline 4 submission. |  | No change. Please see our latest advice in Appendix D5. |  | No Change: We advise that an indication of the scale and extent of potential impacts on Aldeburgh Napes due to construction should be provided. We also remain concerned about potential impacts on Aldeburgh Napes due to cable protection measures and the presence of a cable crossing adjacent to Aldeburgh Napes which could interrupt bedload transport, alter sandbank morphology, and influence shoreline change. This should be considered and further assessed. |  | No change. As above, it is unclear if/how Aldeburgh Napes may be affected by cable installation activities and the presence of cable protection measures/cable crossings on/nearby. Further information/assessment is needed to inform understanding of the magnitude and scale of these impacts on this important (JNCC Annex I) sandbank. Please also see our advice in Appendix D7. |  | No | No change.
14 | D18 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. There remain a number of key geotechnical and construction risks for the Pegwell Bay HDD that will need to be assessed and managed, including drilling fluid loss, groundwater flow into the chalk aquifer, flooding, and collapse of the Bullhead Beds. Therefore, our initial concerns remain. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | Natural England notes in [REP1-111] the Applicant states that the specific details and requirements for additional nearshore boreholes will be confirmed by the Contractor during their detailed design development. This is not best practice as this should be provided at the consenting phase. Especially as, the Applicant anticipates that additional nearshore boreholes will be necessary and are expected to be executed in 2026. In addition, it is stated that National Grid will coordinate with relevant stakeholders, including Natural England to secure the required consents for these planned nearshore borehole activities. We welcome this update from the Applicant and look forward to engagement with the Applicant on the relevant consents. The results from this will inform the final LMS and DFMP to be signed off by the regulators in consultation with NE. If HDD is no longer considered feasible then a DCO/dML material change will be required. No further action is required from the Applicant at this time. |  | Our position remains unchanged since Deadline 5. |  | Our position remains unchanged since Deadline 5. |  | Yes | Please see cover letter to RFI2
15 | D19 | APP-074 should be updated to reflect the need to avoid and where that is not possible minimise impacts to the Coralline Crag when selecting the marine exit site and onwards cable installation works (i.e., impact assessment of the HDD exit options should also be included). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | In [AS-114] it is stated that the HDD exit point will target an exit location that will be designed such that there is not a risk of exiting where the Coralline Crag is at the surface. During detailed design, the HDD contractor will microsite the exit points based on seafloor surveys and ground investigations. However, in [PDA-037] it is stated that all 3 potential points will go through the crag, and it is not stated whether drilling through this geological feature may have any impacts on the crag. This needs to be clarified. Please also see our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | Issue progressed. We welcome confirmation from the Applicant [REP3-021 & REP3-079] that there will be no cable protection placed on the surface of the Coralline Crag outcrop and the HDD exit will be located to the east of a continual section of outcrop. However, we seek clarification on other potential impacts to sub-surface or non-continual sections of Coralline Crag through the lifetime of the proposed project. This is also captured in Appendix D4 of our Deadline 4 submission |  | We welcome the submission of [REP4-102] The Coralline Crag Technical Note and commits to ensuring that the HDDs will exit a minimum of 45m east of the continual Coralline Crag outcrop, thus avoiding direct impacts on the Crag. Whilst the HDD will pass through the Coralline Crag at depth, it is anticipated that this will not lead to collapse of surface outcrops. This resolves our concerns regarding construction-related impacts. However, we wish to see commitment MPE07 go further to ensure that cable protection and any cables which are likely to become exposed are removed at decommissioning and committed to. Please also see our advice in Appendix D5 regarding potential operational impacts on the Crag. |  | No Change: Please see our advice at Deadline 5, Appendix D [REP5-217], Table 1, NE Ref: 4 regarding extending MPE07. |  | Natural England welcomes the updates to [REP-027] which clarifies that there are not expected to be any operational impacts on the Coralline Crag due to jack-up platforms or vessel anchoring, and that cable replacement works within the HDD would be 45m beyond the nearest Coralline Crag outcrop. This resolves this issue. However, please see Appendix D7 regarding the Embedded Measures (Section 1.8) which need to be updated in line with MPE07 by removing reference to placement of rock bags/mattresses at the Coralline Crag. |  | Yes
16 | D20 | Excavated material should be deposited in similar sediment habitats, adjacent to and updrift of the dredge location, this is standard best practice advice especially within designated sites and within the vicinity of sandbanks. The onus is on the Applicant to commit to best practice mitigation measures and therefore align seabed preparation works with installation to reduce the risk of infilling. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | The Applicant states [REP4-242] that all material from pre-sweeping will be deposited within the cable corridor (Order Limits). However, in line with our advice at Deadline 1 and in our Rel Reps, we advise that the Applicant should commit to depositing excavated material in similar sediment habitats, adjacent to and updrift of the dredge location, particularly within designated sites and within the vicinity of sandbanks. |  | We note in [REP5-020] that the mechanism to infill the trench and allow the seabed to revert to natural bedforms is by natural backfill and sediment circulation / deposition. However, as at Deadline 5, we advise that the Applicant should commit to depositing excavated material in similar sediment habitats, adjacent to and updrift of the dredge location, particularly within designated sites and within the vicinity of sandbanks. |  | Issue progressed. We welcome the Applicant’s proposal to deposit excavated sandwave material within the area of pre-sweeping, keeping sediment the same in the sediment cell. [REP6-027] however, this should be secured and the wording needs to be more specific. Please see Appendix D7. |  | No | Resolved: Please see covering letter re amendments to BE05, BE06, and BE07
17 | D21 | Natural England advises that further information on WCS parameters for cable protection and updated assessment of impacts at landfall is required to address consenting risks and issues raised in our relevant/written reps. [RR-3920] |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Further consideration should be given to the risk posed by Stour channel migration to the cable burial depth over the lifetime of the Project. |  | No change |  | No change. The WCS for cable protection and locations remain unclear. Further information is needed. |  | Issue progressed. The Applicant has addressed [in REP4-241] many of our queries and concerns regarding protection at the HDD exit pits during construction and operational phases, which we welcome. However, we advise that the maximum design scenario and magnitude and scale of impacts (such as scour) at both landfalls need to be quantified/further assessed. Please also see our advice in Appendix D5. |  | Issue progressed. The Applicant proposes in [REP5-020] to include an embedded design measure that there will be no infrastructure at the surface in the intertidal and coastal zones over the operational lifetime of the project. Meaning that there will be no interaction of the Proposed Development with coastal/ intertidal physical processes during the operational phase. This is welcomed but it is unclear where this commitment has been made/secured. It should also be clarified whether this commitment includes cable protection. |  | Issue progressed. The updates in [REP6-027] resolves our concerns regarding operational impacts on the Coralline Crag at the Suffolk landfall. However, our concerns remain regarding maintaining adequate depth of burial of the HDD rock bags/concrete mattresses and duct at the Kent landfall. Further assessment is needed of the River Stour low water channel/river mouth topography and morphodynamics and northwards migration of the spit. We also advise the trigger point for contingency actions should be defined within the management measure. Please also see Appendix D7. |  | No | Progressed. Natural England's concerns remain regarding maintaining adequate depth of burial of the HDD rock bags/concrete mattresses and duct at the Kent landfall. The risk also remains that a migrating Stour channel could interact with the installed cable. However, we welcome the update to the IPMP [REP7-168] in which the Applicant has committed to monitoring the River Stour Channel post-consent through pre-installation surveys and throughout the operational life of the asset. A trigger for consultation with the EA has also been included if the Channel migrates to within 50m of the cable.
18 | D22 | Where cable installation activities may alter significant/important bedforms such as Goodwin Sands MCZ, Aldeburgh Napes, Cross Ledge etc., evidence of recovery to sandwave-sandbank should be provided to validate the Applicant’s predictions re: expected to recover and re-establish. Monitoring sandwave-sandbank recovery should be secured in an In Principle Monitoring Plan and dML for associated impacts. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding the resilience and sensitivity of any affected mobile sandbanks to cable protection measures placed on/adjacent to them. See also our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please refer to our advice in Appendix D5 to our Deadline submission. |  | No change. Please see our advice to ExQ3 3PE2 (Appendix K6) and Points 1 and 13 above. We also advise monitoring to demonstrate recovery of significant bedforms such as sandwaves/sandbanks where affected by cable installation activities. |  | Issue progressed. The Applicant has submitted an In-Principle Monitoring Plan [REP6-116], which we welcome. However, it needs to include monitoring to validate EIA/MCZA conclusions and provide evidence of sandwave recovery. Please also see our advice in Appendix D7, L7 and within our covering letter. |  | No | No change.
19 | D23 | The Applicant should evaluate projected vertical elevation changes to the beach/intertidal and coastal retreat rates at both Landfalls during the lifespan of the Project. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. |  |  |  | We no longer consider this matter resolved. We note the concerns regarding the coastal geomorphology baseline for the Suffolk landfall, and updated coastal erosion/shoreline management information provided by East Suffolk Council in [REP2-048] we consider that this remains as a key consenting and environmental risk. Concerns remain regarding coastal evolution at the Kent landfall. Need to establish a more robust baseline characterisation prior to installation to assess impacts against - Please also see our advice in Appendix D4 to our Deadline 4 submission. |  | Natural England welcomes commitment MPE08 [REP4-234] to undertake further analysis to consider the potential for coastal erosion over the lifetime of the Proposed Project. This information will be used to inform the detailed design to ensure that the risk of future exposure of the offshore buried cables is as reduced as far as practicable. This is welcomed and resolves this issue. Although please see our advice in Appendix D5. | [5 empty] | Yes
20 | D25 | Further evidence is needed to support the conclusions regarding impacts to the nearshore seabed morphology due to landfall installation activities within Pegwell Bay. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Clarification of the WCS disturbance footprints for cable installation activities is needed to support and inform the HRA conclusions for the Kent landfall/Pegwell Bay. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | Issue progressed. Natural England welcomes the detailed breakdown of MDS for construction-related impacts to inshore seabed morphology and designated coastal feature receptors at the Kent landfall. However, there appear to be a number of landfall construction activities which have not been included in the MDS (see Appendix D6). In addition, clarification is needed regarding which cable installation activities are sequential or overlap. |  | No change - please refer to our advice at Deadline 6 (Appendix D6). |  | No | Natural England has highlighted in Appendix D8 further areas for clarification regarding potential seabed impacts due to cable pull-in activities at Kent landfall. Please see main letter
21 | D27 | Until further information has been provided by the Applicant as set out in [RR-3920] Appendix D, Natural England is unable to agree with conclusions in regard to marine process receptors included within the HRA |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. We seek further information or clarification on the potential impacts to marine processes which could in turn affect designated sites/protected features |  | No change |  | No change. For more detailed advice, please see Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | Issue progressed. We welcome the Applicant's updated information on the MDS for construction-related impacts to the intertidal/seabed morphology. However, not all potential impacts have been quantified. Uncertainty also remains regarding long-term morphological change in Pegwell Bay. These issues have implications for designated features and supporting habitat in Pegwell Bay that need to be addressed. Please see our advice in Appendix D6. |  | No change since Deadline 6. |  | No | No change.
22 | D30 | It remains unclear if all of the pressures/impact pathways have been fully assessed alone and cumulatively. The MCZ assessment should be updated to reflect the outcome of address points raised in Appendix D [RR-3920] |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | No change. Please see our advice in Points 1 above and Appendix D6 on Goodwin Sands MCZ. |  | No change since Deadline 6. Please see also our advice in to Point 1 above and in Appendix D7. |  | No | No change.
23 | D31 | The Applicant should evaluate migration of the Goodwin Sands sandbanks over the lifespan of the scheme to inform the MCZA and impact assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding their resilience and sensitivity to cable protection measures placed on/adjacent to them. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. |  | No change. Natural England advises that to resolve this issue the Applicant needs to evaluate the potential for impacts on Goodwin Sands MCZ due to the placement of cable protection measures adjacent to the MCZ. This should include consideration of potential changes to the hydrodynamic and sediment transport regimes due to the presence of external cable protection adjacent to the MCZ and migration of bedforms through the lifetime of the Project. |  | No change. We advise that the Applicant should, as advised at Point 1 above, and in Appendix D6, assess seabed mobility and stability for the area of Goodwin Sands MCZ that may be affected by changes to physical processes due to the presence of cable projection adjacent to the MCZ. Please also see Appendix D6. |  | No change since Deadline 6. |  | No | No change - see advice provided to Point 1 above regarding MDS for external cable protection placed adjacent to Goodwin Sands MCZ.
24 | D33 | Cumulative/in-combination effects due to other nearby activities should be considered e.g. aggregate dredging, in particular for Goodwin Sands MCZ. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The Applicant should clarify whether there is the potential for cable protection to be placed adjacent to Goodwin Sands MCZ over the lifetime of the Project. If the Applicant considers it unlikely that cable protection will be required adjacent to the MCZ, then this should be secured as a condition. If it's considered to be a requirement for cable protection adjacent to the MCZ, then its potential to interrupt or modify sediment transport should be assessed. In turn, consideration should be given to the conservation objectives of the protected features of the MCZ. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | No change. Please see our advice in Appendix D5. |  | No change. Please see our advice in Point 1 above and Appendix D6. |  | No change since Deadline 6. Please see also our advice in to Point 1 above and in Appendix D7. |  | No | Not resolved. Uncertainties remain regarding the potential for the WCS external cable protection placed adjacent to the MCZ to interrupt sediment transport processes operating on/around the MCZs could lead to morphological change within the MCZ. In turn, the potential remains for other nearby plans/projects to act cumulatively to affect the morphology/sediment composition within the MCZ.
25 | D34 | The assessment requires further information (in relation to potential changes to the Physical Environment) before we can advise further on the require of mitigation measures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue concerns potential risks to Goodwin Sands MCZ due to the placement of cable protection adjacent to the MCZ and also cumulative impacts to the MCZ, as detailed in the comments above. No change, pending review of documents submitted at Deadlines 1A, Change Request, and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | With regards to our outstanding concerns regarding Goodwin Sands MCZ, please see our additional advice in Appendix D5. |  | No change. We advise that uncertainty remains regarding the potential impact on Goodwin Sands MCZ due to the placement of cable protection adjacent to the MCZ, in addition to pre-sweeping of sandwaves/bedforms along the offshore route that abuts the MCZ, and other activities/plans that may impact the MCZ (i.e. cumulative effects). As a first step, please see our advice to Point 1. |  | No change since Deadline 6. Please see also our advice in to Point 1 above and in Appendix D7. |  | No | No change - please see advice provided above.
26 | New Issue | The coastal erosion assessment refers to the National Coastal Erosion Risk Mapping (NCERM) project data, which has been superseded by NCERM2. The Applicant should consider the NCERM2 project data to inform detailed design/future assessments of coastal change. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change |  | We would welcome confirmation that the Applicant has incorporated the most recent NCERM data into their marine physical processes EIA. |  | We welcome confirmation in [REP4-242] that the 2024/5 NCERM2 dataset has been used to assess future baseline conditions associated with potential shoreline change. This issue is resolved. | [5 empty] | Yes
27 | New Issue | In [REP1-033] it is stated that this ES chapter has been ‘updated in response to Relevant Representations from various stakeholders and to incorporate information from Application Document 9.13 Pegwell Bay Construction Method Technical Note.’ Please note, however, that it is difficult to identify where changes have been made to the ES chapter, apart from Sections 1.7.6 and Table 1.18. We do, however, note that Figures 6.4.4.1.13 and 6.4.4.1.14 have been added to [REP1-010]. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay Construction Method Statement. |  | No change. |  | Natural England is content to close this issue going forwards but continue to request that the Applicant clearly identifies where changes are made to existing documents through the remainder of Examination. |  | No Change: Please see the comments in our D6 cover letter. |  | We consider that this issue can no longer be addressed as Examination will soon be closed. However, we would advise that should further revisions be made to the application documents that changes should be clearly identified and ideally signposted at the start of each document. |  | No
28 | New Issue | Additional mitigation measure MPE06 - Natural England advise that a similar commitment to MPE06 should be adopted for the Kent landfall through monitoring of change in the intertidal and shallow subtidal areas, in particular where protection is planned to be placed at the HDD exit pits. Commitment MPE05 [REP1-103] ensures depth of burial monitoring surveys will be undertaken post installation. Natural England advises that the same commitment should be made for Pegwell Bay. Additionally monitoring to validate ES predictions regarding changes to nearshore seabed morphology (and associated flow dynamics), seabed recovery, and to ensure there are no unexpected changes to intertidal/shallow subtidal morphology |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. |  | No change. Natural England advises that a commitment should be made to monitor morphological change at the intertidal and shallow subtidal areas of the Kent landfall, in particular where protection is planned to be placed at the HDD exit pits. Additionally monitoring should also be carried out to validate ES predictions regarding changes to nearshore seabed morphology (and associated flow dynamics), seabed recovery, and to ensure there are no unexpected changes to intertidal/shallow subtidal morphology |  | Issue progressed. We note and welcome the Applicant’s commitment (MPE06) in [REP5-020] to monitor beach profile and erosion rates at both landfall sites. This issue is likely to be resolved if the Applicant can clarify the wording and details of the proposed monitoring. For example, will it include the Kent landfall in general (i.e. all parts of the intertidal affected by cable installation), rather than focussing only on the sites where the rock bags are planned to be placed at the HDD entry/points. |  | No change. In line with our previous responses, we advise that the Applicant needs to provide more specific details of the monitoring proposed for both landfalls. We also advise that landfall monitoring should not be restricted to the areas ‘where rock bags are planned to be placed at the Horizontal Directional Drilling (HDD) exit pits.', rather it should cover the full extent of the nearshore and intertidal at both landfalls. Please also see our advice in Deadline D7. |  | No | Partially resolved. In MPE06, the Applicant has committed to monitoring beach profile and erosion rates at the Kent landfall over the operational lifetime of the Project, in relation to the trenchless technique construction areas associated with the exit pits. This is welcomed. However, the monitoring also needs to consider the full extent of the nearshore/intertidal/shallow subtidal to ensure there are no unexpected changes to coastal morphology receptors, assess recovery, and validate ES predictions.
29 | New Issue | Figure 6.4.4.1.11 Sheet 1 (Offshore Seabed Surficial Geology Overview Sheet) identifies a number of Annex I – Reefs and Annex I – Sandbanks, including Annex I sandbanks not in a designated site. It is unclear whether these features may be affected by cable protection measures placed on or adjacent to them. The Applicant should provide an indicative map of proposed cable protection locations relative to these features to inform the impact assessment. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. |  | Partially resolved. We welcome the updated Figure 6.4.4.1.11 [REP4-050] which provides an indication of cable crossing locations along the offshore scheme. However, other potential cable protection areas also need to be identified. |  | No change. We advise that the indicative locations of cable protection should be provided. |  | No change since Deadline 6. Please also see our advice in Appendix D7. |  | No | No change. Cable protection locations (apart from the high-risk rock backfill and crossing locations) have not been identified.
30 | New Issue | Three different cofferdam construction options are proposed including prefabricated filled tanks, a barge with moonpool grounded after positioning, or piled sheeting. However, the Marine Physical Environment chapter [REP1-052] states that either multiple or one large moonpool or piled cofferdam will be constructed. The WCS cofferdam construction parameters should be clearly defined and made consistent across the relevant documents. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | Issue resolved. The Applicant has further quantified [in REP4-028] the three cofferdam option parameters for the Kent landfall and provided an explanation for the WCS assessed. | [5 empty] | Yes
31 | New Issue | The impact pathways and maximum design scenario (MDS) parameters for the temporary HDD working area, pulled and pushed duct installation methods have not been considered or assessed in [REP1-052], the Marine Physical Environment chapter. This should be addressed by the Applicant. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. We advise that all construction impacts relevant to inshore seabed morphology and designated coastal feature receptors need to be identified and MDSs quantified. Furthermore, MDS for increases in SSCs, water column turbidity, and associated deposition of disturbed sediments should include not only MDS width, length, area, but also volume and duration of activity. Please see our advice in Appendix D4 to our Deadline 4 submission. |  | No change. Please see our additional advice provided in Appendix D5. |  | Progressed. We note in [REP5-020] that most of the construction-related activities have now been quantified. However, there remains some uncertainty regarding the MDS for activities such as the use of rollers for duct pull-in, the construction access route between the hoverport and intertidal HDD working area, and advance pre-construction activities. |  | No change since Deadline 6, please refer to our advice in Appendix D6. |  | No | Please see cover letter to RFI2.
32 | New Issue | The impact pathways and maximum design scenario (MDS) parameters in relation to the sandwave clearance works are unclear within the [REP1-052], the Marine Physical Environment chapter or within Chapter 6.11, the Marine Conservation Zone Assessment. This should be addressed by the Applicant. |  |  |  | Further information is required in relation to the proposed sandwave clearance activities due to the ambiguity around the project design MDS. The following issues need to be considered and clarified including (a) the MDS location of the sandwave clearance works; (b) the impact pathway for physical environment receptors; (c) the location and impacts in relation to protected sites. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission. |  | Issue progressed. The Applicant is confident that the pre-sweeping/sandwave levelling locations identified and assessed in [REP4-028] are correct and that no other locations have been identified as requiring pre-sweeping/sandwave levelling. We welcome this confirmation [REP4-242]. However, we note that there is the potential for pre-sweeping to occur along the 3.2km section of the cable route that runs adjacent to Goodwin Sands MCZ. Therefore, we advise that the Applicant should consider potential impacts on the MCZ sandbank system due to modification of adjacent/adjoining sandwaves. Finally, consistency on the WCS across named plans/assessments is required please see Appendix E5 to our Deadline 5 submission |  | Progressed. We advise that the MDS pre-sweeping sediment removal parameters need to be clarified, based on the latest information in [REP5-118] which identifies an additional area of pre-sweeping at KP38.7-KP44.4, in addition to the section between KP96.32-KP113.883. The MDS sediment removal parameters should also be presented per trench and for all trenches, i.e. overall total. The assessment(s) should then be updated accordingly. Please see Appendix D6 to our deadline 6 submission |  | No change. We advise that the WCS pre-sweeping/sandwave lowering parameters need to be clarified and, where necessary, updated in the relevant documents/plans. An indicative layout of pre-sweeping locations also needs to be provided. Please see Appendix D7. |  | No | No change. The MDS pre-sweeping requirement still differs in the CSIP [REP7-160] and MPE Chapter [REP7-098].
33 | New Issue | Cumulative effects have not been assessed. This is particularly important for Goodwin Sands MCZ and Pegwell Bay (and its designated features). | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission. |  | No change. Cumulative effects on marine processes at both the Kent landfall and Goodwin Sands need to be considered. |  | No change. Cumulative effects need to be considered, in particular, on Goodwin Sands MCZ and the intertidal at the Kent landfall. |  | No change since Deadline 6. |  | No | No change.
34 | New Issue | Potential risk of groundwater contamination discharging into coastal waters from the former Pegwell Bay hoverport site now incorporated into the Order Limits. | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission. |  | No change. Please see our additional advice provided in Appendix D5. |  | No Change: Natural England notes and welcomes the commitment [REP5-116] made by the Applicant to prepare a hoverport condition monitoring plan post-consent to monitor the condition of the hoverport during construction. This will also include measures for identifying and managing potential contamination risk. However, containment of contaminants are likely to be impactful in their own right - please see Appendix D6 |  | No change. Please see our advice at Deadline 6 and also in Appendix D7. |  | No | No change. Natural England will welcome the opportunity to be consulted on the Hoverport Condition Monitoring Plan post-consent [REP7-160], including the necessary measures for identifying and managing any potential contamination risk. However, we highlight that currently there is insufficient information to inform understanding of the potential implications for the coastal/marine environment due to use of the hoverport for access during construction and operation.
35 | New Issue | The EIA needs to be updated to consider impacts due to extension to the Order Limits to include the Hoverport and access across the intertidal area at Pegwell Bay. This includes updating the baseline and impact assessment. | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission. |  | No change. Please see our additional advice provided in Appendix D5. |  | Progressed: We note that the MDS seabed/intertidal impacts due to the construction access route between the hoverport and HDD working area (including potential use of ground protection mats) have not been included in the updated [REP5-020] MPE chapter, or other relevant docs/plans. These parameters are needed to inform the impact assessment for the intertidal/seabed at the Kent landfall. Please see Appendix D6 |  | Progressed. The MDS construction access impacts at the Kent landfall still need to be quantified/fully assessed, including the use of protective matting on the mudflats. Alternative ground protection solutions should be suitable for the receiving environment. Please also refer to Appendix D7. |  | No | Progressed. The EIA [REP7-098] has not been updated to consider impacts due to the use of the hoverport and access routes across the intertidal at Pegwell Bay, however, the Applicant has committed (B67) to consult on the locations and widths of access routes across the mudflats post consent. Final details of the construction access route and requirements for ground protection mats will also be set out in the Landfall Construction Method Statement Furthermore, the updated CSIP [REP7-160] states that a Hoverport Condition Monitoring Plan will be prepared post consent to monitor the condition of the hoverport during construction. Natural England advises that impacts associated with these works will need to be fully assessed.
36 | New Issue | Impacts to designated chalk features and subtidal chalk due to the proposed project need to be considered. Further detail is needed from the Applicant including consideration of how impacts can be avoided, mitigated etc. | [9 empty] | Part Resolved. The Applicant has confirmed [REP4-242] that the Sea Link LOD is completely outside the Thanet Coast SAC and Thanet Coast MCZ which have chalk reef as a designating feature. No cable will be placed within this feature . Whilst closer to the HDD exits, chalk occurs at least 6m below the surface and is overlain by clays and silts. Therefore, we consider that this issue is resolved. However, the chalk reef extends beyond the boundary of both sites, the Project will also avoid this habitat. However, there is no environmental commitment to secure this. Some sub-surface chalk was observed in vibrocores along the cable route, which is a Section 41 habitat and geological feature. Please see Appendix E3A to our Deadline 3A submission |  | No change since Deadline 5. |  | Part Resolved. Natural England refers to Appendix E7 to our Deadline 7 submission for more detail. |  | No | No Change.
37 | New Issue | Disposal of 75,000m3 of pre-sweeping sediment from the Sunk Pilot Boarding Area anywhere in the cable corridor with potential impacts on sensitive areas of seabed/benthic habitats. |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | Natural England advises that the fate of sediment dredged from the Sunk Pilot Boarding Area needs to be appropriately considered and assessed in the relevant documents. We would also advise that an appropriate buffer should be applied to avoid disposal of this dredged material in proximity to sensitive seabed/benthic habitats. |  | No | No change. However, if the Applicant can commit to not disposing of the Sunk Pilot Boarding Area dredged material in proximity to sensitive areas of seabed/benthic habitats then this issue is likely to be resolved.

## E - Benthic Ecology
Point | Point Number(s) from Appendix E RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix E - Benthic Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression at SoS RFI 1 | RAG | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | E1 | The Environmental Statement should be updated to consider all potential pathways of effect on intertidal and subtidal benthic habitats |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Part Progressed. Please see Appendix E7 |  | No | Partially resolved. However, unresolved issues remain. See R&I Log points: 2, 5, 6, 8, 12, 17, 25 & 41. |  | No Change
2 | E2, E12 | Maximum Design construction footprints should be reviewed and updated to remove any ambiguity. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Part Progressed. Please see Appendix D7 and E7 |  | No | Unresolved. Natural England highlights that landfall methods at Pegwell Bay remain uncertain and that it is unclear if the MDS and WCS have been presented or assessed. |  | Unresolved. Please see cover letter to RFI2
3 | E3, E14, E37 | Natural England advises that benthic mitigation measures avoid, reduce, mitigate impacts to the most sensitive Section 41 NERC Priority Habitats. The Applicant should consider all mitigation options, including bundling of the export cables for each project and micro-siting of cables to ensure permanent impacts to Section 41 Habitats are avoided/reduced wherever feasible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. Please see responses to ExQ2 BE 9 and 10 in Appendix K5 in our deadline 5 submissions |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. |  | No | Partially resolved. Natural England welcomes the adoption of BE05 and BE06. However, the wording requires further revision to strengthen the commitments to ensure permanent impacts to NERC Section 41 Habitats are avoided/reduced wherever feasible. BE05 - It is not immediately clear what Work Plan 6 includes and therefore, needs to be more explicit. But we would expect that the benthic mitigation plan to be agreed prior to any seabed preparation works being undertaken. Furthermore, the benthic mitigation plan must be informed by the findings of a completed and agreed pre-construction baseline survey. The use of the 'as-built' survey is confusing and therefore we request clarity and alignment with standard conditon working. |  | Resolved: We are now content with BE05 and BE06 in C3-015 suitably mitigates impacts from sediment deposition. And wider impacts to NERC habitats
4 | E4, E32 | The Applicant has not committed to removing cable protection at the Project's end of life. Natural England strongly advises that commitment is secured through DCO for the removal of all infrastructure at the time of decommissioning, both within and outside of designated sites. An Outline Decommissioning Plan should be provided at the consenting phase to detail the approach to decommissioning. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. We welcome the submission of [REP4-091] 9.93 (A) Offshore Decommissioning Technical Note . However, it hasn't addressed our concerns. Please see Appendix E Point E.20 to our Deadline 5 submissions |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | No | Unresolved. No change in Natural England's position. |  | Unresolved. Natural England notes that the Applicant is committed to factoring removability of cable protection into its decision-making at the Construction Stage of the Proposed Project. We note that this commitment is secured in the CSIP and Offshore CEMP, which is welcomed. However, we note that there is still no commitment to remove all infrastructure at the time of decommissioning.
5 | E5, E24 | The Environmental Statement should be updated with an appropriately considered and evidenced assessment of the sensitivity of all benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification required around the assessment of impacts (including Coralline Crag). |  | No change |  | Part Resolved. While we welome updates to the Benthic Chapter on the sensitivity of some receptors. Please see Apendix E5 to our Deadline 5 submission where we advise that assessments are updated. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Partly Addressed Natural England advises that the document should be updated to include a ‘high’ sensitivity rating for subtidal chalk to physical disturbance impacts. |  | No | Partially resolved. Issue resolved for reef, sea caves and peat and clay exposures due to updated sensitivity information. As previous advised at Deadline 7, Natural England highlights that no sensitivity information is provided for subtidal chalk. Whilst the sensitivity score for peat and clay exposures may be intended to also apply to subtidal chalk, this is unclear as written. |  | No Change
6 | E6, E25 | All benthic receptors within the Zone of Influence should be characterised and assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on indirect impacts to designated sites |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | No | Partially resolved. Natural England does not consider subtidal chalk and peat and clay exposures to have been adequately characterised and assessed. NE refers to our advice provided at Deadline 7 which describes how chalk and clay is likely to be periodically covered and uncovered by a thin veneer of sediment, but has the potential to be damaged or destroyed by physical disturbance. Therefore, NE advised that areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, should be fully characterised and considered the same as outcropping chalk and clay within assessments. |  | No Change
7 | E7 | Further assessment of impacts from sandwave levelling on benthic receptors is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Natural England advises in Appendix E5 of our D5 submission that to resolve this issue a Sandwave Levelling management plan is required. |  | No Change. Please see Apendices D6, E6 and K6 to our Deadline 6 submission in relation to further advice in relation to sandwave levelling |  | Part Resolved. Please see Appendix D7 where we set out further commiments wthat are required |  | No | Requires revision - new issue. Natural England advises that the wording of BE07 requires revision. Sediment should not be relocated within 50 m of Annex I Sabellaria spinulosa reef or any NERC Act Section 41 Habitat of Principal Importance (e.g. blue mussel beds). Separately, Natural England supports the relocation of sediment within similar sediment habitats, adjacent too, and updrift of sandwaves removed to ensure sediment re-enters the sandwave system, and that levelling works does not distript sediment supply or natural processes. The current wording suggests that sediment should not be relocated updrift of sandwaves, which is incorrect. In addition, note that Sabellaria spinulosa reef is an Annex I habitat, not Annex II species. Text requires revision wherever BE07 is referenced. |  | Resolved: We are now content with BE 05 and BE07 and in C3-015 suitably mitigates impacts on NERC habitats
8 | E8, E52 | The Applicant should provide a transparent justification for the Worst-Case Scenario quantification of benthic impacts both within, and outside designated sites as a result of cable protection placement. Additional information within the Scour and Cable Protection Management Plan is also required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on direct and indirect impacts to designated sites from the placement of cable protection. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change. No further evidence has been presented to support negligible assessment conclusions. Please see Appendix E7 |  | No | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection. Furthermore, in the MCZA [REP7-088] it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope. |  | Unresolved. Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
9 | E9 | With regard to cable protection and the decommissioning of cable protection, we would welcome further refinement of the Rochdale envelope in order to minimise environmental impacts. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. No change. Please see Appendix E5 to our Deadline 5 submission in relation to use of more readily removable cable protection |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | Unresolved. No change in Natural England's position. Please see previous comments |  | No Change. Please see Appendix D8 Table 1
10 | E10 | Mitigation measures should be adopted to differentiate between inside and outside of designated sites unless a precautionary approach will be taken to all installation and operation activities within the assessment. Impacts from all proposed types of external cable protection should be addressed to refine options and allow for a realistic WCS to be assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. In relation to assessment of operation and maintenance activites and in particular cable protection over the lifetime of the project. We advise this should be considered at the time of consent. If not then there should be a commitment to apply for a separate Operation and Maintenance licence will be applied for prior to the commence of the O&M phase of the project |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | Unresolved. No change in Natural England's position. |  | No Change - Please see Point 8 above
11 | E11, E15 | There is insufficient detail on proposed O&M activities relating to the placement of scour prevention / cable protection over the lifetime of the project. Necessary detail should be provided on the parameters for O&M activities including rationale on how total figures have been determined. Further quantified detail should be provided on the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | As for Point 10 |  | No Change. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to O&M activities. Without further consideration we advise that O&M activities are not permitted as part of this licence and a separate marine licence will be required. |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | Unresolved. No change in Natural England's position. |  | No Change
12 | E13, E22 | Higher-level consideration of the UXO clearance activities should be included within MDS. UXO clearance activities both within and outside of designated sites should be provided to sufficiently quantify WCS to benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Please see advice provided in Appendix F5 and EXQ 2 ECOL5 in Appendix K5 to our Deadline 5 submission |  | No Change to our Deadline 5 advice |  | No Change to our Deadline 5 advice |  | No | Unresolved. No change in Natural England's position. Please see main RFI 1 response letter. |  | Unresolved. Natural England welcomes commitment GG39 to discuss with NE management of impacts from an identified UXO, but it is unclear if this aligns with the MOD’s ‘make safe’ policy. If MOD are in agreement with this then this issue would be resolved. Otherwise we advise the commitment includes the requirement to submit and agree a UXO management plan to the MMO in consultation with relevant SNCB prior to an works commencing
13 | E16, E36, E54 | Mitigation measures should be adopted by the Applicant to mitigate for cable route preparation activities and disposal activities. Disposal options should be explored, sediment disposal should match local sediment types to avoid altering habitat character within 1.5km of the Offshore Scheme. A fall pipe should be used when dredging poses a risk of increased suspended sediment affecting sensitive sites or priority habitats. Cleared boulders adjacent to Goodwin Sands MCZ should be redistributed in similar habitats to avoid unnatural clustering and maintain baseline conditions. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Part Resolved. Natural England advises on further commitments in relation to sandwave sweeping is included in Appendix D7. Natural England advises in Appendix E7 that boulder clearance desposition is now resolved |  | No | Unresolved. Only limited inclusion of sediment disposal mitigaton has been incorporated into the outline CSIP [REP6-136 or REP7-160]. No commitment has been made to match disposal areas with local sediment types to avoid altering habitat character within 1.5km of the Offshore Scheme, or to use a fall pipe when disposal of sediment poses a risk of increased suspended sediment affecting sensitive sites or priority habitats. In addition, as stated for Row 8 above, the commitment BE07 requires revision due to incorrect wording - refer to Point 7. This requires across all documents where BE07 is recorded. |  | Resolved Please see ROW 8 above
14 | E17 | Storage options for material from landfall exit pits should be explored to minimise impacts within Sandwich Bay & Hacklinge Marshes SSSI. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Partially resolved. While we welcome the submission of a CSIP concerns still remain. Please see Appendix E5 point E.5 of our Deadline 5 submission for further advice on this matter |  | No Change to our Deadline 5 advice |  | No Change to our Deadline 5 advice |  | No | Resolved.
15 | E21, E23 | Applicant to clarify how individual Sabellaria spinulosa count data has been considered or what thresholds have been used to determine the potential for biogenic reef. A precautionary approach to data interpretation is required to inform a WCS of the extent & distribution of S. spinulosa reef within the Offshore Scheme. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence is required to support the conclusions of the ES that no Sabellaria spinulosa reef was observed by subtidal surveys within the Offshore Scheme. |  | No change |  | No Change. To resolve this issue please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Please Appendix E6 and also comments in E7 in relation determining extent of NERC habitats and requirement for drop Down Video as well as geophysical data |  | No | Unresolved. Natural England continues to have concerns regarding the methodology and approach used to identify Sabellaria spinulosa reef. In addition, refer to advice above (e.g. row 8) regarding BE07 wording. |  | No Change
16 | E24 | Natural England disagrees that Blue Mussel Beds and Sabellaria spinulosa reefs have 'low sensitivity' to the temporary physical disturbance impacts during construction. The Environmental Statement should be updated with an appropriately considered assessment of the sensitivity of receptors and significance of impacts on all habitats listed under Section 41 or the NERC Act |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission | [9 empty] | Yes
17 | E25 | The EIA fails to consider potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures”. All benthic receptors within the Zone of Influence should be sufficiently characterised to enable a robust evidence-based assessment. The ecological importance and rarity of peat, clay and chalk substrates should be properly considered and efforts made to avoid physical impacts where possible. Particularly where such habitats support rare and/or irreplaceable communities such as boring piddocks. If avoidance isn't feasible, the Applicant must demonstrate how impacts have been minimised. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission. Natural England advises that commitments to avoid impacts to Section 41 habitats by micro-siting should be secured in the DCO. Please see Tab C in this R&I log (C10) and Appendix E5 submitted at Deadline 5. Please also see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Natural England advises areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, which have the potential to be impacted by construction works (temporary disturbance) or placement of infrastructure (permanent habitat loss) should be considered the same as outcropping subtidal chalk and clay exposures. The extent of each habitat should be fully quantified and included within the assessment. Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Natural England advises that clarification is provided regarding the extent and distribution of subtidal chalk across the whole of Offshore Scheme. Please see Appendix E7 for more detail |  | No | Partially resolved. Whilst further information has been provided for surficial chalk and peat/clay, we refer to advice provided at Deadline 7 regarding subtidal chalk and peat and clay which are covered by a thin veneer of sediment. Due to the high mobility of sediments and the potential for damage to irreplaceable habitats of principal importance, these habitats should be considered the same as surficial chalk and clay. In addition, whilst NE welcomes BE06, we believe that the wording could be strengthened to ensure secured effective protection for NERC S41 habitats. |  | Resolved: Please see covering letter re amendments to BE05, BE06, and BE07
18 | E26, E41, E45 | The EIA does not consider the likely deposition impacts within Thanet Coast SAC and the assessment is lacking quantification and evaluation of impacts from elevated SSC and sediment deposition within Thanet Coast SAC during construction. The Applicant should update the assessment of potential impacts from SSC and deposition on Thanet Coast SAC Annex I reefs and sea caves and ensure all benthic receptors within the red line boundary and zone of influence are transparently and comprehensively assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that the sensitivity information for reef features within the Thanet Coast SAC to ‘Medium’ sensitivity to suspended sediment concentrations and deposition is updated in line with the precautionary principle, unless further evidence is provided regarding the specific biotopes present within the site, and that impacts are mitigated accordingly. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Partially resolved. Please see Appendix E5 Point 2 to our Deadline 5 submission where we confirm that the sensitivity of reef features of Thanet SAC have been updated, but we note there has been no update to the assessment therefore this remains unresolved. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to limited updates to assessments of SSC |  | Natural England advises in Appendix E7 and K7 that this issue is now resolved |  | Yes | Resolved
19 | E27 | According to MarESA, all benthic receptors are highly sensitive to habitat loss and the EIA (where relevant RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Issues remain outstanding. Natural England advises that the EIA (and where relevant, RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on direct and indirect impacts to designated sites from the placement of cable protection. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No change. Please see advice proivded at Appendix E7 on the need to assess impacts on subcropping chalk |  | No | Unresolved. Natural England continues to advise that all benthic receptors are highly sensitive to direct habitat loss. No change in position. |  | No change
20 | E28 | Clarity is required regarding the extent and distribution of Blue mussel Mytilus edulis beds throughout the Offshore Scheme so that a robust review of the assessment can be made. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence and clarification of the presence and distribution of blue mussel beds is required to support the conclusions of the ES. Natural England also advise that pre-construction surveys to identify the presence and distribution of blue mussel beds across the Offshore Scheme should be secured through the In Principle Monitoring Plan (IPMP). |  | No change |  | No Change - Blue Mussel (Mytilus edulis) are a NERC Section 41 Habitat and therefore we refer to advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 on NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No | Unresolved. Updates do not resolve NE concerns regarding the blue mussel bed assessments. No change in Natural England's position. |  | No Change
21 | E29 | A figure presenting areas within the Offshore Scheme most likely to require cable protection; their spatial relationship to benthic baseline and proximity to designated sites and Section 41 Habitats of Principal Importance should be provided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England would welcome an updated figure to reflect the areas most likely to require all forms of cable protection, including remedial areas. |  | No change |  | Natural England notes that this has been provided within the CSIP which shows location in relation to designated sites. But doesn't consider the location of NERC Section 1 Habitats. Please also see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | In Progress: Please see Appendices D6 and E6 to our Deadline 6 submission where further information is quested of the Applicant to resolve this issue. |  | Part Progressed. Please see Appendix D7 in relation impacts to Goodwin Sands, and Appendix E7 in relation to Nerc Habitats |  | No | Unresolved. No change in Natural England's position. |  | No Change
22 | E30, E58 | The Applicant has made no strong commitment to avoid / microsite around sensitive benthic receptors. The adoption of mitigation measures via a Benthic Mitigation Plan should be considered to reduce/ avoid impacts to Section 41 Habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Whilst commitments to prepare a mitigation plan are welcome, the mitigation hierarchy should be followed which sets out that impacts should first be avoided wherever possible. Securing commitments to avoid sensitive features through micro-siting of the cable wherever possible would resolve this issue. |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. please see Appendix E7 for more detail. |  | No | Unresolved. Commitment BE06 should be reworded to secure stronger commitments to avoid Annex I and NERC Section 41 Habitats of Principal Importance. |  | Resolved: Please see covering letter re amendments to BE05, and BE07
23 | E31 | The extent of all benthic impacts from construction access / work areas, construction of exit pits or cofferdam installation at the Kent landfall has not been assessed within the EA Benthic chapter. We advise that the EIA and RIAA are updated to consider all impacts at landfall. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. However, issues remain outstanding please see Appendix J3A [REP3A-028] of our Deadline 3a submission | [9 empty] | Yes
24 | E33 | The Applicant has not specified the type of cable protection to be used, nor considered the limitations some methods present with successful decommissioning or likelihood of degradation over time. Due consideration should be given to cable protection engineering options that favour the greatest likelihood of successful removal at the Project's end of life. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification is required around cable protection location, type and the impact pathways, including further assessment of scour and secondary scour. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. We welcome the submission of [REP4-091] 9.93 (A) Offshore Decommissioning Technical Note . However, it hasn't addressed our concerns. Please see Appendix E Point E.19 to our Deadline 5 submissions |  | No Change. Please see Appendix E6 to our Deadline 6 submission in relation to mitigation commitments |  |  |  |  | Partially resolved. GM08 states that the Applicant will 'factor in' the removability of cable protection, this is limited and does not secure any commitments to prefence cable protections which is removable. Therefore, Natural England considers the issue to remain unresolved. |  | No Change. Natural England continues to advise that commitment should be secured through the DCO for the removal of all infrastructure at the time of decommissioning, both within and outside of designated sites unless otherwise agreed through a OPSAR derogations case.
25 | E35 | The EIA lacks transparency in how the sensitivity, value and extent of benthic features have been assessed. Not all relevant biotopes within the zone of influence have been properly considered and it is unclear if assessments are based on the worst case sensitivities described. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Part Resolved. While we welome updates to the Benthic Chapter on the sensitivity of some receptors. Please see Apendix E5 to our Deadline 5 submission where we advise that assessments are updated. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  |  |  |  | Unresolved. No change in advice since Deadline 5. |  | No Change
26 | E38 | An Offshore IPMP should be developed and submitted into examination to include monitoring residual concerns in relation to protected habitats and those of conservation importance. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Please see Point E5.9 and E5.32 in Appendix E5 and response to ExQ2 BE 8 and 9 in Appendix K to our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to monitoring commitments |  |  |  |  | Partially resolved. Natural England welcomes the provision of the outline IPMP and updates provided at Deadline 7. However, Natural England advises that further work is required to ensure the IPMP is fit for purpose - refer to Appendix E at Deadline 7. We can also provide further updates on the IPMP submitted at Deadline 7 if required by the SoS at the next RFI deadline, noting that there are further concerns in relation to the timing of potential surveys and issues in relation to creation of scour pits as part of landfall works as identified by the applicant from an engineering perspective which is also relevant to ecology |  | No Change
27 | E39 | Natural England cannot agree with the conclusions of the EIA without a comprehensive assessment of all benthic impacts. We require: - A ecologically relevant understanding of the likely impacts of SSC, deposition and changes to supporting processes from cable protection on features of Goodwin Sands MCZ. - A clearer baseline and quantitative assessment of potential permanent loss of Section 41 NERC Habitats of Principal Importance, especially if avoidance measures are not committed to. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix D5, E5 and J5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Please see Appendix D7 in relation to use of cable protection adjacent to designated sites and Appendix E7 in relation to NERC. Natural England advises areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, which have the potential to be impacted by construction works (temporary disturbance) or placement of infrastructure (permanent habitat loss) should be considered the same as outcropping subtidal chalk and clay exposures. The extent of each habitat should be fully quantified and included within the assessment. Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Natural England advises that clarification is provided regarding the extent and distribution of subtidal chalk across the whole of Offshore Scheme. |  | No | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection . Furthermore, in the MCZA it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope. In addition, BE06 wording requires further strengthening to secure avoidance mitigation for Annex I habitats and NERC S41 Habitats of Principal Importance. |  | Unresolved. Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
28 | E41 | We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In Progress. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection on MCZ features. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to consideration of all impacts |  |  |  |  | Partially resolved. As above. |  | No Change
29 | E43 | While we acknowledge the limited scale of habitat loss, we note that permanent loss of supporting habitat for the Outer Thames Estuary has not been assessed. We advise permanent loss of SPA features' supporting habitat should be screened into the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Resolved. Please see Point 5/G8 of Tab G of our R&I log where we consider that impacts to losses of supporitng habitat for OTE SPA features will be considered in a separate marine licence for UXO clearance |  | Not Resolved: Please see concerns raised in Appendices D6 and E6 on activities have not been fully assessed |  |  |  |  | Resolved
30 | E44 | No mitigation has been proposed for cable protection within or adjacent to designated sites and habitats which support mobile features. Where possible cable protection should avoid benthic supporting habitat. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Resolved. Please see Appendix F5 and Point 5/G8 of Tab G of our R&I log where we consider that impacts to losses of supporitng habitat for mobile features will be considered in a separate marine licence for UXO clearance which is considered to have a greater impact than placement of cable protection. Please note that this is separate issue to intertidal habitat loss covered in Tab J. |  | Not Resolved: Please see concerns raised in Appendices D6 and E6 in relation to cable protection |  |  |  |  | Unresolved. Please see previous comments |  | Partially resolved. for NERC Habitats only through updates to commitments BE05 and BE07
31 | E46 | We acknowledge that despite the need for further transparent assessment of certain impact pathways as highlighted by comments above, it is unlikely that compensation measures will be necessary as commitments to appropriate mitigation measures are possible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Progressed. Please see response to ExQs in Appendix K5 and Appendix E5 of our Deadline 5 where mitigation measures and commitments are discussed in detail |  | No Change to our Deadline 5 advice |  |  |  |  | Partially resolved. Natural England welcomes the mitigation commitments but amendments are required to secure avoidance mitigation for Annex I and NERC S41 habitats. |  | As above
32 | E47 | The current assessment lacks appropriate quantification and evaluation of impacts from SSC and sediment deposition within nearby MPAs during construction. We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  |  |  |  | Partially resolved. Natural England has ongoing concerns regarding mitigation for sandwave levelling and deposition, including during the operational phase, and for indirect impacts upon designated sites from cable protection. Refer to previous advice. |  | Partially resolved for NERC Habitats only through updates to commitments BE05 and BE07
33 | E48 | Natural England requires confirmation that no permanent loss is likely within MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change |  | No change |  | Resolved. The Applicant has confirmed in [REP4-60] and [REP4-90] that there will be no permanent loss of habitat within MCZs | [5 empty] | Yes
34 | E49, E34 | The Applicant has not considered the potential for secondary effects of cable protection adjacent to Goodwin Sands MCZ. A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Goodwin Sands MCZ, followed by secured monitoring via a deemed Marine Licence and an In-Principal Monitoring Plan to determine whether residual impacts are as predicted. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to monitoring and mitigation commitments |  |  |  |  | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection. Furthermore, in the MCZA it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope. |  | Partially resolved. Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
35 | E50 | We highlight the absence of designated anchoring areas to minimise seabed disturbance and advise careful selection of anchoring zones to avoid impacts to sensitive habitats or features. We advise impact assessments of cable installation vessels (jack-up barges or cable laying barges with spud legs) and operation and maintenance activities is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Currently no mitigation measures have been proposed for construction. In relation to assessment of operation and maintenance activites and in particular cable protection over the lifetime of the project. We advise this should be considered at the time of consent. If not then there should be a commitment to apply for a separate Operation and Maintenance licence will be applied for prior to the commence of the O&M phase of the project |  | No Change to our Deadline 5 advice |  |  |  |  | Unresolved. We weclome the updated dcouments, but key information and impact assessments have not been included. For example no mitigation measures have been proposed for construction. And Impacts have not been considered during the O&M phase. |  | No Change
36 | E53 | Natural England advises against the use of grout bags adjacent to Goodwin Sands MCZ, unless filled with locally sourced sediment similar to that within the placement footprint (due to potential degradation of bags over time altering sediment character). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. We note in the CSIP [REP4-090] that the Applicant has not specified the cable installation tools that will be used and what cable protection will be used in what circumstance. Therefore this issue is not addressed. |  | No Change to our Deadline 5 advice |  |  |  |  | Unresolved. Natural England welcomes this update from the Applicant. However, we note that this commitment has not been included within any named plan, and therefore cannot be considered to be secured |  | Resolved MPE13 commits to not using grout bags adjacent to the MCZ
37 | E52, E55 | Natural England is unable to agree with the MCZ assessment conclusions without further evidence and assessment, and maintains that there is reasonable scientific doubt regarding the hinderance of Conservation Objectives (alone or in-combination) of Goodwin Sands MCZ, Kentish Knock East MCZ and Thanet Coast MCZ to be hindered both Alone and in-combination. Particular regard should be given to commitments to remove all cable protection laid directly adjacent to the Goodwin Sands MCZ boundary. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Deadline 5 advice remains unchanged. Please also see Apendix D6 and E6 to our Deadline 6 submission in relation to ongoing MCZ concerns |  |  |  |  | Unresolved. No change in position please see advice on MPE13 |  | Unresolved. Natural England continues to advises that a commitment should be made to not allow placement of external cable protection adjacent to Goodwin Sands MCZ. WCS external cable protection requirement adjacent to the MCZ needs to be clarified. Supporting evidence should be provided to demonstrate feasibility of achieving the 100m separation distance in commitment MPE13. Further evidence is needed to support conclusions that there will be no observable effects on the MCZ due to the presence of cable protection adjacent to the MCZ (including consideration of potential changes to hydrodynamic and sediment transport processes).
38 | E57 | Further information is required to inform a review of the impact assessments, until then, there remains reasonable scientific doubt of the nature of impacts to the intertidal features of Sandwich Bay to Hacklinge Marshes SSSI |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No Change. Please see our responses to EXQs included in Appendix K5 of our Deadline 5 submission |  | No Change to our Deadline 5 advice |  | Please see Appendices D7 and E7 where vehicle assessed, routes, number of return trips and ground pressure is advised upon |  | No | Unresolved: Please see main response letter to RFI 1 | ??? | Please see mainr response letter to RFI 2
39 | New Issue | Concrete mattresses have the potential to provide suitable substrate for colonisation by INNS. Natural England query whether use of a moonpool or prefabricated cofferdam [REP1-108] may also have the potential to introduce INNS at the Kent landfall and, in turn, present a potential impact pathway to designated site features. Clarification needed. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Issue is resolved. Please see Appendix E5 to our Deadline 5 response. | [5 empty] | Yes
40 | New Issue | Natural England remains uncertain as to the level of recoverability and timeframes to do so where compression impacts upon mudflats occur. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about intertidal/supporitng habitat impacts |  | No Change to our Deadline 5 advice |  | Natural England advises that post-consent monitoring is secured to monitor the recovery of the intertidal mudflats morphology and biological communities following landfall construction works, to validate predictions within the ES. Issue can be considered resolved if appropriate monitoring is secured through the IPMP. Natural England advises that the IPMP is updated to include pre-construction and post-construction monitoring of intertidal mudflats to validate predictions for the recovery of mudflat morphology and infaunal communities within the ES and to inform if further monitoring or remedial works are required. |  | No | Unresolved. Natural England advises that a commitment within the IPMP to undertake monitoring of mudflat recovery (morphology and biological communities) post-construction would resolve issue. |  | No Change
41 | New Issue | Documents should be updated to reflect the highly sensitive nature of soft rock habitats abrasion and physical loss. Every effort should be made to avoid physical impacts to these habitats where possible. This is particularly the case where habitats support rare and/or irreplaceable communities such as boring piddocks. Where impacts cannot be avoided, we advise that evidence will need to be presented to demonstrate how impacts has been minimised as much as possible. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. Please see responses to ExQ2 BE 9 and 10 in Appendix K5 in our deadline 5 submissions. |  | No Change to our Deadline 5 advice |  | Partly Addressed Natural England advises that the document should be updated to include a ‘high’ sensitivity rating for subtidal chalk to physical disturbance impacts. Section 3.4.9 in REP6-116 states that the requirement for post-construction benthic survey will be informed by results from pre-construction surveys and final engineering of the project. Natural England advises that the final benthic monitoring plan should be agreed with the MMO, in consultation with the relevant SNCBs. If habitats or species of conservation value (e.g. Section 41 habitats or qualifying annex I habitat) are identified during pre-construction surveys, Natural England advises that commitments for post-construction surveys should be secured to demonstrate either avoidance or, where avoidance is not possible, recovery of habitats. Natural England advises that further monitoring and/or remedial works may be required if impacts are not found to be as predicted within the ES. |  | No | Unresolved. Whilst peat and clay is considered, no information is provided regarding the highly sensitive nature of subtidal chalk to physical disturbance or direct loss, or the ecological importance and rarity of subtidal chalk. Please also see RFI 1 response letter |  | No Change
42 | New Issue | Further to our Relevant Representation advice [RR-3290], we note that all three HDD exit options appear to be located in areas where Coralline Crag is present yet there is no assessment of potential impacts on the Coralline Crag due to the HDD or cable installation at landfall. Further consideration of the locations requiring cable protection is required to inform potential impacts to sediment transport and benthic receptors. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Part Resolved. Natural England welcomes the commitment for HDD exit pits to be located >45m from the continuous Crag formation [REP4-102]. Please see Appendix E5 to our Deadline 5 which highlights commitments that are required to resolve this matter |  | No Change to our Deadline 5 advice |  |  |  |  | Resolved.
43 | New Issue | Justification is required for why the required quantity of rock backfill has increased dramatically. Further information should be provided on where this rock backfill will be placed and the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. Further clarification is also required on the details of cable protection anticipated. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] our Deadline 3a submission |  | No change |  | No Change. Natural England requires further clarification from the Applicant on this matter |  | No Change to our Deadline 5 advice |  |  |  |  | Resolved.
44 | New Issue | Clarification is required as to why the text securing up to date INNS training, biosecurity measures and embedded mitigation measures has been removed. Removed text also includes the requirement to report suspected INNS and, if necessary, take action to control present INNS. No justification is provided for why these measures have been removed, which could increase the risk of INNS being spread or introduced by the project. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Issue is resolved. Please see Appendix E5 to our Deadline 5 response. | [5 empty] | Yes
45 | New Issue | The standard best practice mitigation measures should be adopted where impacts from sandwave levelling could impact within MCZs and/or on NERC Habitat features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission and Appendix D3 [REP3-118] to our Deadline 3 submission. |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to mitigation commitments |  |  |  |  | Unresolved. Natural England welcomes the adoption of BE05 and BE06. However, insufficient mitigation has been secured for sandwave levelling and disposal, and for cable protection. Commitment BE06 requires revision. |  | Resolved: Please see covering letter re amendments to BE05, BE06 and BE07
46 | New Issue | The commitment to the Suffolk Coast HDD should be amended so that the final HDD management plan is agreed with the regulators in consultation with the relevant SNCB, rather than it be for our information only (as per point 59 of [REP 1-103]. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. As advised in Appendices D5 and E5 of our Deadine 5 submission all landfall document need to be agreed with the regulators in consultation with relevant SNCB prior to construction and these documents should be submitted to the MMO 6 months beforehand. Please see DCO comments |  | No Change to Deadline 5 |  | Resolved at commitment B59 in the REAC [REP6-135] |  | Yes | Unresolved: Please see Deadline 7 responses in relation to the necessary strengthening of these commitments.
47 | New Issue | There should not only be a commitment to agree a mitigation plan for NERC habitats in consultation with relevant SNCB prior to construction, but that unless agreed otherwise impacts to theses habitats are avoided. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix E5, of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to mitigation commitments |  | Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. |  | No | Partially resolved. Natural England advises that further mitigation measures are required, and that BE06 requires revision. |  | Resolved: Please see covering letter re amendments to BE05, BE06 and BE07
48 | New Issue | All monitoring requirements/hypotheses should be included in an Offshore IPMP at the time of consent. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Point E5.9 and E5.32 in Appendix E5 and response to ExQ2 BE 8 and 9 in Appendix K to our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to monitoring commitments |  |  |  |  | Partially resolved. Natural England welcomes the provision of the outline IPMP and updates provided at Deadline 7. However, Natural England advises that further work is required to ensure the IPMP is fit for purpose - refer to Appendix E at Deadline 7. We can also provide further updates on the IPMP submitted at Deadline 7 if required by the SoS at the next RFI deadline, noting that there are further concerns in relation to the timing of potential surveys and issues in relation to creation of scour pits as part of landfall works as identified by the applicant from an engineering perspective which is also relevant to ecology. |  | Resolved as set out in C3-017 the CSIMP rather than the IPMP that we will be consulted on the survey designs. But ideally the IPMPO should be updated to also provide the necessary hypotheses to be tested
49 | New Issue | Further interpretation of the findings of REP2-035 Geophysical and Geotechnical Report is required to demonstrate where cable protection is mostly likely to be needed and once this is known undertake an assessment of the potential direct/indirect impacts from cable protection on designated sites features, irreplaceable geological features, and NERC habitats. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix D5 and E5, of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change to Deadline 5 |  |  |  |  | Unresolved. No change in Natural Englands position. Please see comments on the IPMP and BE06 above. |  | Resolved: Please see covering letter re amendments to BE05, BE06 and BE07. However updates to the IPMP are still required
50 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). Natural England advises there is a risk of an AEoI occurring from visual and noise disturbance from the use of a hover craft. Therefore, further information on the use of the proposed hovercraft is required before we can advise further on the impact to designated sites. |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New issue identified following review of documents submitted at Deadlines 6. Please see our Cover Letter and Appendix E7 to our Deadline 7 submission. |  | No | Unresolved. Please see main RFI1 response letter |  | Resolved Natural England welcomes the inclusion within the commitment to agree Hovercraft egress and routes post consent with ourselves prior to construction and welcome the definition of ‘emergency works’, But feel it could be strengthen by included ‘…make safe’ We consider Hovercraft use now resolved.

## F - Marine Mammals
Point | Point Number(s) from Appendix F RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix F - Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | F1, F6 | Worst Case Scenario. It remains unclear if precautionary estimates have been considered. Clarity is needed in the wording to demonstrate how a precautionary approach has been adopted in addition to use of updated survey data. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, it is stated in paragraph 4.4.17 that "The criteria for assessing effects and residual significance are presented in Application Document 6.2.1.5 Part 1 Introduction Chapter 5 EIA Approach and Methodology." [APP-046] Natural England currently do not have access to this document so it is unclear if this issue has been properly addressed. |  | No change. |  | No Change. |  | No Change. Please see our advice in Appendix F5. |  | Resolved - agree with the Applicant's updated text in REP5-133 9.121.1 that there is now sufficient information in Part 4 Marine Chapter 4 Marine Mammals |  |  |  | Yes
2 | F2 | The assessment should be updated to consider peak abundances for each species as representative of the WCS. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The seasonality of the peak abundance and density estimates for each marine mammal species used in the assessment is not clearly stated. Natural England are therefore unable to determine if this issue has been addressed throughout the assessment. Further information from the Applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. Uncertain if issue has been properly addressed. |  | No change. |  | No Change. |  | No Change. Please refer to our advice in Appendix F5. |  | Resolved - agree with the Applicant's updated text in REP5-133 9.121.1 that there is now sufficient information in Part 4 Marine Chapter 4 Marine Mammals |  |  |  | Yes
3 | F3 | Natural England cannot currently agree with the conclusions of the EIA for the reasons outlined below see comments F12-F21. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | No change. |  | No change. |  | No change. Please see our advice in Appendix F5. |  | Reduced risk as some information has been provided. However, In-combination and cumulative issues still require resolution. Please see Appendix F6 to our Deadline 6 Submission |  | Natural England welcomes the updated information provided by the Applicant with regard to the in-combination assessment and the commitment to participate in the Developers Co-ordination Forum (DCF). Although these changes do not resolve our outstanding issues with the methodology for undertaking the in-combination assessment, we are satisfied that the commitment to the DCF will ensure that there is no AEoI to the SNS SAC, provided that commitment is conditioned in the DCO/dML. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
4 | F4, F33 | Natural England cannot currently agree with the conclusions of the HRA for the reasons outlined below. The HRA should be revisited once outstanding issues with assessment methodologies have been addressed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England do not see any evidence of the changes in the assessment. In-combination assessment is particularly poor and has not been improved at all. Specifically, to assess whether there will be significant noise disturbance within a harbour porpoise SAC, the applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. Please consulate the Guidance for assessing the significance of noise disturbance against Conservation Objectives of harbour porpoise SACs (England, Wales & Northern Ireland). |  | No change. |  | No change. |  | No change. Please see our advice in Appendix F5. |  | Progressed. The Applicant has provided information direct to Natural England to address this issue. However, it was received on 12 April and therefore Natural England has not had sufficient time to review ahead of Deadline 6, we will update our position at Deadline 7. |  | Natural England welcomes the updated information provided by the Applicant with regard to the in-combination assessment and the commitment to participate in the Developers Co-ordination Forum (DCF). Although these changes do not resolve our outstanding issues with the methodology for undertaking the in-combination assessment, we are satisfied that the commitment to the DCF will ensure that there is no AEoI to the SNS SAC, provided that commitment is conditioned in the DCO/dML. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
5 | F5 | The Environmental Statement (ES) states that the Berwickshire and North Northumberland Coast SAC is designated for harbour seal. This is incorrect, this SAC is designated for grey seal. Wording should be updated. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The issue is resolved. | [11 empty] | Yes
6 | F8 | The assessment should be updated to consider abundances of species within the study area in the winter months and the highest abundances taken forward to assessment as representing the WCS. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | It is now acknowledged that the peak abundance of harbour porpoise within the order limits is likely to be in the winter months, rather than summer. However, it is unclear as to if this has been reflected within the marine mammal abundance and density tables. Further information from the applicant regarding the seasonality of these peak abundance and density estimates for all species would clarify this. Uncertain if issue has been properly addressed. |  | No change. |  | No change. |  | No Change. Please see our advice in Appendix F5. |  | Resolved - agree with the Applicant's updated text in REP5-133 9.121.1 that there is now sufficient information in Part 4 Marine Chapter 4 Marine Mammals |  |  |  | Yes
7 | F9 | Both SCANS III and SCANS-IV are referenced as the source used for abundance and density estimates. Clarity is needed on the data used to estimate abundance in table 4.14. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | Issue is resolved. Scans IV named in [REP1-056] Application Document 6.2.4.4 (E) Part 4 Marine Chapter 4 Marine Mammals, Table 4.14. | [5 empty] | Yes
8 | F12 | Heinanen & Skov (2015) should also be included in the data used in the assessment, particularly for harbour porpoise and HRA. Include Heinanen & Skov (2015) in the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | Issue is resolved following review of documents provided by the Applicant in Application Document 6.2.4.4 (E) Part 4 Marine Chapter 4 Marine Mammals (Tracked) [REP1-056]. | [5 empty] | Yes
9 | F13 | A range of harbour porpoise abundance estimates and densities are provided here for various management units and SCANS blocks, but it is not clear from the table or accompanying text which figures have been taken through to inform the assessment. This is also the case for all other species of cetacean and pinniped. Please provide clarification as to which figures have informed the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | No Change. Although multiple density estimates and species abundances have been presented for cetaceans in table 4.14, density estimates for harbour and grey seals are not presented anywhere. This information should be provided and used to calulate the number of each seal species potentially impacted int he assessment. |  | Progressed. The Applicant has provided information direct to Natural England to address this issue. However, it was received on 12 April and therefore Natural England has not had sufficient time to review ahead of Deadline 6, we will update our position at Deadline 7. |  | Natural England is satisfied that density estimates have been provided for cetacean species and it is discussed in the text which estimates the assessment is based on. However, Natural Englnad is not clear where the density estimates for the seal species have come from as Carter et al (2025) relates solely to seals in Scotland. We would seek further clarification on the numbers used to undertake the calculations. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
10 | F14 | Table 4.18 presents the hearing groups presented in Southall et al, but the assessment uses the metrics found in NMFS (2018), so it is not clear why the hearing groups in NMFS (2018) haven’t been used. Please provide clarification of the functional hearing groups used in the assessment and ensure one set of criteria is used consistently throughout. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | Following a review of documents provided by the Applicant in Application Document 6.2.4.4 (E) Part 4 Marine Chapter 4 Marine Mammals) (Tracked) [REP1-056]. Whilst this doesn't completely clarify the matter, at this stage in the Examination, further clarification is unlikely to affect the outcome, so we are content to mark this issue as no further action required by the Applicant. |  | Resolved. We welcome the update to the more recent criteria. Natural England is concerned about changes to approach (Marine mammal chapter version H) in table 19 removing PTS and the addition in Table 20 of a reduced sound level for SBP. This does not follow the standard approach and would normally require discussion. However, the outcome is not affected as the JNCC standard mitigation will still be in place so this issue can be considered closed. |  |  |  | Yes
11 | F15 | There is no information presented regarding the modelling that was presumably undertaken to generate the figures presented in Table 4.20. Therefore, Natural England cannot be sure the appropriate model type or parameters have been used in the assessment. Please provide further details regarding any underwater noise modelling that was undertaken during the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | Natural England expects the project to have undertaken underwater noise modelling to accurately predict the impacts of underwater noise. The outputs of this modelling will inform the impact ranges for the noisy activities planned for this project and therefore are essential for assessing the impacts from the project on marine mammals. No information has been provided to show evidence of this modelling. Natural England expects to see an underwater noise modelling report with details of the methodology and outputs from the modelling to be incorporated into the impact assessments. |  | No Change to the advice provided at Deadline 4. Please can the Applicant clarify if the use of the NMFS User Spreadsheet Tool is the 'modelling' that is referred to within the assessment. Natural England do not conisder this to constitute a robust substitute for underwater noise modelling. |  | Natural England maintains our position that the modelling should be undertaken in order to provide a robust assessment. However, given the current position and the risks associated with this particular project Natural England has downgraded the risk and consider this issue to be at an agree to disagree situation. Our advice has taken into consideration that further assessment will be required for the UXO works after consent and advise the imperical underwater noise modelling should be undertaken to inform that future assessment. This issue is now closed. |  |  |  | Yes
12 | F16, F28, F29, F30 | It is not appropriate to use harbour porpoise as a proxy for all other species, including pinnipeds, when separate injury criteria are presented in the NMFS (2018) guidelines. Impacts to seal species and their respective designated sites should be carried out separately from the assessment of impacts to harbour porpoise. Account should be taken of the different hearing ranges and sensitivities of different species within the assessment. As stated above, the SELcum metric from the modelling should be used to inform impacts to designated sites, not just the SEL. Impacts to species, particularly from PTS, should be assessed using the SELcum metric. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | Natural England agrees with the Applicant's response to our comments on REP2-014 and this is now resolved. | [7 empty] | Yes
13 | F17 | It is not appropriate to use A-weighted sound levels (used for human hearing) in an assessment of the impacts of airborne noise on seals, especially when an M-weighted sound levels for phocids in air is presented in Southall et al 2019. The M-weighted sound levels for phocids in air should be used to assess the impacts of airborne noise on seals. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Correction made in Document 9.49 Seals and Airborne Sound Disturbance Technical Note. [REP1-122] The issue is resolved. |  | No change. |  | M-weighted sound levels modelling has now been under taken and presented in document 9.49 [REP1-122] with updated noise information provided in 9.13 [REP2-012]. (Please note this is only in relation to airborne noise disturbance to seals and the above issue regarding underwater noise modelling is still unresolved). The planned HRA update at Deadline 5 should fully resolve this issue. NOTE: This was incorrectly marked as resolved at Deadline 3. |  | Natural England advises that given the stage in examination and that we agree with the conclusion we are content to mark this issue as resolved. | [5 empty] | Yes
14 | F18 | Natural England advises that the predicted zone of PTS as described by the SELcum metric in Table 4.20 should inform the mitigation zone, not the outdated standard 500m described in the 2017 JNCC guidelines. The JNCC guidelines for minimising the risk of injury to marine mammals from geophysical surveys have been updated as of February 2025 and are available in draft form on the JNCC website. These guidelines state that the mitigation zone should be a minimum of 500m. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The updated 2025 JNCC guidance has been referenced, however it should still be clarified in the wider text that a 500m mitigation zone should be used as a minimum. Issue partially addressed, though further clarification is needed before issue is downgraded. |  | No change. |  | Natural England agrees with the Applicant's response to our comments on REP2-014 and this is now resolved. | [7 empty] | Yes
15 | F19 | The pre-shooting search should be 30 minutes in duration, not 20 minutes as stated here. Please refer to the updated JNCC February 2025 guidelines for minimising the risk of injury to marine mammals from geophysical surveys. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | Issue is resolved following review of documents provided by the Applicant in Application Document 6.2.4.4 (E) Part 4 Marine Chapter 4 Marine Mammals) (Tracked) [REP1-056]. | [5 empty] | Yes
16 | F20 | A Marine Mammal Mitigation Protocol (MMMP) should be produced that outlines the procedures to be followed to correctly implement the appropriate mitigation as outlined in the JNCC 2025 guidelines for minimising the risk of injury to marine mammals from geophysical surveys. An outline MMMP should be provided to support the application and a MMMP secured through condition in the DCO/dML. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England reviewed Document 7.5.11 Outline Marine Mammal Mitigation Plan [REP1-025] As acknowledged by the Applicant, this is an early stage version and will be updated and refined throughout the course of the project, following advice from Natural England. Some issue addressed, though further advice will be needed. In general, The purpose of the MMMP is to serve as a concise, user-friendly manual outlining the specific mitigation measures that must be implemented in the field for activities that may impact marine mammals. To maintain clarity and focus, sections on legislation, project details unrelated to the MMMP, and general marine mammal descriptions should not be included in this document, as they are more appropriately placed in the Marine Mammal EIA chapter or other supporting materials. Instead, the MMMP should concentrate on clearly presenting mitigation measures, operational procedures, observer responsibilities, and reporting requirements. The MMMP represents the practical outcome of the assessments conducted during the EIA process. |  | No change. |  | No change. |  | Issue is resolved following review of documents provided by the Applicant in Application Document 9.86 Applicant’s Comments on Other Submissions Received at Deadlines 3 and 3A submitted at Deadline 4 [REP4-242] with an update to the MMMP (Application Document 7.5.11 (C) Outline Marine Mammal Mitigation Plan) (Tracked) [REP4-070]. | [5 empty] | Yes
17 | F21 | There is no quantification of the potential impacts to marine mammal species, i.e. how many animals could potentially be impacted, despite abundance and density data being provided. Therefore, Natural England are not currently able to agree with the assessment conclusions. Issues outlined here regarding the methodology for assessment should be resolved and the assessment updated accordingly. After further review of relevant representations the risk rating has been upgraded to red. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | No change. Please see our advice in Appendix F5. |  | Progressed. This is resolved for cetaceans. However the same information is required for both seal species as stated in Appendices F5 and F6 to our Deadline 5 and 6 submissions. |  | It is unclear to Natural England why Carter et al (2025) has been used to inform the assessment for SeaLink as this paper relates solely to seals in Scottish waters. We welcome the methodology that has been used however we would seek further clarification on the numbers used to undertake the calculations. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
18 | F23 | Natural England are content that the listed projects can be scoped out of the cumulative impact assessment based on the justification provided. | [15 empty] | Yes
19 | F31, F32 | It is not sufficient to state that delivery of projects in-combination can be managed without an adverse in-combination effect without providing any information as to what the scale of the impact from all these projects in-combination is predicted to be or how these impacts will be managed. There is no consideration of in-combinations impacts to marine mammals in this section. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change. |  | No change. |  | No change. Please see our advice in Appendix F5. |  | No Change: Natural England is not satisfied that AEoI of the Southern North Sea SAC can be excluded from in-combination effects of underwater noise to harbour porpoise. Whilst we welcome the updated figures for this project and LionLink and agree that OWF’s will make up the majority of the in-combination impact we do not agree that plans/projects can be disregarded. We advise that HRAs require that all plans/projects, that include noise generating activities that could overlap are included in the in-combination assessment. |  | Natural England welcome the updated information provided by the Applicant with regard to the in-combination assessment and the commitment to participate in the Developers Co-ordination Forum (DCF). Although these changes do not resolve our outstanding issues with the methodology for undertaking the in-combination assessment, we are satisfied that the commitment to the DCF will ensure that there is no AEoI to the SNS SAC, provided that commitment is conditioned in the DCO/dML. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.
20 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA and seal colonies in the area. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). Natural England advises there is a risk of an AEoI occurring from visual and noise disturbance from the use of a hover craft. Therefore, further information on the use of the proposed hovercraft is required before we can advise further on the impact to designated sites. |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New issue identified following review of documents submitted at Deadline 6. Please see our Cover Letter and Appendix F7 to our Deadline 7 submission. |  | No | Unresolved. No change in Natural Englands position since deadline 7. Please see previous comments.

## G - Marine Ornithology
Point | Point Number(s) from Appendix G RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix G - Marine Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | G1, G7 | Natural England advises a timing restriction is needed on construction activities from 1st November to 31st March inclusive, irrespective of whether other developments occur, to mitigate impacts on red-throated diver within the Outer Thames Estuary (OTE) SPA . |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Partial commitment to the seasonal restriction has been made but Natural England emphasise the importance of avoiding impacts throughout the over-wintering period. See Appendix G4 to our Deadline 4 response for full details (pending review of documents submitted at Deadline 3). |  | Resolved. Following advice from Natural England that a timing restriction is needed on construction activities from 1st November to 31st March inclusive, irrespective of whether other developments occur, to mitigate impacts on red-throated diver within the Outer Thames Estuary (OTE) SPA (see RR3920 Appendix G1,G7), the Applicant has withdrawn paragraph 5.9.10 from the document. The Applicant no longer suggests that mitigation for cumulative impacts on RTD may not be necessary if other developments in planning do not go ahead. Therefore Natural England are content with the Applicant's commitment to the seasonal restriction regardless of whether other plans and projects proceed. | [5 empty] | Yes
2 | G2, G4 | Based on the information submitted Natural England cannot rule out AEOI on the OTE SPA. We recommend that the November to March timing restriction on cable construction activities is widened to include pre-lay grapnel run, O&M activities (including surveying) and decommissioning phases. As a minimum, adherence to Natural England’s best practice protocol will be required for these phases but depending on the proposed level of activity in each phase, that may not be sufficient. To progress this matter we recommend the Applicant provides additional detail on anticipated frequency , duration and extent of such works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Partial commitment to the seasonal restriction has been made but Natural England emphasise the importance of avoiding impacts throughout the over wintering period. We continue to advise that the proposed mitigation may not be a sufficient commitment to avoid disturbance/displacement effects during the sensitive winter period and the project may still contribute to in-combination effects. |  | No Change. Please see Appendix G5 to our Deadline 5 submission |  | Progressed. The Applicant has provided new info on the likely duration and speed of the PLGR across the SPA but has yet to provide an assessment of its impact. Following discussions at the meeting on the 1st April the Applicant provided further correspondence regarding their position on including PLGR works within the RTD seasonal restriction. Providing that the commitment is submitted by the Applicant at D6 Natural England will consider this issue to be resolved. Please see Appendix G6 to our Deadline 6 submission |  | Natural England welcomes the Applicants commitment of a full seasonal restricton to all offshore cable laying activities within the OTE SPA and its 2km buffer including the PLGR and non-emergency related operations and maintenance work. We also welcome the commitment to follow our best practice guidance on vessel movements throughout. In addition, Natural England notes that the 2 km buffer is only secured within the CEMP as mitigation. Therefore we advise that it also needs to be secured within the DCO/dML. Once this is adequately secured we will consider this issue resolved. Please see Appendix G7 to our Deadline 7 submission for further mitigation suggestions to further minimise impacts on RTD. |  | No | Resolved. The latest REAC states the 2km buffer is included in the DCO/dML as Condition 4(1)(b) of the DMLDCO Schedule 3, Requirement 6 Offshore Construction Environmental Management Plan Condition 4(1) of the DML Red Throated Diver Protocol. This suggests the commitment to include the PLGR within the seasonally restricted period and apply this condition to the SPA and its 2km buffer has been secured and the matter is resolved.
3 | G3, G10 | We note the applicant's intention to consult NE before pre-lay grapnel run during January-March. Should some O&M works be considered necessary during the November-March period (e.g. in emergency situations), a report detailing the nature of the event, and the specific location, duration and extent of any works undertaken, including associated vessel transits, may be requested to quantify potential impacts and for assessment of future cumulative/in-combination effects from similar projects. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No Change. Whilst we not that the Applicant is aware that futher permission for O&M activities during the sensitivie period will be required the pre-lay activies still remain a concern |  | Progressed. Following discussions at the meeting on the 1st April the Applicant provided further correspondence regarding commiments associated with Emergency works to address our concerns. Providing that these commitments are submitted by the Applicant at D6 Natural England will consider this issue to be resolved. Please see Appendix G6 to our Deadline 6 submission |  | Following a meeting with the MMO on the 24 April 2026 it is unclear whether the definition of emergency works has been adequately updated and agreed. Natural England continues to advise that the definition as set out at Para. 1.10.12 of the CEMP [REP6-073] is therefore not agreed. But once it is, all relevant named plans/documents should be updated. |  | No | No change.
4 | G5 | The Applicant states that RTD numbers in the OTE SPA are declining by February. Evidence from both the January and February 2013 (APEM, 2013) and the early and late February 2018 surveys (Irwin et al, 2019) of the OTE SPA suggest that RTD numbers appear to build in the late winter period rather than decline. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No Change. However, whilst Natural England continues to disagree with the Applicant on this matter, a commitment to avoid the the most sensitive period for RTD would resolve this matter. |  | Progressed. However, should the Applicant fully apply the RTD best practice protocol including adoption of a seasonal restriction this becomes a moot point and would be considered resolved |  | Issue resolved. Natural England welcomes the commitment to the RTD best practice protocol including adoption of the seasonal restriction 01 Nov - 31 March. Please see Appendix G7 to our Deadline 7 submission. |  | Yes
5 | G8 | In order that a meaningful assessment or WCS impacts can be made, a higher-level consideration of the UXO clearance activities included within MDS is needed. Information from neighbouring projects can be used as a proxy and commitments to mitigation measures secured. To provide a sufficiently broad WCS quantification of benthic impacts we also advise that UXO clearance activities both within, and outside, designated sites should be provided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Natural England welcomes the Applicant’s commitment to continue engagement with both Natural England and the MMO to ensure that the consenting approach for UXO activities is appropriate and that the assessments supporting the marine licence applications fully capture the potential effects of the Proposed Project. | [7 empty] | Yes
0 | G9 | Based on the information and mitigation submitted within the application we cannot rule out an AEOI on the OTE SPA. To determine the required level of mitigation, the Applicant is recommended to provide a detailed spatial & temporal analyses of anticipated works for pre-lay grapnel run, O&M activities and decommissioning, and to quantify and assess the implications for using of the SPA by RTD. The required elements are set out in detail within our Relevant Representations. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No change. Natural England still requires more detail on the O&M and Decommissiioning activities during the over wintering period. To resolve this issue Natural England advises that either the relevant information is provided and assessment or there is a blanket commitment to avoid the most senstive period for RTD for activities during these project phases, with the understanding that a separate ML would be required to undertake works during this time |  | Progressed: Following a meeting with the Applicant on the 1st April and further correspondence the following has been discussed: a) PLGR: The Applicant has been provided guidance on how to assess the impact using the 'bird days lost approach and has indicated they will present an assessment at D6. Following further discussions at the meeting on the 1st April and further correspondence on the 2nd April Natural England understand that the Applicant will be applying the seasonal restrictions to all activities. Providing that the commitment is submitted by the Applicant at D6 Natural England will consider this issue to be resolved. b) O&M and Decommisioning: Note the Applicant has pledged to mitigate decommisioning in the same way as construction and conduct O&M activities (except emergencies) outside the seasonally restricted period. Natural England consider this issue resolved. c) Emergency works: Following a meeting with the Applicant on the 1st Apri, proposed wording/conditions to ensure emergency works are securely captured and mitigated have been discussed. Providing that the conditions are provided by the Applicant at D6 this issue will be resolved. |  | Natural England welcomes the steps the Applicant has taken to mitigate impacts by including the commitments below and considers these issues resolved. a) To apply the RTD protocol during emergency works to be secured in the CSIP / CSEMP to minimise the impacts as much as possible and submit a log to the MMO no more than 4 weeks post conclusion of the emergency works highlighting activity, location and duration etc. b) To acknowledge and include a process to be followed within a named plan that depending on the duration of emergency works within the SPA ensures that any requirement for compensation for impacts is considered and where MMO consider necessary implemented. c) To include Pre Lay Grapnel Run (PLGR) works within the seasonal restriction. Natural England note that the definition of 'Emergency Works' is yet to be agreed with MMO and included within the relevant named plan/doc. We continue to advise that this is necessary and this point is unresolved. Please see Appendix G7 to our Deadline 7 submission for further mitigation suggestions to mrore fully minimise impacts on RT. |  | No | Partially resolved, part b) remains outstanding. The latest REAC states RTD mitigation will be applied during emergency works and this has been secured in the DCO/dML. Regards point a) the latest RTD protocol (Doc. 7.8 (E), section 1.5.15) includes a commitment to provide a log of activity within 4 weeks of any emergency works. Regards point b) there remains no process stated in the plan that would enable development of a Method Statement (or similar) that will need to be agreed with Natural England and MMO before emergency works can commence within the sensitive winter period.
7 | G11 | The Applicant should update their cumulative impacts assessment to account for smaller impacts that have, at present, been scoped out. Also to consider the ongoing impacts of London Array offshore wind farm. Further, a more detailed consideration of the potential interactions between Five Estuaries, North Falls and Sea Link through the project stages is needed to inform mitigation measures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No change. To resolve this matter an updated in-combination assessment or a seasonal restriction commitment as set out above is required. |  | Progressed: Following discussions had at the meeting on 1st April agreeing to additional conditions regarding 'emergency works' and further correspondence on the 2nd April agreeing to apply the seasonal restriction to all activities, Natural England can consider this issue resolved providing the relevant commitments are submitted by the Applicant at D6. |  | Issue resolved. Natural England welcomes the inclusion and commitment to a seasonal restriction for all works. Please see Appendix G7 to our Deadline 7 submission. |  | Yes
8 | G12 | Natural England are unable to agree with the conclusions of the EIA until a comprehensive assessment of all impacts are considered, including a demonstration that sufficient mitigation is proposed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No change. Please above comments in relation to seasonal restrictions |  | Progressed: Following discussions had at the meeting on 1st April agreeing to additional conditions regarding 'emergency works' and further correspondence on the 2nd April agreeing to apply the seasonal restriction to all activities, Natural England can consider this issue resolved providing the relevant commitments are submitted by the Applicant at D6. |  | Issue resolved. Natural England welcomes the Applicant's commitment of a full seasonal restricton to all offshore cable laying activities within the OTE SPA and its 2km buffer including the PLGR and non-emergency related operations and maintenance work. We also welcome the commitment to follow our best practice guidance on vessel movements throughout. In addition, Natural England notes that the 2km buffer is only secured within the CEMP as mitigation. Therefore we advise that it also needs to be secured within the DCO/dML. Once this is adequately secured we will consider this issue resolved Please see Appendix G7 to our Deadline 7 submission for furhter mitigation suggestions to more fully minimise impacts on RTD. |  | No | Resolved. The latest REAC states the 2km buffer is included in the DCO/dML as Condition 4(1)(b) of the DMLDCO Schedule 3, Requirement 6 Offshore Construction Environmental Management Plan Condition 4(1) of the DML Red Throated Diver Protocol. This suggests the commitment to include the PLGR run within the seasonally restricted period and apply this condition to the SPA and its 2km buffer has been secured and the matter is resolved.
9 | G16 | Natural England are unable to agree with the conclusions of the HRA until a transparent and comprehensive assessment of all impacts are considered, including a demonstration that sufficient mitigation is proposed |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. |  | No change. To resolve this matter an updated in-combination assessment or a seasonal restriction commitment as set out above is required. |  | Progressed: Following discussions had at the meeting on 1st April agreeing to additional conditions regarding 'emergency works' and further correspondence on the 2nd April agreeing to apply the seasonal restriction to all activities, Natural England can consider this issue resolved providing the relevant commitments are submitted by the Applicant at D6. |  | Natural England welcomes the Applicants commitment of a full seasonal restricton to all offshore cable laying activities within the OTE SPA and its 2km buffer including the PLGR and non-emergency related operations and maintenance work. We also welcome the commitment to follow our best practice guidance on vessel movements throughout. In addition, Natural England notes that although the 2 km buffer is only secured within the CEMP as mitigation, and therefore advises that it also needs to be secured within the DCO/dML. Once this is adequately secured we will consider this issue resolved. Please see Appendix G7 to our Deadline 7 submission for further mitigation suggestions to more fully minimise impacts on RTD. |  | No | Resolved. The latest REAC states the 2km buffer is included in the DCO/dML as Condition 4(1)(b) of the DMLDCO Schedule 3, Requirement 6 Offshore Construction Environmental Management Plan Condition 4(1) of the DML Red Throated Diver Protocol. This suggests the commitment to include the PLGR run within the seasonally restricted period and apply this condition to the SPA and its 2km buffer has been secured and the matter is resolved.
10 | G17 | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. |  | New issue |  | New issue |  | New Issue |  | Issue raised at Deadline 4. |  | No Change. Please see Appendix G5 to our Deadline 5 submission |  | Progressed: Following review of the Issue Specific Hearing (ISH) recordings from 26th of March [EV9-009] and further confirmation with the Applicant at a meeting on the 1st April, Natural England acknowledges and welcomes the inclusion of the 2km buffer for the proposed mitigation for RTD in the OTE SPA. Provided that this is confirmed and secured within named plans/documents within the Applicants submission at Deadline 6 Natural England would welcome this commitment and consider this issue resolved. |  | Issue resolved. Natural England welcomes the Applicants commitment of a seasonal restricton for cable installation to include a 2 km buffer around the OTE SPA. In addition, Natural England notes that although the 2 km buffer is only secured within the CEMP as mitigation, and therefore advises that it also needs to be secured within the DCO/dML. Once this is adequately secured we will consider this issue resolved. Please see Appendix G7 to our Deadline 7 submission for further mitigation suggestions to more fully minimise impacts on RTD. |  | No | Resolved. The latest REAC states the 2km buffer is included in the DCO/dML as Condition 4(1)(b) of the DMLDCO Schedule 3, Requirement 6 Offshore Construction Environmental Management Plan Condition 4(1) of the DML Red Throated Diver Protocol. This suggests the commitment to include the PLGR run within the seasonally restricted period and apply this condition to the SPA and its 2km buffer has been secured and the matter is resolved.
11 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). Natural England advises there is a risk of an AEoI occurring from visual and noise disturbance from the use of a hover craft. Therefore, further information on the use of the proposed hovercraft is required before we can advise further on the impact to designated sites. |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue |  | New issue identified following review of documents submitted at Deadlines 6. Please see the Cover Letter and Appendix G7 to our Deadline 7 submission. |  | No | Unresolved. No new information provided yet. Unresolved. See also above comments regarding emergency works in the SPA more generally.

## H - Suffolk LVIA
Point | Point Number(s) from Appendix H RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix H - Suffolk & Essex Coast and Heaths Designated Landscape - Landscape Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved at End of Examination | Consultation, actions, progression | RAG SoS Int Parties Cons 1
1 | H1 | Without further information, Natural England is concerned that the project may have a significant impact (in EIA terms) on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. Same at H2 so greyed out/removed | [15 empty] | Yes
2 | H2 | Natural England is concerned about the significant (in EIA terms) cumulative impact that the project’s construction phase will have on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. We note that no compensation is proposed, and it is not clear how the project has sought to further the purposes of the Suffolk & Essex Coast & Heaths National Landscape. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change. See Appendix H4 of Natural England's Deadline 4 submission for detailed advice. |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | Partly Resolved. Natural England notes that a Statutory Undertaking has been agreed beween the developer SCC and the National Landscape for the provision of a sum to contribute towards funding projects within the affected area of the National Landscape, and a project officer to adminsiter this. Although we note this matter is incuded as a contribution to furthering the purpose of the National Landscape, our comments regarding the assessment, suitibility of the 6Ha proposals and advice that impacts to acid grassland within a National Landscape shoud be avoided, remain unchanged.
3 | H3 | The assessment in Table 2.1 should be expanded to ensure that it can be understood with respect to impacts on the specific Suffolk and Essex Coast & Heaths National Landscape Indicators. Natural England are expecting significance of effects to be reported at this special quality scale so it is clear which part of the baseline may change. Natural England are unclear which special qualities of the Suffolk & Essex Coast & Heaths National Landscape will be affected by this proposal, and we advise that this information is essential to the assessment. For example The “intactness of the landscape” SQ specifically refers to the important of acid grassland and heath. Natural England advise that impacts to this SQ are clearly assessed. |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled however at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
4 | H4 | Further baseline information is required to clarify the extent and habitat type which are impacted by the cable route within the Suffolk & Essex Coast & Heaths National Landscape and its setting. This information is required to understand the scale of impact on very highly susceptible features of the landscape, such as acid grassland. Table 2.1, Document: 6.3.2.1.C highlights that acid grassland is an important defining element of natural beauty for the Suffolk & Essex Coast & Heaths National Landscape. There is also insufficient evidence used to justify that the impacts to acid grassland are small scale Natural England does not agree that impacts in relation to small geographical extents can moderate impact to statutory purposes. Information should indicate the exact locations for trenched and trenchless cable construction. This information should be used to inform a clear justification on the use of open cut techniques within the Suffolk & Essex Coast & Heaths National Landscape. In addition it is not clear if the 4.05 ha of land within the extended golf club will be able to be reinstated. Will this area remain in operation as a golf course following reinstatement? It is not clear how the golf course proposals have been considered in combination with the proposal. Natural England advise that the Applicant provides detail on how the location of the enhancement area for acid grassland within the Suffolk & Essex Coast & Heaths National Landscape was chosen (also see H12). We note that there are two types of acid grassland defined in the management plan, this is lowland dry and also lowland dry + heathland. It is not clear which habitat type is impacted, and Natural England advise that this is clarified (this information cannot be worked out from the Phase I mapping). |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | Partly Resolved. Although we welcome that pH will be collected it has not been used to inform the site selection or suitability of the compensation area. We maintain that impacts should be avoided by employing trenchless techniques. In additon we highlight that the compensation area 6ha is less than the impact footprint.
5 | H5 | Clarity is needed on: (1) the methodology used to assess impacts on the setting of the Suffolk & Essex Coast & Heaths National Landscape (2) the conclusions made in terms of impacts to the setting of the Suffolk & Essex Coast & Heaths National Landscape (3) Clarification is required on what the impact on users of the Suffolk Coast Path is assessed to be. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
6 | H6 | Natural England remains unclear on the realistic anticipated overall timeframe for construction and reinstatement (of soils, habitats and hedgerows) in relation to works within the NL and its setting, and we advise that these details are clearly set out and evidenced. The Applicant should set out how much habitat will be affected by the cable route, where habitat will be reinstated, and the timescales involved for the works (for construction and reinstatement). It remains unclear which areas will be impacted and reinstated. For example, will the area of the golf course disturbed and reprofiled (4.05 ha) impact any reinstatement potential in this area? The magnitude of landscape effects (as assessed) is dependent on the short duration and reversibility of works, which should be evidenced. We advise that the complexity of this habitat some of which is priority habitat and added risks of reinstatement, including time to reach functionality should be evidenced in the LVIA. NE advises that the Applicant needs to set out information on the recoverability of habitats post-construction, highlighting any risks to this. This information should include the justification used to assume full reinstatement by year 15, and in line with the mitigation hierarchy, clear justification for why open cut trenching methods within the Suffolk & Essex Coast & Heaths National Landscape and its setting cannot be avoided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
7 | H7 | Multiple major projects will combine to cause significant adverse impacts on the statutory purpose of the Suffolk & Essex Coast & Heaths National Landscape. This conclusion of adverse and significant effects on the Suffolk & Essex Coast & Heaths National Landscape and Suffolk Heritage Coast requires further consideration. We advise that further assessment (in alignment with GLVIA) is required (used) to underpin this conclusion (is provided), and that impacts are reported in terms of impacts on the Special Qualities of the Suffolk & Essex Coast & Heaths National Landscape, and in relation to information on anticipated construction schedules. Natural England advises the Applicant engages with all parties on how compensation can be achieved, in consultation with the Suffolk & Essex Coast & Heaths National Landscape partnership and Natural England. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change. As Above at point 2.
8 | H8 | The Applicant should provide further information to support the assessment of impacts to Suffolk Heritage Coast, and the conclusion of minor adverse construction effects. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at 1A, change request and 2. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
9 | H9 | Any replacement planting should reflect the Landscape Character of the area. This should be specifically clarified within the outline vegetation reinstatement plans. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at 1A, change request and 2. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
10 | H10 | The commitments register should include contingency measures should reinstatement plans fail, or should reinstatement not be achievable within the timeframes stated. This is particularly important for acid grassland, and for this habitat, the commitments register should reflect the contingency measures described in 6.7.3 of the oLEMP. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding andtherefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
11 | H11 | Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023. It is not clear how the project proposes to further the purposes of the national landscape. Natural England refer the developer to Guidance for relevant authorities on seeking to further the purposes of Protected Landscapes - GOV.UK for further advice. The developer may also wish to speak to the National Landscape team for further advice on possible opportunities. The guidance refers to avoiding harm, and contributing to conservation and enhancement. We would expect the duty to be applied (where reasonably practical) to each stage of the mitigation hierarchy to achieve the conservation aim of the duty. The guidance also refers to enhancement and therefore we would advise that this aspect also needs to be considered to 'further the purpose' of the designation. We have advised that the mitigation hierarchy applies to each stage of the assessment of impact. We advise that a clear justification is required detailing why avoidance of impact through employing trenchless crossings in the Protected Landscape, has not been pursued. Natural England understand that 6ha of acid grassland enhancement and creation are being put forward to satisfy the new duty, in relation to the direct temporary construction impacts on acid grassland within the protected landscape. Natural England advise that the Applicant provides clarity and justification as to whether the proposals are to conserve and enhance, and how the duty has been applied at each stage of the mitigation hierarchy. |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change |  | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | As above
12 | H12 | From the information provided it is not clear how the 6Ha proposals seek to further the purposes of the Protected Landscape. The current baseline of the 6Ha enhancement area appears to include priority deciduous woodland habitat and biodiversity interest, it is not clear how the enhancement proposals may themselves impact on an area of existing value for biodiversity. It remains unclear what the existing baseline pH is for this area and how the applicant has considered impact pathways from the adjacent pig farm and cultivated land on any potential for reinstatement of acid grassland in this location. It is not clear which Special Qualities and Indicators will be targeted by the acid grassland enhancement. We advise that an explanation of how 10 years is a sufficient length of time in which to manage this area to a sufficient standard to compensate for direct impacts to acid grassland in the Protected Landscape. We continue to advise that in accordance with the mitigation hierarchy and the importance of this habitat landscape in both landscape, and ecological terms, the project should avoid sensitive habitats and employ trenchless techniques in this area. | [9 empty] | Natural England have reviewed all current information and documents provided by the Applicant up until Deadline 4 which has not substantially changed our position from our Deadline 4 response [REP4-194]. Natural England have no additional advice to provide. |  | Natural England has a meeting scheduled with the Applicant. However at this junction we consider that a change of position is unlikely and therefore we consider this matter remains outstanding and it is likey that we will agree to disagree with the Applicant regarding this issue following review of all submitted material. In addition to our Deadline 6 response (provided in Appendix H6) Natural England has provided addional information regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6). |  | This matter remains outstanding and therefore Natural England agree to disagree with the Applicant regarding this issue following review of all submitted material. Please see our Deadline 7 Appendix H7 for a summary position statement in addition to our Deadline 6 response for detailed advice (provided in Appendix H6). Natural England also provided an addional narrative regarding all outstanding LVIA matters for the Applicant to consider (see Annex 1 to Appendix H6 at Deadline 6). |  | No | No change.
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removing refs amending furthering the purpose ref the purpose