## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 3 Submission.
For:
The construction and operation of Morgan and Morecambe Ofshore Wind Farms Transmission Assets Offshore Wind Farm, located approximately 0 - 37 km km from Northwest English Coast in the Irish Sea.
Planning Inspectorate Reference EN020028
07 July 2025

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Morgan and Morecambe Offshore Wind Farms Transmission Assets examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relevant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO/ dML B - Physical Processes C - Benthic Subtidal and Intertidal Ecology D - Fish and Shellfish E - Marine Mammals F - Offshore Ornithology G - Onshore Ecology H - Onshore and Intertidal Ornithology I - Fylde MCZ The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status. Insert background text on how the R&I tabs have been set out as needed
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be an ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Natural England's Principal Areas of Disagreement Summary Statement (PADSS)
As per our response to the Rule 6 letter Natural England will be updating our PADS at Deadlines 1, 3, 4 and 6.
Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | Rel Rep RAG rating and D1 | Update on Progression at Deadline 3 | RAG D3
Development Consent Order (DCO and deemed Marine Licence (dML)
NE1 | Definition of commence with respect to the offshore works. | This definition is linked directly to the definition of offshore preparation works and excludes the works detailed under offshore preparation from the definition of commence. We would note that this definition of commence is different to those used and accepted under a wide number of consented offshore wind projects | The definition of commence and offshore preparations works within the DCO and all three DMLs must be amended. | It is possible this issue could be progressed following amendments requested. |  | Resolved. NE welcomes the updated wording for the definition of "commence" in Article 2 (a) of the DCO and dMLs 1 and 2.
NE2 | Duration of submitting pre-construction plans before construction begins | Due to the increasing complexity of construction of large offshore works, the proposed four month consultation period is no longer appropriate. | The Applicant should amend the dMLs to allow for documents to be submitted at least six months prior to commencement. | It is possible this issue could be progressed following amendments requested. |  | Resolved. NE welcomes the update to the DCO Schedules 14 and 15 Part 2 Condition 19 (1) requiring pre-construction documentation to be submitted at least six months prior to commencement.
Benthic Ecology and Physical Processes
NE3 | Worst Case Scenario (WCS) during construction, operation and maintenance. | Natural England advise that there are a number of potential impacts both on benthic ecology and physical processes which have not been adequately considered or assessed within the Environmental Statement (ES). | Natural England advises that the ES and where relevant, Marine Conservation Zone (MCZ) assessment, are updated to consider all potential pathways of effect on intertidal and subtidal benthic habitats. | It is possible this issue could be progressed if the Applicant follows SNCB advice. |  | No change.
NE4 | Removal of infrastructure at the decommissioning stage. | Natural England is concerned that there is currently no commitment to the removal of cable/scour protection at end of project life. | Natural England advise that the Applicant should include a commitment to remove cable/scour protection at end of project life and this should be secured within the DCO. | It is possible this issue could be progressed if the Applicant follows SNCB advice. |  | No change.
NE5 | Lack of cable protection location and design information. | There is currently insufficient information on the anticipated location, extent and design of cable protection measures placed along the Export Cable Corridor (ECC). Therefore, we are unable to fully understand the potential impacts of cable protection on sediment transport pathways, particularly within Fylde MCZ. | Natural England advise that where possible, further information is provided on the anticipated location, extent and design of cable protection measures. | Potential resolution. This is subject to the Applicant providing further information on cable protection location and design. |  | No change.
NE6 | Mitigation measures for Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats. | Natural England notes that no further mitigation in relation to physical processes or benthic receptors has been proposed. Additionally, there is no consideration for relevant NERC habitats. | Natural England advises that impacts to priority habitats listed under Section 41 of the NERC Act (2006) are avoided and due consideration is demonstrated. We advise that relevant Application documents should be updated accordingly, and this is secured within the DCO/DMLs. | It is possible this issue could be progressed if the Applicant follows SNCB advice. |  | No change.
NE7 | Lasting habitat loss/change from the placement of cable protection. | Natural England disagrees with the Applicant that 3.04ha of lasting habitat change/loss of subtidal sand and subtidal mud interest features from Fylde MCZ from the placement of cable protection will maintain the conservation objectives of the site. We advise that the Project is likely to cause lasting impacts on benthic features within Fylde MCZ. | Every effort should be made to reduce impacts through the adoption of robust mitigation measures. We advise that the MCZ assessment should proceed to a stage 2 assessment and provide a without prejudice Measure of Equivalent Environmental Benefit case. | Unless the Applicant’s position changes, it is unlikely that there will be agreement between the Applicant and Natural England during examination on this issue. |  | Resolved. The Applicant has undertaken a Stage 2 MCZ Assessment and without prejudice MEEB and submitted these into Examination at Deadline 1. Therefore this issue has been resolved at Deadline 2. Please note other comments relating to the MCZ assessment are not resolved. This comment has specifically been resolved as the Applicant has provided the documents requested. NE have provided further comments on the Applicants' In-Principle MEEB proposal in 'Tab J Benthic Compensation' of this R&I Log and Appendix J of our Deadline 2 submission.
Fish and Shellfish Ecology
NE8 | Long term loss of supporting habitat and potential loss of prey species (sandeel). | Dynamics between predator prey relationships for piscivorous birds and sand eel could be impacted due to loss of prey species. | Natural England advise that the loss of prey species (sandeel) due to long term habitat loss (from scour/cable protection) of supporting habitat should be assessed and updated in the final ES chapter. | It is possible this issue could be progressed with further provision of information. |  | In progress. Natural England notes the justification in the Applicants response to NE's Relevant Representations comment RR-1601.49 in relation to Offshore Ornithology and long-term loss of habitat supporting prey species for the features of Liverpool Bay SPA in PDA-014. We also note the response to 1601.46 in relation to Fish and Shellfish Ecology. To fully resolve this issue the quantification utilised in RR-1601.49 should also be applied in the context of suitable spawning areas for prey species across the cable corridor within the Liverpool Bay SPA which could be lost during construction. This information should be updated in the relevant parts of the application, in particular the ISAA.
NE9 | Ribble Estuary MCZ assessment. | Natural England do not agree that smelt should be screened out, further assessment is required as the activity may be capable of affecting the protected feature of the MCZ. There is potential for electro-magnetic field (EMF) to cause barrier effects that hinder smelt movements in and out of the estuary. | Complete an assessment on potential EMF impacts. Provide further detail on proposed cable depth below the riverbed and detail pertaining to EMF from the cable below the Ribble estuary MCZ. | It is possible this issue could be progressed with further provision of information. |  | No change.
Marine Mammals
NE10 | UXO clearance | UXO clearance is included as a licenced activity in the DCO/marine licence (which includes high order clearance). We advise that a separate licence is sought for UXO clearance due to the lack of information available and the over precaution that must be incorporated into the impact assessment at this stage. | Natural England advise that UXO clearance should be authorised under a standalone marine licence post consent and removed from the draft DCO. | It is possible this issue could be progressed by removing UXO clearance from the DCO/DML. |  | No change.
Offshore Ornithology
NE11 | No assessment of long-term loss of habitat supporting prey species for the offshore ornithological features of Liverpool Bay Special Protection Area (SPA). | The Applicant has not screened in long term loss of habitat supporting prey species (due to scour/cable protection) for the offshore ornithological features of Liverpool Bay SPA as an impact pathway for Likely Significant Effect (LSE). | The Applicant should include an assessment of the indirect effect of long-term habitat loss due to scour/cable protection for prey species of the offshore ornithological features of Liverpool Bay SPA. | It is possible this issue could be progressed with further provision of information. |  | In progress. Natural England are satisfied with the justification in the Applicant’s response to NE’s Relevant Representations [PDA-014], they explained that the total area of potential habitat loss is considered small enough to rule out this impact pathway. Natural England are satisfied that the additional information on the predicted habitat loss in PDA-014 would allow adverse effects on the Liverpool Bay SPA to be ruled out. To fully resolve the issue, we recommend that this information is used to update the relevant parts of the application, in particular the Information to Support an Appropriate Assessment.
NE12 | Assessment and conclusion of no adverse effect on site integrity for the red-throated diver and common scoter features of Liverpool Bay SPA. | Natural England do not agree that an adverse effect on site integrity for the red-throated diver and common scoter features of Liverpool Bay SPA can be ruled out due to the displacement and disturbance impacts of the Project in-combination with other projects during the sensitive winter period. | The Project’s impact can be removed by the Applicant committing to a full restriction on construction activity within the wintering months of November-March inclusive. | Potential resolution. This is subject to the Applicant bringing forward an appropriate seasonal restriction to address the potential impacts to the species. |  | Resolved. The Applicant has now committed to a restriction on all construction activity and UXO clearance from November to March (inclusive) within the original Liverpool Bay SPA boundary plus a 2km buffer. This addresses Natural England's concerns and AEoI can now be ruled out for the red-throated diver and common scoter features of the SPA.
Onshore Ecology and Nature Conservation
NE13 | Impacts to sand dune Lytham St Annes SSSI features. | Issues remain around certain features particularly changes to the water table, dewatering effects during construction using Transition Joint Bays (TJB) and the impacts on dune slack vegetation. | The Applicant needs to more thoroughly assess the impacts on dune slack vegetation and consider a more precautionary approach with regards to the recoverability / resilience of the dune slacks relating to dewatering effects. | It is possible this issue could be progressed with further provision of information including additional monitoring of water table pre- and post- construction and sufficient baseline data. |  | No change.
NE14 | Additional information required on Direct Pipe Trenchless Technique to be able to fully assess the potential impacts to Lytham St. Annes Dunes SSSI. | Insufficient detail on Direct Pipe, to fully assess the potential impacts on the SSSI. No inclusion of an outline contingency plan and no assessment of the Worst Case Scenario (WCS) i.e. no other option assessed if Direct Pipe is not an option. | Provide further detail on the Direct Pipe methodology to be able to fully assess the potential impacts to the SSSI. Assess the WCS including a contingency should Direct Pipe not be possible. | It is possible this issue could be progressed with further provision of information. |  | No change.
NE15 | Lack of sand dune habitat survey effort. | From the information provided, Natural England advise that there is insufficient evidence for us to be able to advise on the scale and significance of impacts to dune slacks at St. Annes Old Links Golf Course BHS. | The Applicant needs to undertake detailed dune slack surveys across the Study Area to inform the EIA. These surveys need to be undertaken during summer 2025. | It is possible this issue could be progressed with further imminent survey effort and provision of information. |  | No change.
NE16 | Lack of Agricultural Land Classification (ALC) survey effort. | From information provided, Natural England advise that there is insufficient evidence for us to be able to advise on the scale and significance of impacts to soils. | The Applicant needs to undertake a detailed ALC and soil survey of the agricultural land across the full Study Area to inform the EIA. These surveys need to be undertaken during summer 2025. Natural England advises that the commitment to restore land needs to be secured in the DCO. | It is possible this issue could be progressed with further imminent survey effort and provision of information. |  | No change.
NE17 | Developing on areas of restorable peat. | There is insufficient information to ascertain whether the proposal will have direct or indirect impacts on deep peat. | Provide further evidence to show if restorable peat is present. This should include peat data for the route of the cables and include soil cores in the areas mapped as deep peat England Peat Status Greenhouse Gas and Carbon Storage. | It is possible this issue could be progressed with further provision of information. |  | No change.
Onshore and Intertidal Ornithology
NE18 | Impacts to Ribble and Alt Estuaries SPA/Ramsar site intertidal waterbirds due to the landfall works. | Natural England advise that the proposed level of restriction to the landfall works is insufficient to avoid an adverse effect on the Ribble & Alt Estuaries SPA/Ramsar site. | The Applicant should develop comprehensive seasonal restrictions for the key intertidal species and months of the year. These should be underpinned by updated HRA conclusions based on data from site specific surveys, and a more thorough assessment of the potential habitat loss/disturbance effects and their implications for SPA/Ramsar site species. | Potential resolution This is subject to the Applicant bringing forward an appropriate level of seasonal restriction to address the potential impacts to the species. |  | Progressed but not resolved. The Applicant has now committed to a restriction on all construction activity from November to March (inclusive) at landfall. This addresses Natural England's concerns regarding the over-wintering features of the SPA and Ramsar site, however our concerns regarding the passage features of the SPA and Ramsar site remain outstanding.
NE19 | Lack of an in-principle derogations case for impacts to intertidal SPA/Ramsar site waterbirds. | Unless effective seasonal restrictions for the wintering and passage periods can be committed to, we advise that an in-principle derogations case will need to be developed. This would need to demonstrate no alternative solutions to delivering the public interest objectives of the project and Imperative Reasons of Overriding Public Interest (IROPI). | A robust in-principle derogations case should be submitted into the Examination, including a demonstration that a greater degree of seasonal restriction is not achievable, and a far more detailed submission regarding the installation and management of the compensatory measures. | Potential resolution. This is subject to the Applicant providing an in-principle derogations case demonstrating that there are no alternative solutions to delivering the project’s objectives, including a greater degree of seasonal restriction, and a detailed proposal for compensatory measures. |  | Progressed but not resolved. The Applicant has now committed to a restriction on all construction activity from November to March (inclusive) at landfall. This addresses Natural England's concerns regarding over-wintering SPA and Ramsar site birds, but without further mitigation, AEoI cannot be ruled out for the passage features of the SPA. We still have concerns regarding the effectiveness of the proposed initiative at Fairhaven saltmarsh and continue to consider that it constitutes compensation, not mitigation.
NE20 | Impacts to Ribble and Alt Estuaries SPA/Ramsar terrestrial waterbirds. | Natural England advise that there is not currently enough information within the Application to rule out impacts for wintering, passage and terrestrial features of Ribble and Alt Estuaries SPA/Ramsar site. | We require further clarity from the Applicant on the following aspects: HRA conclusions should be based on data from site specific surveys, habitat loss and its implications for SPA/Ramsar site species should be further quantified, proposed mitigation areas need further justification on their appropriateness. | Potential resolution. This is subject to the Applicant providing further information to support their HRA conclusions, consideration of spatial scheduling to reduce the level of impact, and greater detail on the proposed mitigation habitats. |  | Progressed but not resolved. The Applicant has provided further information on the proposed mitigation areas in [REP2-045] and [REP2-018]. However, a high level review indicates the information still lacks sufficient detail in regards to mitigating impacts to SPA/Ramsar site waterbirds.
NE21 | Mitigation of impacts to Newton Marsh SSSI. | Impacts to Newton Marsh SSSI have not been sufficiently assessed. There is minimal information on what works will take place in close proximity to this site and how the work will be managed to not affect the site. | Natural England advise that further consideration of Newton Marsh SSSI is included and updated within the assessment. Further justification should be provided on how the Applicant has concluded no risk to the site and what mitigation measures might be implemented. | It is possible this issue could be progressed with further provision of information. |  | Resolution in progress. The Applicant has provided further information in [REP2-044] regarding Newton Marsh SSSI and the River Ribble crossing which has satisfied our concerns. Given Newton Marsh SSSI is well used by SPA waterbirds, it is necessary to update the ISAA in due course to set out why Newton Marsh SSSI will not be impacted by the construction phase. This would then fully resolve our concern.
Fylde MCZ
NE22 | MCZ assessment and Measures of Equivalent Environmental Benefit (MEEB). | Natural England do not agree with the Applicants conclusion of no likelihood of hindering the conservation objectives of Fylde MCZ, which has been designated for subtidal sand and subtidal mud. It is our opinion that the impact on Fylde MCZ will be long term and will alter the extent of the physical attributes and distribution of biological communities supported by these features. | Natural England advise that every effort should be made to reduce the impacts through the adoption of robust mitigation measures, including commitments to remove infrastructure at the decommissioning phase. Natural England advise that the MCZ assessment should proceed to a stage 2 assessment and provide a without prejudice MEEB case. | Unless the Applicant’s position changes, it is unlikely that there will be agreement between the Applicant and Natural England during examination on this issue. |  | Resolved. The Applicant has undertaken a Stage 2 MCZ Assessment and without prejudice MEEB and submitted these into Examination at Deadline 1. Therefore this issue has been resolved at Deadline 2. Please note, other comments relating to the MCZ assessment are not resolved. This comment has specifically been resolved as the Applicant has provided the documents requested. NE has provided further comments on the Applicants 'Without prejudice MEEB proposal in 'Tab J Benthic Compensation' of this R&I Log and Appendix J of our Deadline 2 submission.

## A - DCO DML
Point | Point Number(s) from Appendix A [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix A - DCO and dML | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_A1 | A1/A4 | The definition of commence and offshore preparations works within the DCO and all dMLs must be amended by the Applicant to exclude all works except pre-construction surveys to inform the construction plans and mitigation. |  | Resolved. NE welcomes the updated wording for the definition of "commence" in Article 2 (a) of the DCO and dMLs 1 and 2.
RI_A2 | A2/A10 | Due to the increasing complexity of construction of large offshore works, we advise that six months is considered an appropriate period prior to construction, not four months as stated in Schedules 14 and 15 Part 2 Condition 19 (1), [APP-005]. |  | Resolved. NE welcomes the update to the DCO Schedules 14 and 15 Part 2 Condition 19 (1) requiring pre-construction documentation to be submitted at least six months prior to commencement.
RI_A3 | A3 | The definition of 'maintain' within the DCO and schedules 14-17 of the deemed Marine Licences (dML) restricts work that is materially different or has materially different impacts. The Applicant should amend the wording to ensure maintenance works do not lead to impacts in excess of those assessed within the ES. |  | Resolved. NE welcomes the updated wording for the definition of "maintain" in Article 1, Part 1 of the draft DCO and in Article 1, Part 1 of each of the dMLs at Schedules 14-17.
RI_A4 | A5 | The Applicant should remove the definition of Natural England in Article 2 (1) [APP-005] and replace with a definition of Statutory Nature Conservation Body (SNCB), all references to Natural England throughout the DCO and DML (and Schedules) should be amended to state the relevant SNCB. |  | No change. |  | No change.
RI_A5 | A6 | The Applicant should amend [APP-005] Schedule 2A Table 3 of the DCO to include maximum number and size of UXOs to remove using high order detonations. This should also be updated in Schedule 2B table 4 and in Schedules 14 and 15. If the information required to undertake a full assessment is not yet available, UXO clearance should not be included as a licensed activity in the DCO - a standalone Marine Licence should be sought post-consent from the MMO. |  | No change. The Applicant has proposed to remove high order unexploded ordinance (UXO) detonations and restrict the project to low order detonations. NE maintains its position that UXO detonation should be subject to a separate marine licence post consent, regardless of whether the removal is low or high order. Further, that the maximum number of detonations (low or high order), should be recorded on any consent granted. However, without prejudice to our position, we accept that low order removal is preferred. Additionally, whilst we welcome the inclusion of the maximum number of UXO's to be removed by low order, further information on how this number was derived should be provided. |  | No change.
RI_A6 | A7 | The Applicant has committed to Biodiversity Net Gain (BNG), but has not included it as a DCO requirement. The Applicant should include a requirement that secures the delivery and maintenance of BNG as a matter of good practice. |  | No change. |  | Natural England highlight that our initial comment was raised due to the Applicant's proposals for biodiversity benefit areas. However, we note the development is not subject to a mandatory net gain requirement. Therefore we reiterate our comment in RI_G35 and response to the ExA Q's 6.2.1 and 6.2.2. We therefore consider this matter closed at D3.
RI_A7 | A8 | Micro-siting around features of conservation importance, such as reef of Annex I quality, is a standard mitigation. We request that the requirement to consider micro-siting around features of conservation importance be secured within the DMLs, as it is currently with respect to archaeological interest features. |  | No change. We note that the Applicant has updated the wording in Schedules 14 and 15 to include 'environmental micro-siting requirements'; however, there is still no condition to micro-site around features of conservation importance secured within the dMLs. |  | No change.
RI_A8 | A9/A14 | a) Natural England requests that a condition to secure an updated Offshore Operations and Maintenance Plan (OOMP) be included, we note this is a standard condition of most OWFs. b) Additionally, it should be stipulated within the OOMP that cable protection may only be deployed under this consent for a period of ten years post-construction outside of Fylde MCZ, and no deployment of cable protection during O&M within Fylde MCZ. Any additional cable protection within Fylde MCZ will require a new Marine Licence. |  | No change. We note that condition 11 in Schedules 14 and 15 the dMLs require that an OOMP is submitted, with SNCB consulted prior to approval and must provide for review and resubmission every three years during the operational phase. However, the condition does not secure that no cable protection should be deployed later than 10 years post-construction outside of Fylde MCZ, and no deployment of cable protection during O&M within Fylde MCZ. |  | No change.
RI_A9 | A11 | Schedule 14 and 15 Part 2 Condition 20 relates to the detonation of UXOs, however there is no mention within this condition of securing the use of Noise Abatement Systems (NAS). Amend the condition to include the need to consider the use of NAS. |  | Resolved. The Applicant has updated the draft DCO to limit UXO clearance authorised under the DCO and dMLs to low order clearance only. Therefore the requirement for securing the use of NAS is redundant.
RI_A10 | A12 | Schedule 14 and 15 Part 2 Conditions 24, 25 and 26 do not include any of the detailed ecological monitoring required. We would expect benthic surveys to be conducted to identify any features of conservation importance. We would also expect post-construction monitoring to be secured for any features of conservation importance identified in the pre-construction surveys that are predicted to be impacted by construction, in order to monitor their recovery. The Applicant should update the monitoring conditions to secure these. |  | No change. |  | No change. Natural England notes the Applicant's response ([PDA-015], 1601.A.12). Whilst we acknowledge the conditions require submission of relevant monitoring plans in accordance with the OIPMP, we highlight that there are several outstanding comments raised in our RR's which relate to further updates and ecological surveys to be included in the OIPMP. Therefore our concerns relate to the lack of proposed monitoring within the OIPMP rather than how this has been secured within the DCO. Additionally, we note the response provided by the Applicant and have removed reference to piling from our original comment.
RI_A11 | A13 | The recent SoS decision for Sheringham and Dudgeon Extensions Project (SADEP) approved Condition 20 in Schedules 10 and 11 of SADEP DCO based on a recommendation from Natural England and the MMO for particular impacts requiring remediation or further mitigation works. Natural England advises that a similar condition should be included within all offshore wind dMLs. |  | No change. |  | No change.
RI_A12 | A15 | Offshore emergency works have not been clearly defined by the Applicant within the outline OOMP or the DCO. We advise that the Applicant should define ‘offshore emergency works’ in the DCO/dML and this definition should be updated within the outline OOMP. The MMO’s guidance on emergency works offshore should be followed and referred to within the Application. |  | No change. Natural England notes the Applicants response [PDA-015], but NE maintains that activities which are standard operation and maintenance and those which would be considered an emergency should be clearly defined to avoid ambiguity, and measures should be put in place to ensure that even in emergencies impacts to designated sites are minimised as much as possible. |  | No change.
Additional issue identified following D1 submissions
R1_A13 | A16 |  |  | After reviewing [REP1-009] submitted at D1 Natural England identified an additional issue in the draft DCO not previously raised at RR/WR. Natural England notes that the provision in Schedule 12 para 5 (1) would restrict our onshore consultation time to a maximum of 10 days with no ability to request extension unless we request further information. Our standard turn-around time for statutory consultations is 21 days. The documents being consulted on are often of a highly technical nature requiring input from several members of staff and this shortened timeframe would create a significant challenge in responding. Further, we note that the overall time period for approval of these documents is 8 weeks. Therefore, we request that this provision be amended to allow 21 days to respond and note this should not increase the overall time to approve these documents. |  | No change.

## B - Physical Processes
Point | Point Number(s) from Appendix B [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix B - Physical Processes | RAG Status Rel and Wri Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_B1 | B1/B8 | a) There is uncertainty regarding the likely success of the Direct Pipe Trenchless Technique. Further details on the Direct Pipe Trenchless Technique, associated infrastructure, and the sediment geology, is required to be able to fully assess the potential impacts on coastal processes at the landfall. b) An outline contingency plan should be developed, and the worst-case should assessed and included within the relevant Application documents i.e. cable installation failure when using the Direct Pipe Trenchless Technique. |  | No change. |  | No change.
RI_B2 | B2/B21 | There is currently no commitment to the removal of cable/scour protection at end of project life (decommissioning). Natural England advises that a commitment to remove all on and above seabed infrastructure associated with the development within benthic designated sites (excluding cable crossings) at the time of decommissioning should be secured in the DCO, to prevent permanent impacts to marine physical processes. Without a commitment in the DCO, the worst-case scenario should assess the impacts of leaving assets permanently in situ. It is also noted that leaving cable protection on the seabed even outside of designated sites is not aligned with OSPAR. |  | No change. |  | Progressed but not resolved. The Applicant has removed the option of 'rock dump' from the list of cable protection types to be used within Fylde MCZ in their updated Outline CSIP [REP2-023]. This is welcomed, but we continue to advise that a commitment with the action to remove all on and above seabed infrastructure (including cable/scour protection) within benthic designated sites is secured in the DCO.
RI_B3 | B3/B16/B17/B18 | a) There is currently insufficient information on the anticipated location, extent and design of cable protection measures placed along the Export Cable Corridor (ECC). Further information should be provided on location, extent and design of cable protection measures for us to advise on the potential impacts of cable protection on sediment transport pathways, particularly within Fylde MCZ . b) Further consideration within the assessments should be given to changes to sediment transport processes and seabed morphology due to the placement of cable protection measures at these locations. This should be updated within the relevant Application documents. c) Further options to minimise/mitigate impacts from cable protection on physical processes should be explored. |  | No change. |  | No change. We note the Applicant's response in ([PDA-016], 1601.B.18). We highlight that this response misquotes one of the Applicant's commitments: "CoT47 states that no foreign material will be placed on the bed’s surface in the inter-tidal region and low profile/tapered armouring would be employed in shallow water should this be required." This differs to the wording provided for CoT47 in the Applicant's Commitment Register [REP2-011] which relates to cable protection and sandwave clearance within Fylde MCZ.
RI_B4 | B4/B15 | a) We note that limited mitigation in relation to physical processes or benthic receptors during sandwave and boulder clearance has been proposed and further consideration should be demonstrated. b) Natural England advises that impacts to priority habitats under Section 41 of the NERC Act 2006 are avoided and due consideration is demonstrated. We advise that relevant Application documents should be updated accordingly and this is secured within the DCO/DMLs. |  | No change. |  | No change.
RI_B5 | B5 | We advise that the Applicant adequately considers the potential for a four-year gap between the completion of the first project (i.e. Morgan) and the commencement of the second (i.e. Morecambe) for 'Construction Scenario 3b'. We advise the MDS is updated within the Project Description and relevant Chapters to account for this, taking into consideration the potential for the recovery of seabed species and habitats resulting in outdated baseline data. We also advise that the relevant impact assessments are updated and outcomes taken account of in named plans. |  | No change. |  | No change. Natural England's original concerns in our Rel Reps [RR-1601] remain. Whilst we welcome the Applicant's further consideration [AS-070] of the MDS for construction, for the reasons discussed in our Rel Reps, we are concerned that a 'sequential' rather than 'concurrent' construction scenario may be the WCS for impacts to seabed morphology, physical features and adjacent shorelines (e.g. intertidal and nearshore zones, coastal morphology, and Fylde MCZ).
RI_B6 | B6 | It is not clear that the 9% and 10% total cable corridor values for sandwave clearance and cable protection respectively refer to the MDS requirements for each of the individual 6 cables (noting that each will have its own trench) or collectively. Similarly, clarity on the MDS specifications within and outside the Fylde MCZ should be provided. We advise that the MDS for construction and cable protection footprints are reviewed and updated where necessary across all ES chapters and named plans. And specific areas and volumes included for cable protection within and outside Fylde MCZ on the DCO/dML. |  | No change. |  | Resolved. The Applicant has provided further clarification on individual cable vs. collective MDS for sandwave levelling in [PDA-016]. However, please see B10 below in relation to concerns with sandwave levelling. And for cable protection quantities please see B12, B15, B18 and C2, C5, C9 C16, C25
RI_B7 | B7 | Natural England requires a plan showing the location of the proposed exit pits and Transmission Joint Bays (TJB) within the Application documents to be able to fully advise on the potential impacts of cabling under Lytham St Annes Dunes SSSI and St Annes Old Links Golf Course BHS. |  | No change. |  | Resolved. The Applicant has provided a plan showing the location of proposed exit pits and TJBs at Deadline 1 [REP1-040].
RI_B8 | B9 | Natural England notes that the MDS for Pre-Lay Grapnel Run (PLGR), Unexploded Ordnance (UXO) clearance and boulder clearance have not been fully assessed within the ES Chapters. It is stated in the documents that “this is to prevent double counting of the seabed footprint parameters”. However, there is no certainty that these activities will be undertaken at the same time or within the same footprint as the other site preparation activities especially the relocation of boulders. We advise the MDS figures for each of these activities should be presented in the Project Description and all other relevant chapters in line with Natural England’s Best Practice Guidance Phase III. |  | No change. |  | No change.
RI_B9 | B10 | We note that the MDS for sandwave clearance and seabed preparation is 1,426,900m3. However, this has not been broken down any further into individual activities, location, nor has a sandwave clearance impact width and length been provided and assessed. Natural England advises that the Applicant provides all the parameters associated with sandwave clearance and seabed preparation and the tools to be used for sandwave levelling to ensure the MDS and WCS have been assessed. This information should be included and updated within the ES Chapter and/or relevant named plan. |  | No change. |  | No change. We note the Applicant's response to our Relevant Reps and acknowledge that sandwave impact width and length have been provided [PDA-016]. However, it is still not clear if all of the parameters have been provided to determine the total spoil volume. Additionally, this has not been broken down into individual sandwave clearance/seabed preparation activities. Once all of the parameters have been provided and included in the ES, this issue can be readily resolved.
RI_B10 | B11 | Natural England advises that further assessment of the feasibility of the following cable installation tools: ploughing, jetting, mechanical cutting in shallow waters is required to support the worst-case scenario assessment for nearshore cable installation. |  | No change. |  | No change.
RI_B11 | B14/B29 | a) Natural England advises that the worst case impacts from UXO clearance in relation to marine processes, including recovery is further assessed. b) Whilst the Applicant has stated UXO clearance activities may take place within Fylde MCZ; we advise that UXOs should be moved outside of the MCZ prior to detonation. The Applicant should demonstrate why they have not committed to this mitigation. This information should be included and updated within the ES Chapter and/or relevant named plans. |  | No change. |  | No change.
RI_B12 | B16 | We advise that further information is provided by the Applicant on how seabed mobility has been considered with regards to cable protection requirements and locations in relation to this specific Application. This should be updated and included within the ES chapters (including those relating to landfall) and in the Outline CSIP. |  | No change. |  | No change. To expand on our Rel Reps and resolve this comment, we advise that seabed mobility needs to be adequately assessed along the export cable routes. This should consider rates and directions of bedform migration and, if possible, estimated bed elevation changes. We also advise that the 2023 ABPmer report, should be provided to increase understanding of seabed level variability and future seabed levels.
RI_B13 | B19/B22 | It is unclear what the potential impacts may be for intertidal Direct Pipe installation, trenching, and temporary infrastructure (e.g. cofferdams) on seabed and coastal morphology, and how recovery of the landfall location will be secured. Natural England advise that (a) the Applicant should consider and assess all potential impacts to seabed morphology that may arise due to trenchless landfall works during the lifetime of the Projects. Including size and duration of installation of cofferdams and potential disruption to coastal processes. And (b) produce an Outline Landfall Method Statement and secure this in the DCO/dMLs. Natural England also advises further information is needed about the location of the export cables across the beach. |  | No change. |  | No change. We note the Applicant's response to our Relevant Reps [PDA-016]. The Applicant has provided evidence and examples from other windfarms in relation to Direct Pipe installation. The response states that the Construction Method Statement (CMS) will cover landfall activities. However, an outline CMS has not been submitted into examination, therefore our original comment still stands.
RI_B14 | B20 | It is unclear in [APP-042] 1.10.4.1 what is meant my 'foreign material'. Natural England advises that the Applicant secures a commitment that no foreign material will be placed above the surface (winter beach levels), which could potentially interfere with sediment transport pathways. We advise that this is also secured in the DCO/DMLs. |  | No change. |  | No change. The Applicant has confirmed that their sentence 'no foreign material will be placed on the beach above the surface' relates to the O&M stage. Natural England continues to advise that this is secured as a commitment and in the DCO/dML's. We also highlight our response to RI_B3 above which is also applicable here.
RI_B15 | B21/B31 | Whilst we recognise that several cable protection types have been presented, no commitment to using a specific cable protection has been made. Natural England advises the selection of cable protection should favour those engineering options which reduce potential impacts to marine processes and have the greatest likelihood of successful removal at decommissioning. |  | No change. |  | Progressed but not resolved. We note that the Applicant has removed the option of 'rock dump' from the list of cable protection types to be used within Fylde MCZ in their updated Outline CSIP [REP2-023]. However, we continue to advise that a commitment with the action to remove all on and above seabed infrastructure (including cable/scour protection) within benthic designated sites is secured in the DCO.
RI_B16 | B23/B31 | Natural England advises that an outline Construction Method Statement and outline CSIP are provided/updated as part of the consenting stage to demonstrate that the WCS has been assessed, and any predicted impacts can be sufficiently mitigated. |  | No change. |  | No change.
RI_B17 | B24 | Natural England advises that surveys of the recoverability of the seabed, with a focus on sandwave reformation are undertaken to confirm predictions of recovery rates, and monitoring of the impacts of construction activities outside of Fylde MCZ on geomorphological receptors should be included for consideration in the Offshore In Principle Monitoring Plan (OIPMP). |  | No change. |  | No change. Natural England's concerns in our Rel Reps [RR-1601] remain. We continue to advise the Applicant to include a commitment to carry out monitoring of: - Sandwave recovery (particularly within Fylde MCZ); and - Dune/beach/intertidal morphology. These should be included for consideration in the OIPMP. In addition, we highlight that the Morgan Generation Project did include adaptive monitoring to monitor the changes to, and recovery of, sandwaves. See [REP5-043] of the Morgan Gen Examination submission.
RI_B18 | B32 | Natural England do not agree with the Applicants conclusion of no likelihood of hindering the conservation objectives of Fylde MCZ which has been designated for subtidal sand and subtidal mud. Natural England consider that any placement of scour prevention/cable protection has the potential to disrupt sediment process which could disrupt marine processes and have a lasting impact on interest features over the lifetime of the project and beyond which is potentially irreversible. |  | No change. |  | No change.
RI_B19 | B34 | Natural England advises that the Project is likely to cause lasting impacts on benthic features within Fylde MCZ. Natural England have provided further advice on Fylde MCZ in Appendix I. |  | Resolved. The Applicant has undertaken a Stage 2 MCZ Assessment and without prejudice MEEB and submitted these into Examination at Deadline 1. Therefore this issue has been resolved at Deadline 2. Please note other comments relating to the MCZ assessment are not resolved. This comment has specifically been resolved as the Applicant has provided the documents requested. NE have provided further comments on the Applicants' In-principle MEEB proposal in 'Tab J Benthic Compensation' of this R&I Log and Appendix J of our Deadline 2 submission.
Additional issue from Relevant Representations added and upgraded to Amber
RI_B20 | B13 | We note that the physical processes assessment for Morgan and Morecambe Transmission Assets was undertaken using a conceptual modelling approach, based off of Mona Offshore Wind Project. The Applicant has stated this is due to the Transmission Assets being located within the same geological formation as the Mona offshore export cable. Ideally, project specific numerical modelling of the impacts of cable protection in isolation should be undertaken to inform in-combination assessments for future projects. |  |  |  | We have included this comment from our Relevant Reps and upgraded to Amber in response to the ExA Q7.1.6 and the Applicant's response in [PDA-016] . We note that the impact of cable protection on physical processes was not modelled for Morgan Generation, whilst the Mona OWF Project numerical modelling did consider the impact of cable protection on physical processes. However, we also note that Mona OWF is c. 10km south of the Offshore Order Limits, and the Mona export cable corridor has a different route and landfall to that of the Morgan and Morecambe export cable corridors. Whilst it is stated that the Transmission Assets are located ‘within the same geological formation as the Mona offshore export cable”, it is unclear how/if the MDS project design parameters and environmental conditions for Mona compare with those for the Morgan and Morecambe Transmission Assets export cable corridors i.e. the suitability of the Mona export cable corridor model results as an analogue for Morgan and Morecambe Transmission Assets. We advise that the suitability of the Mona Offshore Wind Project modelling results to inform the Morgan and Morecambe Transmission Assets impact assessment, needs to be supported with additional information on the similarity of the MDS project design parameters and environmental conditions (e.g. sediment type and availability, water depth, wave and tidal regimes) between the various projects.

## C - Benthic Sub&Inter Ecol
Point | Point Number(s) from Appendix C [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix C - Benthic Subtidal and Intertidal Ecology | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_C1 | C1 | Natural England advises that there are a number of potential impacts both on intertidal and subtidal benthic habitats which have not been adequately considered or assessed within the Environmental Statement (ES). The specifics of which are included in the points within this worksheet. |  | No change. |  | No change.
RI_C2 | C2/C10/C44 | Natural England is concerned that MDS parameters are for cable protection to be installed at any point through the lifetime of the Project (including Operation and Maintenance), rather than the amount that will be required for the construction phase alone. Natural England advises that additional detail is needed on how the potential for the addition of further cable/scour protection during the O&M phase has been considered, and what proportion of the Maximum Design calculations for cable/scour protection the O&M requirements account for both within and outside of the MCZ. |  | No change. |  | No change.
RI_C3 | C3/C48/C50 | a) Natural England advises that the Project is likely to cause lasting impacts on benthic features within Fylde MCZ and that the sites ‘maintain’ conservation objectives will be hindered. b) Every effort should be made to reduce the impacts through the adoption of robust mitigation measures, including commitments to remove infrastructure at the decommissioning phase. c) We advise that the MCZ assessment should proceed to a stage 2 assessment and a without prejudice MEEB case provided. |  | Resolved. The Applicant has undertaken a Stage 2 MCZ Assessment and without prejudice MEEB and submitted these into Examination at Deadline 1. Therefore this issue has been resolved at Deadline 2. Please note other comments relating to the MCZ assessment are not resolved. This comment has specifically been resolved as the Applicant has provided the documents requested. NE have provided further comments on the Applicants' In-Principle MEEB proposal in 'Tab J Benthic Compensation' of this R&I Log and Appendix J of our Deadline 2 submission.
RI_C4 | C4/C32 | Natural England advises that impacts to priority habitats under Section 41 of the NERC Act 2006 are avoided and where that is not possible due consideration is demonstrated. Particular consideration should be given to those which are most sensitive and/or listed as threatened/in decline under OSPAR. |  | No change. |  | No change.
RI_C5 | C5/C28/C29 | Natural England strongly advises that a commitment to remove all infrastructure associated with the development at decommissioning is secured in the DCO. This should be provided in an Outline Decommissioning Plan should also be provided as part of the consent phase to detail the approach to decommissioning. |  | No change. |  | Progressed but not resolved. We note that the Applicant has removed the option of 'rock dump' from the list of cable protection types to be used within Fylde MCZ in their updated Outline CSIP [REP2-023]. However, we continue to advise that a commitment with the action to remove all on and above seabed infrastructure (including cable/scour protection) within benthic designated sites is secured in the DCO.
RI_C6 | C6/C26/C39 | Natural England notes that the Applicants current EIA assessment fails to consider or assess the potential pressures and impacts on the supporting benthic habitats for Special Protection Area (SPA) features, including Liverpool Bay SPA. Full consideration is required to inform a robust assessment of the likely impacts upon designated ornithological features. |  | No change. |  | Progressed but not resolved. In [PDA-014], the Applicant has stated that the total area of potential habitat loss is considered small enough to rule out this impact pathway (long-term loss of habitat supporting prey species). Natural England is satisfied that predicted habitat loss would allow adverse effects on the Liverpool Bay SPA to be ruled out. To fully resolve the issue, we recommend that this information is used to update the relevant parts of the application, in particular the Information to Support an Appropriate Assessment. Once updated in relevant application documents this matter can be resolved.
RI_C7 | C7 | We advise that the Applicant adequately considers the potential for a four-year gap between the completion of the first project (i.e. Morgan) and the commencement of the second (i.e. Morecambe) for 'Construction Scenario 3b'. We advise the MDS is updated within the Project Description and relevant Chapters to account for this, taking into consideration the potential for the recovery of seabed species and habitats resulting in outdated baseline data. We also advise that the relevant impact assessments are updated and outcomes taken account of in named plans. |  | No change. |  | No change. Natural England's original concerns in our Rel Reps [RR-1601] remain. Whilst we welcome the Applicant's further consideration [AS-070] of the MDS for construction, for the reasons discussed in our Rel Reps, we are concerned that a 'sequential' rather than 'concurrent' construction scenario may be the WCS for impacts to seabed morphology, physical features and adjacent shorelines (e.g. intertidal and nearshore zones, coastal morphology, and Fylde MCZ).
RI_C8 | C8 | It is not clear that the 9% and 10% total cable corridor values for sandwave clearance and cable protection respectively refer to the MDS requirements for each of the individual 6 cables (noting that each will have its own trench) or collectively. Similarly, clarity on the MDS specifications within and outside the Fylde MCZ should be provided. We advise that the MDS for construction and cable protection footprints are reviewed and updated where necessary across all ES chapters and named plans. And specific areas and volumes included for cable protection within and outside Fylde MCZ on the DCO/dML. |  | No change. |  | The Applicant has provided further clarification on individual cable vs. collective MDS for sandwave levelling in [PDA-016]. However, please see B10 below in relation to concerns with sandwave levelling. And for cable protection quantities please see B12, B15, B18 and C2, C5, C8, C9 C16, C25
RI_C9 | C9/C29 | Natural England notes that the cable protection types listed within the design envelope (Table 3.7) appear to be contradictory to the commitment for all cable protection to be removable from an environmental perspective. Due consideration should be given to the nature of the cable protection used and should favour those engineering options with the greatest likelihood of successful removal, from an environmental perspective, at the Projects’ end of life. |  | No change. |  | Progressed but not resolved. We note that the Applicant has removed the option of 'rock dump' from the list of cable protection types to be used within Fylde MCZ in their updated Outline CSIP [REP2-023]. However, we continue to advise that a commitment with the action to remove all on and above seabed infrastructure (including cable/scour protection) within benthic designated sites is secured in the DCO.
RI_C10 | C11 | a) Natural England advises that clarity is provided within the Application documents on the likely impacts from using Direct Pipe cable installation techniques. We advise that the following is provided and updated within the Application documents: - Scour protection requirements at the direct pipe exit and/or entry locations; - Cable/scour protection requirements in the intertidal and subsequent mitigation; and - MDS for the sum of both projects for ‘maximum cofferdam area dimensions’ to be included in Tables 3.6 and 3.13. b) We also advise that a landfall management plan should be provided in outline at the time of consent. All landfall impacts, including subtidal impacts, should be considered collectively to determine management/mitigation measures to ensure that significant impacts (both direct and indirect) are avoided to designated site features. |  | No change. |  | No change. Please aslo see our answers to the ExA Q7.1.4 and Q7.1.6 and our comment in RI_B13 with regards to cable/scour protection mitigation in the nearshore and the landfall management plan. We note the Applicant's response in ([PDA-017], 1601.C11), which states that no cable / scour protection will be required between MLWS and MHWS, we therefore advise that CoT114 is updated to include this wording.
RI_C11 | C12 | Natural England advises that a further assessment of the feasibility of the cable installation tools in shallow waters is required to support the worst-case scenario assessment. |  | No change. |  | No change.
RI_C12 | C13 | Natural England advises that storage options for material from the landfall exit pits and open cut trenching are explored to minimise impacts and allow for sufficient back filling. |  | No change. |  | No change.
RI_C13 | C14 | Natural England notes that the MDS for Pre-Lay Grapnel Run (PLGR), Unexploded Ordnance (UXO) clearance and boulder clearance have not been fully assessed within the ES Chapters. There is no certainty that these activities will be undertaken at the same time or within the same footprint as the other site preparation activities especially in relation to boulder relocation. We advise that the MDS for PLGR, UXO clearance and boulder clearance are presented within the Project Description and all other relevant chapters in line with Natural England’s Best Practice Guidance Phase III. |  | No change. |  | No change.
RI_C14 | C15 | Natural England advises that it is not clear how the MDS for sandwave clearance and seabed preparation has been derived. Natural England advises that the Applicant provides all the parameters associated with sandwave clearance and seabed preparation that were used to calculate the total MDS figure for ‘sandwave clearance: offshore export cable (m3)’ inside and outside of designated sites. These should be included and updated in the Project Description and the relevant Chapters in the ES to ensure that the impacts have been fully assessed. |  | No change. |  | No change. We note the Applicant's response to our Relevant Reps and acknowledge that sandwave impact width and length have been provided [PDA-016]. However, it is still not clear if all of the parameters have been provided to determine the total spoil volume. Additionally, this has not been broken down into individual sandwave clearance/seabed preparation activities. Once all of the parameters have been provided and included in the ES
RI_C15 | C16 | Natural England notes that the MDS sandwave clearance requirements stated are inconsistent between the Project Description [APP-024] and Benthic ES Chapter [APP-045] and named plans. No MDS figures for construction footprints have been presented within the Project Description. Natural England advises the maximum temporary construction footprints are reviewed and updated where necessary across the Application documents. |  | In progress. We note the updated MDS parameters for sandwave clearance in Table 1.1 [REP1-064] which lists the errata for sandwave clearance in [APP-045]. Once the changes are made to the applicable application documents and submitted into Examination this matter will be resolved. |  | No change.
RI_C16 | C17 | Natural England notes that within the CSIP it is stated that the distance between the cable crossings means that there will be separation in cable protection (rock armouring/mattress) making one linear line of protection. Natural England is concerned about the potential physical processes and benthic impacts from this which have not been assessed. We also assume that because this protection would be considered as cable crossing it would be considered permanent. Natural England advises that cable crossing requirements and impacts are reassessed to ensure that the MDS/WCS has been assessed. |  | No change. |  | Resolved. The Applicant has provided further clarification on this matter in [PDA-017]. We also note the Applicant has submitted their Stage 2 MCZ Assessment and without prejudice MEEB at Deadline 1 which includes further information regarding cable crossings in Fylde MCZ.
RI_C17 | C18 | Natural England is not clear how 14 cable repairs of a length of 56km has been determined. Currently as written, the cable repairs could be of any length. There is therefore a lack in consistency in WCS for cable repairs presented across the project description and named plans within and outside of designated sites. Natural England advises that clarification is provided by the Applicant on the maximum number of repairs per cable and in total, maximum length of each cable repair. Assessments and named plans should be updated accordingly. |  | No change. |  | No change. We note the Applicant's response in ([PDA-017], 1601.C.18). Our original comment was specifically in relation to how the cable repair parameters were written in the OOOMP [APP-224].
RI_C18 | C21/C27 | Natural England does not agree with the statement that there was a “relatively low abundance of burrows overall” that “were not consistent with a confident classification as the ‘sea pen and burrowing megafauna communities’. We note that this statement is contradictory to the findings of the Technical Report [APP-046] which found burrows to be ‘common’ in some locations, and therefore more numerous than the ‘frequent’ threshold required to meet the OSPAR definition for ‘sea pen and burrowing megafauna communities’. Natural England advises that (a) the ES is updated to accurately reflect the findings and conclusions of the technical report. And (b) where possible, impacts to these Features of Conservation Interest (FOCI) are minimised. To inform the updates Natural England also advises that the EIA should be updated, and appropriate sensitivity attributed to the benthic communities assessed as determined using MarESA. |  | No change. |  | No change.
RI_C19 | C22/C45 | It does not appear that that the duration, nature or area of seabed impacts from UXO clearance has been quantified or assessed within the ES chapters. We therefore require evidence that seabed depressions from both UXO detonations and jack-up legs will back-fill with similar sediment type and over what duration. Natural England requires the Applicant to quantify and evaluate the worst-case impacts from UXO clearance and jack-up events. |  | No change. |  | No change.
RI_C20 | C23 | Natural England advises that the ES Benthic Chapter [APP-045] is updated to consider impacts from construction of exit pits and/or cofferdam installation (where necessary) and associated site access and ancillary construction work areas. It has also not been stated whether or not scour protection may be required at the exit put locations and whether any such requirements would be temporary or permanent. |  | No change. |  | No change.
RI_C21 | C24 | Natural England notes that open cut trenching is likely to be required for each of the 6 cables at landfall. However, it does not appear that the MDS duration, nature or extent of benthic and water quality impacts from open cut trenching has been quantified or assessed. Natural England advises that the EIA and where relevant, MCZ assessments and named plans are updated to consider these impacts including an update with accurate worst-case prediction values for Suspended Sediment Concentrations (SSCs) arising from trenching in the Export Cable Corridor (ECC). |  | No change. |  | No change.
RI_C22 | C25 | Natural England notes that for cable landfall works there is a requirement for 2 x jack-up vessel deployments per cable out to KP10. Natural England queries how avoidance of benthic interest features and designated sites have been demonstrated? Natural England advises that as matter of best practice, the use of jack-up vessels should be excluded from benthic MPAs. Otherwise, clear justification as to why this is not possible and evidence of how impacts can be mitigated should be provided with evidence to support successful mitigation. a) We advise more detail and assessment is required regarding cable installation in shallow water depths below 11m in the ES Chapter and named plans. b) We also advise that an Outline Cable Landfall plan is provided and submitted into examination. |  | No change. |  | Progressed but not resolved. We welcome the Applicant's response stating the refinement of the MDS to account for one jack-up event per cable rather than 2 [PDA-017]. However, we advise that this should be updated in the relevant Application documents. Our other concerns (points a) and b)) still remain.
RI_C23 | C30 | Natural England strongly advises that the Applicant’s commitments; CoT108 and CoT109 should include removal of all cable protection at the decommissioning phase within Fylde MCZ, rather than only stating it will be designed to be removable. This should be provided in an Outline Decommissioning plan. |  | No change. |  | Progressed but not resolved. We note that the Applicant has removed the option of 'rock dump' from the list of cable protection types to be used within Fylde MCZ in their updated Outline CSIP [REP2-023]. However, we continue to advise that a commitment with the action to remove all on and above seabed infrastructure (including cable/scour protection) within benthic designated sites is secured in the DCO.
RI_C24 | C31 | Natural England notes that dredge disposal activities including sandwave clearance will be conducted throughout the Transmission Assets Order Limits. We highlight that no commitments have been proposed to mitigate impacts either within or outside of benthic designated sites, with the exception of CoT116 which states immediately adjacent to the impact occurring to enable recovery. Natural England advises that mitigation measures should be adopted by the Applicant and the relevant documents updated accordingly. More specifically, disposal options should be explored to ensure that sediment is deposited in areas of similar sediment character, adjacent and upstream of the levelling location, and using a fall pipe so that the risk of permanently altering the sediment character in any given location is minimised. |  | No change. |  | Progressed but not resolved. We welcome the Applicant's update in [REP2-023] however mitigation should go further as per our original comment.
RI_C25 | C33 | Natural England welcomes the commitment to micro-site the cables to further reduce the need for cable protection. However, this is not included within the commitments log or secured so it can’t currently be considered mitigation. Natural England advises that proposed mitigation measures are secured within a named plan or on the face of the DCO/dML. |  | No change. |  | No change.
RI_C26 | C34 | Natural England does not agree with the 35 year duration which has been stated as the duration for which subtidal habitat loss will occur. Natural England advises that in the current absence of commitments to remove cable/scour protection, then the loss should be assessed as permanent. Natural England advises that the EIA should be updated with more appropriate descriptions of the timescales associated with impacts and assessment adjusted accordingly. |  | No change. |  | No change.
RI_C27 | C35 | Natural England advises that the monitoring proposed within the Offshore In Principal Monitoring Plan (OIPMP) currently appears to focus on physical/sediment recovery and lacks sufficient ecological context. Natural England advises that the rationale within Table 1.3 of the OIPMP needs to be updated to additionally include “temporal and spatial changes in benthic communities and their recoverability….” in order for the OIPMP to meet its objective. |  | No change. |  | No change.
RI_C28 | C43 | From the information and figures presented ([APP-019] 1.8.2.31), it is not possible to determine whether the subtidal mud habitat type and NERC (2006) Priority habitat ‘Burrowing megafauna communities’ (as mapped in Figure 1.21 of the Benthic Technical report) overlap with the Fylde MCZ boundary. Site-specific benthic characterisation baseline should be presented together with the MCZ boundary in a single figure so that the habitats present can be checked against those assessed within the MCZ assessment report. |  | No change. |  | Progressed: We welcome the Applicants updated figure in [REP1-059] which overlays the site-specific benthic characterisation baseline and the MCZ boundary. Whilst we note the Applicant's response, we highlight that the figure indicates that potential sea pen and burrowing megafauna habitat overlaps with the cable corridor and Fylde MCZ. Therefore our position in this comment and point RI_18 remain unchanged. We further stress the need for adequate mitigation as stated in RI_C4.
RI_C29 | C47 | Please see comments C28 – C33 regarding mitigation which are equally applicable to this section and Fylde MCZ. |  | No change. |  | No change.
RI_C30 | C51 | Natural England advises that the adoption of mitigation measures via a Benthic Mitigation Plan, and associated monitoring in the Offshore In-Principle Monitoring Plan are further considered in order that impacts (particularly permanent loss), on the more sensitive Section 41 Habitats are avoided and/or reduced wherever feasible through mitigation measures such as micro-siting. |  | No change. |  | No change.

## D - Fish and Shellfish
Point | Point Number(s) from Appendix D [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix D - Fish and Shellfish Ecology | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_D1 | D1/D17 | Natural England do not agree that smelt should be screened out. There is potential for EMF to cause barrier effects that hinder smelt movements in and out of the estuary. Minimum and maximum target burial depths between 0.5 m and 3 m are detailed for the marine component. The Applicant should provide further detail on proposed cable depth below the riverbed and detail pertaining to EMF from the cable below the Ribble Estuary MCZ and this should be used to appropriately assess EMF impacts. |  | No change. |  | No change. EMF is a growing area of potential concern and lacking in evidence. Natural England continue to advise that the potential impacts should be assessed. Also see NE's response to ExA Q1 - Q7.2.3.
RI_D2 | D2/D7/D8/D11 | Natural England recommend that an assessment of the long-term loss of seabed habitat that potentially supports prey species for the ornithological features of Liverpool Bay SPA is included. This should be based on an assessment of the area of suitable spawning and other supporting habitat for prey species (sandeel) that could be lost due to the construction of the cable corridor. The MDS states that cable protection will be designed to be removable, however there is no commitment to remove upon decommissioning. Sandeel exhibit high site fidelity and leaving cable covering in situ during decommissioning phase would be considered permanent habitat loss. Natural England also advises that the Applicant commit to removing all cable protection within Fylde MCZ at the time of decommissioning or assess permanent habitat loss of supporting prey species for Liverpool Bay SPA. |  | No change. |  | In progress. Natural England notes the justification in the Applicants response to NE's Relevant Representations comment RR-1601.49 in relation to Offshore Ornithology and long-term loss of habitat supporting prey species for the features of Liverpool Bay SPA in PDA-014. We also note the response to 1601.46 in relation to Fish and Shellfish Ecology. To fully resolve this issue the quantification utilised in RR-1601.49 should also be applied in the context of suitable spawning areas for prey species across the cable corridor within the Liverpool Bay SPA which could be lost during construction. This information should be updated in the relevant parts of the application, in particular the ISAA.
RI_D3 | D3/D10 | There is potential for permanent habitat loss for sandeel and herring resulting from UXO and jack up barges altering sediment compositions. It is not clear whether this has been assessed. UXO clearance and jack up barges need assessing for effects from permanent habitat loss on sandeel and herring. |  | No change. |  | No change. Natural England welcomes the removal of high order UXO detonation, however maintain that UXO clearance and jack up barges need assessing for effects from permanent habitat loss. This is particularly important for areas of mixed sediment where the depressions tend to backfill with finer sediments.
RI_D4 | D5/D9 | Natural England defers to CEFAS on survey data acquisition, data sources, assessment methodology and its conclusions in relation to herring and sandeel. Natural England advises the Applicant refer to CEFAS comments as advisors to the MMO on this matter.
RI_D5 | D6 | It is unclear whether all relevant pathways have been assessed and/or quantified. Where relevant, the calculations for temporary and/ or permanent habitat loss impacts need to be considered with regards to suitable habitat for sandeel and herring. Natural England advise that full consideration of the likely nature, extent, duration, and significance of impacts upon SPA supporting habitats is required to inform a robust assessment of the likely impacts upon designated ornithological features and in turn prey species. |  | No change. |  | In progress. The comment in RI_D2 is also applicable here.
RI_D6 | D12 | Natural England largely agree with justification for in-combination assessment impacts for UXO and EMF but see comments D10 & D11 for further consideration. |  | No change. |  | No change.
RI_D7 | D18 | Natural England do not agree with the statement that smelt have been shown to habituate to anthropogenic noise sources. There is little evidence to support this. The Applicant should provide more robust evidence to support this conclusion or remove the statement.

## E - Marine Mammals
Point | Point Number(s) from Appendix E [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix E - Marine Mammals | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_E1 | E1/E17 | Natural England note that UXO clearance is included as a licenced activity in the DCO/marine licence (which includes high order clearance). This is a live issue for some projects in the consenting process (Mona OWF and Morgan OWF) and it is also applicable for the Transmission Assets. We strongly advise that a separate marine licence is sought for UXO clearance due to the lack of information available regarding the size, type and number etc of UXO that will require clearance and the over precaution that must be incorporated into the impact assessment at this stage. Without further information on what size of devices will proceed to clearance stage, the assessment (and associated mitigation protocols) must consider the worst-case scenario presented. Natural England advise that UXO clearance should be authorised under a standalone marine licence post consent and removed from the draft DCO. |  | In progress. The Applicant has proposed to remove high order unexploded ordinance (UXO) detonations and restrict the project to low order detonations. Natural England maintains its position that UXO detonation should be subject to a separate marine licence post consent, regardless of whether the removal is low or high order. Further, that the maximum number of detonations (low or high order), should be recorded on any consent granted. However, without prejudice to our position, we accept that low order removal is preferred. Whilst we welcome the inclusion of the maximum number of UXO's to be removed by low order, further information on how this number was derived should be provided. We advise that the Applicant should submit an updated version of their MMMP and Marine Mammal Chapter into Examination to reflect that high order has been removed from the DCO. We highlight that the Morgan Generation project made similar updates and submitted these into the Morgan Examination at Deadline 6 [REP6-032]. |  | Natural England welcomes the removal of high order UXO detonations from the DCO and the outline MMMP submitted at D2 [REP2-027]. However Natural England maintains its position that UXO detonation should be subject to a separate marine licence post consent, regardless of whether the removal is low or high order.
RI_E2 | E2/E18 | Natural England have outstanding concerns on the assessment methodology. We see the issues as follows: • Dual effect categories in the assessment matrix where in certain cases non-significant and significant effects can result from the same combination of magnitude and sensitivity. It is generally accepted that the assessment should follow the precautionary principle thus further justification is needed when lower effect categories are chosen. Or, ideally, dual categories in the matrix should be avoided. • Terminology used to base the conclusions of the assessment is not defined thus there is uncertainty as to what spatial or temporal scale terms such ‘short term’, ‘medium term’, long term’, “temporary”, “small scale”, “regional’, ‘highly localised’ mean. Natural England advises the assessment methodology be revised and the assessment updated accordingly. |  | No change. |  | No change.
RI_E3 | E3/E30 | The effective range of ADDs for harbour porpoises is 7.5 km approximately (JNCC 2022). The Applicant needs to outline how they plan to mitigate the rest of the estimated injury zone up to 15.37 km for high order UXO clearance activities. It is not clear what other measures the Applicant will commit to in order to mitigate for the full injury zone. The Applicant should provide further information on mitigation options for the entire harbour porpoise injury zone from high order UXO clearance for the alone and cumulative effect assessment (CEA). |  | In progress. We note the Applicant has removed high order UXO from the DCO [REP1-008]. We advise that the Applicant should submit an updated version of their MMMP and Marine Mammal Chapter into Examination to reflect that high order has been removed from the DCO. We highlight that the Morgan Generation project made similar updates and submitted these into the Morgan Examination at Deadline 6 [REP6-032]. Provided that these updated documents are submitted into examination, we believe this issue will be readily resolved. |  | In progress. Our comment at Deadline 2 also applies here.
RI_E4 | E4/E28/E34 | Natural England does not support use of scare charges for UXO clearance, and we advise that this measure is not considered in the final Marine Mammal Mitigation Protocol (MMMP). Remove the use of scare charges for UXO clearance from the final MMMP. |  | In progress. NE notes that high order detonations have now been removed from the DCO and they will require a separate marine licence. We also note that the MMMP mentions scare charges may only be needed for high order detonations. For clarity, the MMMP and Marine Mammal Chapter should be updated to remove this reference to scare charges. Once the relevant documents have been updated we believe that this is readily resolvable. |  | Natural England welcomes the removal of scare charges/soft start charges from the updated MMMP for UXO clearance [REP2-027]. We advise that the Applicant should submit an updated Marine Mammal Chapter into Examination to reflect that soft start charges have been removed. Provided that these updated documents are submitted into examination, we believe this issue will be readily resolved.
RI_E5 | E5/E24 | Standard industry measures (such as Marine Mammal Observers (MMOs), Passive Acoustic Monitoring (PAM) and Acoustic Deterrent Devices (ADDs)) are intended to minimise the risk of injury, thus they cannot be used as a justification to conclude that there will be no significant disturbance of the species. Mitigation measures aimed to reduce disturbance should be considered instead of relying on measures for reducing the risk of injury. This needs to be revised throughout the assessment. |  | In progress. Our response to RI_E3 above also applies here. |  | In progress. Our comment at Deadline 2 also applies here.
RI_E6 | E6/E25/E26/E30 | Natural England has outstanding concerns regarding the Cumulative Effects Assessment (CEA). Natural England does not agree with the significance of effect for PTS during UXO clearance in the cumulative effects assessment, particularly for harbour porpoise and does not agree with the justification for the conclusions made. Assess population-level consequences of disturbance during the cumulative effects assessment for all scenarios and produce an appropriate mitigation plan if significant effects are predicted. Given the cumulative number of vessels across all projects as well as large disturbance ranges, Natural England does not agree with the assigned magnitude score ‘low’ for disturbance from elevated underwater sound due to vessel use and other (non-piling) sound producing activities. The assessment provides very limited consideration of the potential significant increase of number of vessels and vessel movements for each project. Revise the CEA for disturbance from elevated underwater sound due to vessel use and other (non-piling) sound producing activities with an increased level of magnitude and commit to implementing the Vessel Traffic Management Plan. |  | In progress. Our response to RI_E3 above also applies here. |  | In progress. Our comment at Deadline 2 also applies here.
RI_E7 | E7 | The Maximum Design Scenario (MDS) for Unexploded Ordnance (UXO) clearance differs between the documents. Natural England advise that details relating to UXO clearance MDS should be updated for consistency across all chapters to ensure the Worst Case Scenario (WCS) is appropriately discussed and assessed.
RI_E8 | E8 | The MDS for Injury and disturbance to marine mammals from elevated underwater sound due to vessel use and other sound-producing activities in the Marine Mammals chapter [APP-050] differs from the MDS outlined in Chapter 7 Shipping and Navigation [APP-056]. Natural England advise that the MDS should be correctly reported and assessed in all relevant chapters and where chapters make reference to each other ensure all details, e.g. MDS, are consistent.
RI_E9 | E11/E12 | Table 4.7 [APP-050] includes all correct protected areas and features. However, the referenced figure 4.1 ‘SACs and MNRs, designated for the protection of marine mammals within the regional study area’ has not been included in Volume 2, Figures [APP-064]. The figure labelled 4.1 in [APP-064] is the marine mammal study area and relevant species MUs not the designated sites. Some figures in accompanying volumes do not have a reference number on the figure but are referenced in the ES. Ensure all figures are appropriately included, labelled, referenced and identifiable from the reference in ES.
RI_E10 | E13 | Natural England notes the inclusion of harbour seals in the assessment without a population estimate for the Isle of Man population. Natural England acknowledges the lack of data currently available in the literature to provide an estimate for the Isle of Man.
RI_E11 | E14 | Natural England advises that the reference population for grey seal should consider both the GSRP population estimate and the NW MU estimate. Natural England advise that both should be considered. Revise assessment so that it is undertaken against the NW MU grey seal population alone as the reference population, in addition to the assessment completed against the GSRP population.
RI_E12 | E15 | Natural England does not agree with the approach of using a 100km buffer region for grey seal in order to determine connectivity with the Transmission Assets based upon average foraging ranges for the species. maximum foraging distances from Carter et al., 2022 should be used to determine the connectivity from an identified haul out site and the project area. Natural England previously raised this issue during the PEIR stage and it has not been addressed. We do not now anticipate any material changes would be made to the baseline.
RI_E13 | E16 | Natural England acknowledges the inclusion in the ES of survey data and other data/ up to date references as requested, e.g. SCANS IV and two years of survey data at Morecambe Offshore Windfarm: Generation Assets and the inclusion of other key references Marine Mammal Welsh Atlas (2023), IAMMWG (2022) and SCOS 2022.
RI_E14 | E19 | The significance of auditory injury to harbour porpoise from UXO detonation should be amended to major, in line with the most significant option in the dual matrix category. Update the conclusions for auditory injury for harbour porpoise in the ES. |  | In progress. Our response to RI_E3 above also applies here. |  | In progress. Our comment at Deadline 2 also applies here.
RI_E15 | E20 | Inconsistency in the approach when assigning the sensitivity score for effects on marine mammals due to changes in prey availability. Minke whale has been assigned a sensitivity of medium, however harbour seal and harbour porpoise have both been assigned a sensitivity of low. Due to the vulnerability of harbour porpoise and harbour seal to changes in prey availability, their assigned sensitivity score should be medium in the assessment.
RI_E16 | E21 | Natural England disagrees that a period of several months can be considered “short term”. However, in paragraph 4.11.6.30 the same description of works is described as ‘medium term’. Define the terms to describe both temporal and spatial impacts and apply them consistently across the assessment.
RI_E17 | E22/E27 | Natural England notes that the predicted disturbance ranges for sub-bottom profilers (SBPs) and vibro-coring are 17.3km and 10.6km respectively. However, no mitigation measures have been discussed for these large disturbance ranges. Natural England acknowledges that there are currently no other mitigation options available for SBP surveys beside those outlines in the JNCC guidelines for minimising the risk of injury to marine mammals from geophysical surveys (JNCC, 2017). Thus, there is a need for monitoring to fill the knowledge gap on the impact of SBP surveys on harbour porpoises. We therefore advise that monitoring should be considered with the aim to collect data before, during and after SBP surveys to examine changes in the baseline. Inclusion of this monitoring in the IPMP would resolve this issue.
RI_E18 | E23 | The maximum disturbance ranges predicted for SBP is up to 17.3 km and is described as ‘mild disturbance’, however in 4.11.6.29 it states that for ‘impulsive sound sources there is an understanding of the difference between strong and mild disturbance, whereas for non-impulsive (continuous) sound sources (MBES, SSS, SBES, SBP (chirp/pinger) and vibro-coring), there is only a single available threshold (120 dB re 1 μPa (SPLrms)), which is classed as the distance beyond which no animals would be disturbed.’ This statement contradicts the conclusion of mild disturbance from SBP sound source. Define the terms correctly for impulsive and non-impulsive sound sources and apply them consistently across the assessment.
RI_E19 | E26 | Given the cumulative number of vessels across all projects as well as large disturbance ranges, Natural England does not agree with the assigned magnitude score of ‘low’ for disturbance from elevated underwater sound due to vessel use and other (non-piling) sound producing activities. Revise the CEA for disturbance from elevated underwater sound due to vessel use and other (non-piling) sound producing activities. Ensure the Applicant commits to implementing their Vessel Traffic Management Plan.
RI_E20 | E29 | Natural England acknowledge the MMOs advice to the Applicant to commit to using Noise Abatement Systems (NAS) as mitigation during construction. Natural England notes CoT64 where the Applicants has committed to developing and implementing a detailed MMMP which will include the use of low order techniques as the primary mitigation where possible. The detailed MMMP should consider guidelines for minimising the risk of injury to marine mammals from UXO (JNCC, 2025). Natural England advises the Applicant should continue to prioritise other measures, such as avoidance, relocation and low-order clearance methods such as deflagration over high order clearance and to consider and apply new guidelines for minimising the risk of injury to marine mammals from UXO. These other measures should all be included in the final MMMP.
RI_E21 | E31 | Natural England defers to CEFAS as the underwater sound specialists to comment on the Underwater Sound Technical Report.
RI_E22 | E33 | Please note that it is Natural England’s remit to provide advice on the assessment in so much as it relates to SACs in English waters. We defer to the relevant SNCBs on the appropriate approach for assessing SACs outside English waters.
RI_E23 | E35 | Natural England notes that the Applicant is more likely to carry out sequential UXO clearance, however the assessment states that ‘A spatial MDS would occur where UXO clearance activities coincide at all three projects simultaneously’. There remains potential for UXO clearance activities to coincide at all 3 projects simultaneously, therefore there could be a significant impact on marine mammals that could manifest to population level effects based on the PTS figures for high order UXO clearance. Natural England advise the Applicant to produce an appropriate mitigation plan should this scenario occur. |  | In progress. Our response to RI_E3 above also applies here. |  | In progress. Our comment at Deadline 2 also applies here.
RI_E24 | E36 | We note that the mitigation measures to minimise disturbance to marine mammals included within the Offshore EMP are only relevant to the transiting vessels. Consider appropriate measure for all other (non-piling) sound producing activities, not just transiting vessels.

## F - Offshore Ornithology
Point | Point Number(s) from Appendix F [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix F - Offshore Ornithology | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_F1 | F1/F12 | The Applicant should complete a quantified cumulative assessment of impacts on species sensitive to disturbance and displacement, including mortality figures for each project included in the assessment, and provide clarity on the parameters used to produce those figures. The result should comprise a total abundance of birds that could be affected and a range of final mortality estimates based on a range of possible displacement and mortality rates, as per Natural England best practice guidance. |  | No change. |  | In progress. The Applicant has now committed to a full seasonal restriction on all construction activity and UXO clearance from November to March (inclusive) within the original Liverpool Bay SPA plus a 2km buffer. This adddresses NE's concerns and AEoI can now be ruled out for the red-throated diver and common scoter features of the SPA. We do not anticipate significant numbers of these species outside the original SPA boundary. This comment relates to EIA scale assessments, therefore once suitable wording is included in the ES chapter this matter can be resolved.
RI_F2 | F2/F16 | Natural England recommend that an assessment of the long-term loss of seabed habitat that potentially supports prey species for the ornithological features of Liverpool Bay SPA is included in the Information to Support Appropriate Assessment. This should be based on an assessment of the area of suitable spawning and other supporting habitat for prey species that could be lost due to the construction of the cable corridor, with consideration of i) diver and in particular scoter densities along those parts of the cable route where rock protection might be needed and ii) the presence of key species/habitats that fall within that area. |  | No change. |  | In progress. Natural England are satisfied with the justification in the Applicant’s response to NE’s Relevant Representations [PDA-014], they explained that the total area of potential habitat loss is considered small enough to rule out this impact pathway. Natural England are satisfied that the additional information on the predicted habitat loss in PDA-014 would allow adverse effects on the Liverpool Bay SPA to be ruled out. To fully resolve the issue, we recommend that this information is used to update the relevant parts of the application, in particular the Information to Support an Appropriate Assessment.
RI_F3 | F3/F4/F18/F19 | Natural England do not agree with the conclusion that adverse effect on site integrity (AEoI) for the red-throated diver and common scoter features of Liverpool Bay SPA can be ruled out due to the displacement and disturbance impacts of the Project alone during the construction phase. Natural England highlights that the conservation advice for these features include targets to maintain the distribution of the feature and the extent, distribution and availability of supporting habitat, preventing deterioration from current levels, not just population abundance. The Project’s potential to cause AEoI can be avoided by the Applicant committing to a full restriction on all offshore construction and pre-construction (UXO clearance) activity with the potential to cause disturbance within the SPA and a 2km buffer around it during the wintering months of November to March (inclusive). |  | No change. |  | Resolved. The Applicant has now committed to a restriction on all construction activity and UXO clearance from November to March (inclusive) within the original Liverpool Bay SPA boundary plus a 2km buffer [REP2-025]. This addresses Natural England's concerns and AEoI can now be ruled out for the red-throated diver and common scoter features of the SPA.
RI_F4 | F5/F20 | Natural England are unable to reach a conclusion regarding the Project’s impacts during the operations and maintenance (O&M) phase, either alone or in-combination, as the maximum design scenario (MDS) is set out on an annual basis. Alongside the annual MDS, the Applicant should set out the MDS for the key wintering months of November to March (inclusive), particularly for any activities which have the potential to cause disturbance to sensitive ornithological features within Liverpool Bay SPA and consider the need for a seasonal restriction for O&M activities. |  | No change. |  | No change. The Applicant have not provided clarity on how many days of vessel movement would be expected in the winter during O&M activities. We advise the Applicant consider a commitment to not carry out any routine maintenance in the winter unless in urgent circumstances (we are aware this is already an unlikely scenario as weather conditions are usually prohibitive).
RI_F5 | F9 | Natural England note that the Applicant has calculated a bespoke regional population for red-throated diver based on the fact that the BDMPS population from Furness (2015), which is generally used as the standard reference for EIA population scales, is smaller than the most recent population estimate for Liverpool Bay alone (HiDef, 2023). The Applicant should calculate a regional population based only on populations that sit within the original BDMPS region and use this for assessing red-throated diver impacts.
RI_F6 | F13 | We note that the wintering period has been identified as covering November-February inclusive. Natural England considers the key sensitive period for red-throated diver to extend until the end of March. Seasonal restrictions on construction activity to avoid impacts on wintering birds should cover the period from the start of November to the end of March. |  | No change. |  | Our response to RI_F3 is also applicable here.
RI_F7 | F14 | The Applicant should present a range of cumulative quantitative displacement impacts from other projects on red-throated diver and common scoter at an EIA scale in the Irish sea, both those exerting ongoing pressures during their operations and maintenance phase and those whose construction impacts will overlap with the Project, plus the predicted impacts from the Project in its construction stage. |  | No change. |  | No change.
RI_F8 | F15 | Due to the sensitivity of key ornithological features of Liverpool Bay SPA during the wintering months of November to March (inclusive). Therefore the Applicant should include descriptions of the maximum design scenario for activities causing airborne sound, underwater sound or presence/movement of vessels and infrastructure within the wintering period for each phase of the Project, in addition to the annual descriptions.
RI_F9 | F17 | To fully consider the in-combination impacts on the distribution and the extent, distribution and availability of supporting habitat for the red-throated diver and common scoter features of Liverpool Bay SPA, the Applicant should present an assessment of the area and the proportion of the SPA that is subject to displacement and disturbance impacts due to the Project in-combination with other projects and include West of Duddon Sands OWF as its 10km buffer overlaps with the SPA. |  | No change. |  | Resolved. The Applicant has now committed to a restriction on all construction activity and UXO clearance from November to March (inclusive) within the original Liverpool Bay SPA boundary plus a 2km buffer [REP2-025]. This addresses Natural England's concerns and AEoI can now be ruled out for the red-throated diver and common scoter features of the SPA.
RI_F10 | F21 | Natural England notes the Hynet North West Carbon Capture and Storage (CCS) project has been screened out of the offshore ornithology assessment due to low data confidence. There is a high risk of spatial and temporal overlap of the construction of Hynet North West CCS and the Transmission Assets, therefore Natural England advise this project should be screened into the CEA for offshore ornithology and assessed as part of the Tier 2 projects. Further information should be sought from the Hynet project, specifically information on mitigation measures during construction. |  | No change. |  | Resolved. Natural England notes the inclusion of Hynet in [REP2-043]. In addition, the Applicant has now committed to a restriction on all construction activity and UXO clearance from November to March (inclusive) within the original Liverpool Bay SPA boundary plus a 2km buffer [REP2-025]. This addresses Natural England's concerns regarding the CEA.

## G - Onshore Ecology
Point | Point Number(s) from Appendix G [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix G - Onshore Ecology | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_G1 | G1/G20/G25/G37 | Natural England is unable to rule out significant impacts on sand dune SSSI features associated with Lytham St. Annes Dunes due to uncertainties around changes to the water table (both during construction and operation). We are also concerned about dewatering effects associated with pumping out water from the Transition Joint Bay (TJB) during construction, and the cable acting as a conduit altering water flow through the system. Similar concerns are also flagged for sand dune habitat (S41 priority habitat under the NERC Act 2006) at St. Annes Old Links Golf Course Biological Heritage Site (BHS) and Lytham Foreshore Dunes and Saltmarsh BHS. a) We advise that Impacts on dune slack vegetation (which is referable to the Annex I habitat H1290) needs to be more thoroughly assessed. b) Natural England advises the Applicant to consider the installation of dipwells (automatic dataloggers) to monitor the position of the water table pre- and post-construction and this commitment should be included as a part of the ongoing Monitoring Plan c) In addition, we advise that modelling is necessary to determine the position of the water table and potential fluctuations that may arise as part of the proposals over the lifetime of the project. |  | No change. |  | No change. Our response is provided in Appendix G3 section 1.1.
RI_G2 | G2/G17 | Natural England advises that the limited project specific data collected makes it difficult to assess any potential changes in habitat/ species composition associated, for example, with a modified water table brought about by the dewatering and pumping of water during construction from the TJB. Natural England advises that surveys of St. Annes Old Links Golf Course BHS should be undertaken in June 2025 to fill in the evidence gaps to better assess potential changes to habitats and species from the potential dewatering of the site. Use of fine scale Lidar may help identify low lying areas which may be relict dune slacks. |  | No change. |  | No change. Our response to R1_G1 is also applicable here.
RI_G3 | G3/G11 | Further details (map and GPS locations) as to a) the location of the Transmission Joint Bays (TJBs) in Blackpool Airport, b) exit pits on the foreshore, c) the location of Compound 2 and d) the cable alignment under the sand dunes and cable depth is needed to help rule out impacts on sand dune SSSI features associated with Lytham St. Annes Dunes. |  | No change. |  | No change. The additional information provided by the Applicant in "Annex 5.3 to the Applicants response to Hearing Action Points: ISH1 13, 14, 16, 17" [REP1-040] provides some further clarity (including additional maps) on the location of the Transmission Joint bays, exit pits on the beach and Construction Compound 2. However, the Annex notes that the final positioning will not be agreed until the detailed design post consent (para. 2.2.1.5). It is also noted that the final route around the care home i.e. whether the cables cross the dunes to the north, south or are spilt around the care home will also not be agreed until the detail design post consent. Until the final design (post consent), the exact location of the exit pits and cable route under the dunes will not be agreed and this information is required to help rule out impacts on SSSI features.
RI_G4 | G4/G12/G16/G38 | Natural England advises that further details on the Direct Pipe Trenchless Technique and evidence to support its feasibility is required to be able to fully assess the potential impacts to Lytham St. Annes Dunes SSSI. An outline contingency plan should be developed and the Worst Case Scenario (WCS) should be at least assessed in the assessment, i.e. cable installation failure when using Direct Pipe Trenchless Technique. |  | No change. |  | No change.
RI_G5 | G5/G33 | The condition of Lytham St. Annes Dunes SSSI is currently assessed as Unfavourable Recovering (based on a 2014 Natural England assessment). To achieve Favourable condition of the dunes ongoing management of the Fylde Dunes (including Lytham St. Annes Dunes SSSI and Lytham Foreshore Dunes and Saltmarsh BHS as outlined in Skelcher (2024) has been agreed. Natural England advises that the Applicant should consider in the Outline Ecological Management Plan how the required management actions outlined in Skelcher will continue to take place during the duration of the project. |  | No change. |  | No change. As a route for solution to this issue Natural England advise the Applicant to include a commitment to ensure ongoing habitat management works within Lytham St. Annes Dune SSSI and Lytham Foreshore Dunes & saltmarsh will be able to continue unhindered during cable installation so to help achieve Favourable condition of these priority habitats. The required management actions are referenced in Skelcher (2024). NE expect the existing management works can continue as planned as the Applicant is suggesting there will be no above ground works within the sand dunes of Lytham St. Annes Dune SSSI or Lytham Foreshore Dunes & saltmarsh. In addition the new CoT110 and CoT129 restricting works on Lytham St Annes beach (between November and March (inclusive)) will mean most habitat management will not coincide with cable installation.
RI_G6 | G6/G48 | From the information provided Natural England does not consider there to be reasonable justification for the lack of Agricultural Land Classification (ALC) survey effort to date. Natural England advises (a) the Applicant needs to undertake a detailed ALC and soil survey of the agricultural land across the full Study Area to inform the application. And (b) the commitment to restore land needs to be secured in the DCO to not only reinstate the land but to ensure the site will be restored at a minimum to the same ALC grade as before construction, to ensure that land quality will not be negatively affected. |  | No change: We note the response provided by the Applicant in [REP1-043]. However, Natural England's advice remains that in order to inform the impacts of the development on Best and Most Versatile Soils that are to be temporarily disturbed/ lost, ALC and soil surveys are required from the whole study area. This is also required to inform any specific mitigation required. Natural England believes this issue can be resolved and welcomes engagement with the Applicant to agree suitable survey methodology. |  | No change. Our response is provided in Appendix G3 section 1.2.
RI_G7 | G7/G51 | Natural England utilises the England Peat Status Greenhouse Gas and Carbon Storage which identifies that part of the cable route is situated on deep peat. At this stage there is not enough information for Natural England to advise if the proposal will have direct or indirect impacts on deep peat. Natural England do not support the principle of developing on restorable peat. Natural England advises that further evidence and survey data is required. Peat surveys should be carried out in line with the IUCN peatland programme field protocol. A Peat Management Plan will be required for any buried deep peat around the cabling route, even if it is remaining in situ. |  | No change. |  | No change. Our response is provided in Appendix G3 section 1.3.
RI_G8 | G8 | Natural England advises as per our advice on other joint DCO applications such as the East Anglia offshore windfarms and most recently for Dudgeon and Sheringham Extension Projects that a commitment is made, that whichever project is constructed first installs the onshore cable ducts for both projects to minimise the environmental impacts and the working corridors if construction overlaps. We advise full consideration of all mitigation measures are considered as part of the consenting process. |  | No change. |  | No change.
RI_G9 | G9 | To better understand the potential impacts at dune structure and function, Natural England queries the minimum required distance between the 6 proposed cables in order to minimise the effect of heat transfer. Where the cable crosses under Lytham St. Annes Dunes SSSI and St. Annes Old Links Golf Course BHS the Order Limit has been minimised (which is welcomed), but using the current MDS this would mean the route is constrained at its narrowest point to 260m to the north and 220m to the south. Depending on the required distance between the cables this could result in the cables underlying a significant proportion of the SSSI dunes and relict dunes. Natural England advises that clarity is needed regarding the minimum distance between cables. This ideally would be illustrated showing the cable alignment within the Order Limits and the distance between the cables given in metres. |  | No change. |  | No change. The additional information provided in "Annex 5.3 to the Applicants response to Hearing Action Points: ISH1 13, 14, 16, 17" [REP1-040] does not provide further clarity - e.g. para 2.2.1.5 notes that the final positioning of the exit pits and the final routing around the care home i.e. whether the cables cross the dunes to the north, south or are spilt around the care home will not be agreed until the detail design post consent. Therefore it is currently unclear how close the cables are to each other. Para 3.15.2.8 of the [REP2-009] Project Description notes "Once installed, the electrical cables must be suitably spaced out in order to minimise the mutual heating effect of one cable circuit on another, and to allow for heat dissipation".
RI_G10 | G10 | Natural England advises that the Applicant clarify what temperatures may extend to the surface and across the dune structure when the cable is operational and assess and provide evidence on any possible impact on sand dune vegetation in terms of affecting water availability and mimicking drought (especially with increased issues of summer drought associated with climate change). |  | No change. |  | No change. This follows on from point RI_G9 above. Table 3.19 of the Project Description [REP2-009] provides a typical HDD cable burial depth of 15m. In order to progress this issue we require the Applicant to give an indication of likely heat transfer from the cable to the dunes and how this might impact sand dune vegetation (affecting water availability and mimicking drought).
RI_G11 | G13 | Natural England advises that the ES should present the detailed and semi-detailed Agricultural Land Classification (ALC) survey information. This should include a breakdown of the ALC grades (area, %) in relation to the application site boundary and include ALC and soil data for the cable route and areas of permanent infrastructure and habitat enhancement. A breakdown of the proposed site into disturbed and undisturbed land categories should also be included, split by ALC grade, to help illustrate the potential for impact on agricultural land grade. |  | No change: we note the response provided by the Applicant in [REP1-043]. However, Natural England's advice remains that in order to inform the impacts of the development on Best and Most Versatile Soils that are to be temporarily disturbed/ lost, ALC and soil surveys are required from the whole study area. This is also required to inform any specific mitigation required. Natural England believes this issue can be resolved and welcomes engagement with the Applicant to agree suitable survey methodology. |  | No change. Our response is provided in Appendix G3 section 1.4.
RI_G12 | G14 | Natural England notes the reference to topsoil removal, back filling of topsoil level and replacement of topsoil, but no proposed timeline of activities included. As part of an Outline Soil management Plan [APP-200] Natural England advises that further information on the timeline of proposed soil handling is provided and mitigation measures to minimise the impacts secured. |  | No change. |  | No change. Our response is provided in Appendix G3 section 1.5.
RI_G13 | G15 | Natural England notes that following installation of ducts and backfilling of trenches the cables will be pulled through the ducts from joint bays. Natural England advises that the depth of the cabling laying be secured in a named plan and on the face of the DCO/dML. This depth is expected to be consistent with the industry standard of 0.9m depth. |  | No change. |  | No change.
RI_G14 | G19 | Further information on the timings of survey observations, quadrat locations and how wetness of dune slacks was calculated should be provided to better understand the robustness of the survey data. This should include date of NVC surveys (2016 or 2024), map showing quadrant locations and a quadrant data table |  | No change. |  | In progress. [REP2-014] Volume 3, Annex 3.3: Phase 1 habitat, national vegetation classification and hedgerow survey technical report has been updated to provide a map showing locations of each of the NVC survey sites based on the X, Y coordinates (Figure 1.1). In addition, Figure 1.3 shows the quadrat locations extracted from the Skelcher (2016) report. In order to resolve this issue it would be appropriate to reference the Skelcher (2016) report on Figure 1.3 to avoid confusion of when and by whom the quadrats where undertaken. Similarly, in Appendix B of [REP2-014] - the survey dates of both the woodland quadrats and in Appendix C sand dune quadrats should be given. It is presumed that the quadrat data in Appendix C is also taken from Skelcher 2016, however this is also unclear and is not specified.
RI_G15 | G21 | Natural England notes that the maximum design parameter represented in Table 3.23 for the construction cable corridor (temporary) does not align with calculations made elsewhere within the chapter. Natural England advises that the MDS should be consistent across ES chapters and named plans. |  | No change. |  | Resolved. The justification and information provided in [PDA-021] satisfies Natural England's concerns. We acknowledge that the information in Table 3.23 [AS-024] relates specifically to the cable corridor within Blackpool Airport which is not applicable across the whole scheme.
RI_G16 | G22 | Natural England notes that the document states that proposed biodiversity benefit and ecological mitigation areas have not been subjected to surveys. Natural England advises that soil testing for basic soil properties (pH, SOM and macro-nutrients) should be completed at the same time as the ALC and soil survey.
RI_G17 | G23 | Natural England notes that it is stated that the location of representative auger boring surveys were chosen to reflect the main soil types identified within the Onshore Order Limits, according to the desktop information. Natural England advises that this is insufficient. Natural England advises that the ES should present the detailed and semi-detailed Agricultural Land Classification (ALC) survey information across the full Study Area. This should include a breakdown of the ALC grades (area, %) in relation to the application site boundary and include ALC and soil data for the cable route and areas of permanent infrastructure and habitat enhancement. |  | No change. |  | No change. The response to RI_G6 is also applicable here.
RI_G18 | G24 | It is unclear whether the archaeological trenches would meet the requirements to obtain relevant data (soil properties) to determine ALC grade. Natural England advises that further survey data should be provided to support the ES soils assessment and further monitoring requirements prior to construction agreed. |  | No change: we note the response provided by the Applicant in [REP1-043]. However, Natural England's advice remains that in order to inform the impacts of the development on Best and Most Versatile Soils that are to be temporarily disturbed/ lost, ALC and soil surveys are required from the whole study area. This is also required to inform any specific mitigation required. Natural England believes this issue can be resolved and welcomes engagement with the Applicant to agree suitable survey methodology. |  | No change. The response to RI_G6 is also applicable here.
RI_G19 | G26 | Natural England advises that the commitment needs to be secured in the DCO to not only reinstate the land but to ensure the site will be restored at a minimum to the same ALC grade as before construction, to ensure that land quality will not be negatively affected. The commitment to implementing additional measures to further benefit the land quality/productivity should also be included. We also advise that the Outline Soils Management Plan should include restoration criteria to ensure the land is aligned to the ALC survey results. |  | No change: we note the response provided by the Applicant in [REP1-043]. However, Natural England's advice remains that in order to inform the impacts of the development on Best and Most Versatile Soils that are to be temporarily disturbed/ lost, ALC and soil surveys are required from the whole study area. This is also required to inform any specific mitigation required. Natural England believes this issue can be resolved and welcomes engagement with the Applicant to agree suitable survey methodology. |  | No change.
RI_G20 | G27 | Natural England advises that air quality impacts on ecological features including international and nationally designated sites and their qualifying features should be considered in the chapter. |  | No change. |  | No change. Natural England notes that the information provided includes Red Scar and Tun Brook Woods SSSI, however information for other sites has not been provided including Ribble & Alt Estuaries SPA/Ramsar and Ribble Estuary SSSI, Lytham St Annes Dunes SSSI and Newton Marsh SSSI. In addition, effects due to changes in air quality (including dust) and deposition of pollutants associated with increases in vehicle movements for construction are identified as an impact pathway that’s scoped in for further assessment in [APP-075] Table 3.18 (page 124). This is in contradiction to [APP-121] which identifies Ribble and Alt Estuaries SPA and Ramsar, Ribble Estuary SSSI, Newton Marsh SSSI and Lytham St Annes Dines SSSI as sites sensitive to Air Quality impacts (dust).
RI_G21 | G28 | Natural England advises that further information is needed regarding the proposed mitigations measures to minimise/mitigate impacts on sand lizards e.g. measures to minimise vibration which could cause sand lizard burrows to collapse. The proposed mitigation (3.11.13.19) has not been previously discussed and agreed and the positioning of the cut-off trenches needs to be considered in terms of potential dewatering effect/damage to the foredunes. |  | No change. |  | No change. The response RI_G40 is also applicable here.
RI_G22 | G30 | Natural England advise that a UXO contingency plan should be provided – should UXO be found within Lytham St. Annes Dunes SSSI. |  | No change. |  | No change. Natural England acknowledges that [APP-068] makes reference to a UXO desk study report and that this includes a risk mitigation strategy as stated in [PDA-021]. Once the UXO desk study report is submitted into Examination this issue will be resolved.
RI_G23 | G31 | The Applicant has outlined the onshore survey area as a 150m buffer around the Onshore Order Limits. Natural England typically advise that a buffer of 200m should be used. Provide justification for why a 150m buffer was chosen and how this can be shown to be a sufficient distance to account for all disturbance incidents to Important Ecological Features (IEFs). |  | No change. |  | Natural England is satisfied with the Applicant's clarification on the survey limits in [PDA-021], this issue is now resolved.
RI_G24 | G32 | Natural England notes that for Sand Lizard – timing of works (piling / installation of cofferdams at TJB etc) could be used to minimise risk that vibration cause burrows to collapse when being used by hibernating or breeding Sand Lizard. Natural England advises that further consideration is given to timing restrictions for works near to known Sand Lizard populations. |  | No change. |  | No change. The response for RI_G40 is also applicable here.
RI_G25 | G34 | Natural England advises that monitoring plans are updated to include pre and post construction monitoring of humid dune slacks. This will help to determine the success of the mitigation measures and confirm the assessment. |  | No change. |  | No change. We refer the ExA to Appendix G3 of our Deadline 3 response.
RI_G26 | G35 | Natural England should be informed of any bentonite breakouts that occur on any SPA, Ramsar or SSSI sites or within any sand dune or foreshore habitats. Ground investigation works should be taken to inform consenting and to ensure the technical feasibility of any proposed mitigation associated with landfall installation methodology. Natural England advises that geotechnical data should be used to ensure that mitigation measures are fit for purpose and are relevant to the proposed installation methodology. |  | No change. |  | No Change. We advise that an outline HDD/trenchless crossing management plan similar to that submitted into examination for North Falls is submitted into examination which encapsulates the bentonite breakout plan.
RI_G27 | G36 | Fairhaven Saltmarsh is identified in the Outline Ecological Management Plan (J6) as a permanent mitigation area. Natural England advises that more details regarding the proposed permanent mitigation area at Fairhaven Saltmarsh – for example the fencing specification and installation measures are required The Applicant should also refer to Skelcher (2024) botanical report which covers this area (survey from 2010 & 2016)– showing the saltmarsh and sand dune communities that are present. |  | No change. |  | In progress. The Applicant has now committed to a restriction on all construction activity from November to March (inclusive) at landfall. This addresses Natural England's concerns and AEoI can now be ruled out for the over-wintering features of the SPA. We still have concerns regarding the assessment and proposed mitigation. The additional information included in [REP2-045] and [REP2-018] is still lacking in detail in regards to mitigating impacts to passage features of the SPA.
RI_G28 | G39 | Natural England disagree with the conclusion of effect of changes in hydrogeology on the SSSI and LNR will be minor adverse - not significant. Natural England advises that further survey evidence should be provided to support the Application conclusions. |  | No change. |  | No change. Our response to R1_G1 is also applicable here.
RI_G29 | G40/G18 | Natural England has focused on coastal habitats and no SAC sites were identified within the Order of Limits. Natural England have not reviewed the HRA reports – but note sand dune habitats which could be classified as an Annex I habitat type have been covered in [APP-018]. Natural England advises that impacts to Ramsar habitats will be required. |  | No change. |  | Resolved. Natural England is satisfied with the Applicant's clarification in [PDA-021] and we acknowledge the detail included in [APP-075] section 3.11.3.3 and consider this sufficient. For completeness we suggest the Applicant update the ES chapter (Table 3.7) to acknowledge that sand dunes are described as part of the Ribble and Alt Estuaries Ramsar description Site Information Service page notes.
RI_G30 | G41 | [APP-018] Table 1.24 does not consider all potential impact pathways or relevant European sites, specifically air quality impacts have not been considered. [APP-121] states the Ribble Estuary SPA/Ramsar includes features sensitive to dust within 20m of the Onshore Order Limits, therefore these features need to be considered in the HRA. Natural England advises that air quality impacts on internationally designated sites should be considered. |  | No change. |  | No change. According to [APP-018] any supporting habitat is considered under Annex I habitats - offshore and coastal (section 1.4.2.2), however this part of the assessment does not consider air quality impacts. Any dust or traffic emissions from the proposal could impact these functional habitats and is therefore a potential pathway and needs to be considered within the HRA. In addition [APP-121] identified these sites as having air quality sensitive features.
RI_G31 | G42 | Table 3.17 includes a list of all Important Ecological Features (IEFs) taken forward into assessment. Natural England advise the chapter to be updated to include information demonstrating why other IEFs have been scoped out for further assessment. |  | No change. |  | No change. Red Scar and Tun Brook Woods SSSI is not included within Table 3.17 [APP-075], but Table 3.8 lists it as a nationally designated site within the onshore ecology study area, which will be considered. Natural England acknowledges that SSSI's are considered later in the chapter (page 161), but for clarity this should be included in Table 3.17 as it is a site of national importance that does require further assessment. Newton Marsh SSSI - Table 3.8 [APP-075] states that impacts on Newton Marsh SSSI are considered in [APP-090] Chapter 4: Onshore and Intertidal Ornithology as the notified features of the SSSI (aggregations of golden plover and black-tailed godwit) are not relevant to Onshore Ecology and Nature Conservation. However effects due to changes in air quality are not considered in [APP-090]. As identified in [APP-121] Chapter 9: Air Quality, Newton Marsh SSSI has features which are sensitive to air quality impacts.
RI_G32 | G43 | Table 3.40 and section 3.11.6.2 give the breakdown of coastal saltmarsh loss temp (0.03ha) and permanent (0ha). Natural England advises the Applicant provide further information on where the 0.03ha of saltmarsh loss will occur. |  | No change. |  | No change. Natural England acknowledge the response in [PDA-021] however it is still unclear if there is actual loss of saltmarsh in this area. If the area has been surveyed and found to be species poor grassland, we question why this loss of saltmarsh is being included and not reported as temporary loss of species poor grassland. A map or a link to an existing map showing the area where the saltmarsh has been highlighted would be useful to further understand this point.
RI_G33 | G44 | Although the Applicant has suggested that they will be using Natural England’s District Level Licensing (DLL) Scheme, Natural England has not (as yet) approved the use of the DLL scheme for this project. Natural England has agreed in principle to the project using District level Licensing, however this is dependent on the availability of compensation ponds at the time of enquiry. Until an Impact Assessment and Conservation payment Certificate (IACPC) has been signed by the applicant and counter-signed by Natural England they cannot rely on District Level Licensing as a Licensing approach for this project.
RI_G34 | G45 | Natural England notes that in Table 3.15 the summary of key findings for species includes a potential outlying badger sett recorded within the Onshore Order Limits that appears disused. However, badgers are not considered further within Chapter 3, and no evidence is presented to confirm the outlying badger sett is not used. Badgers are a Protected Species under the 1992 Protection of Badgers Act, and it is the responsibility of the applicant to ensure they have sufficient evidence to demonstrate the proposal will not impact on protected species. Therefore, Natural England is unable to provide a Letter of No Impediment for Badger at this time. |  | No change. |  | Natural England notes the Applicant's commitment to undertake pre-commencement surveys to identify if works will be within 30m of a badger sett. We deem this approach acceptable but wish to highlight that a licence will be required should surveys identify an active badger sett. We note these measures are secured within the OEMP [REP2-019], which we support.
RI_G35 | G46 | Natural England notes the development is not subject to a mandatory net gain requirement and note the Applicant has outlined how they will deliver biodiversity benefit for areas of permanent habitat loss from permanent above-ground infrastructure using Defra BNG methodology and metric version 4.1 for the calculations. We also note that Lea Marsh BHS will be subject to habitat creation and enhancement measures. Unless there are changes in the design parameters we have no further comment to make during this examination.
RI_G36 | G49 | Natural England advise that topsoil bunds should not exceed 3m in height. Natural England advises that Application documents are updated to reflect best practice. |  | No change. |  | Increasing topsoil storage mounds to 4 metres in height is generally not considered best practice, as it can compromise the physical and biological integrity of the soil, therefore our original comment is still applicable. However we note that the DEFRA code of practise for the sustainable use of soils on construction sites states 3-4m for topsoil bunds, therefore Natural England will not engage further on this issue.
RI_G37 | G50 | Natural England disagrees that the depth of subsoiling operations will depend on the nature of the soil type affected and extent of any compaction that may have occurred. The depth of decompaction should reflect the depth of compaction. Natural England advises that the Applicant reconsider the information around soil compaction and consider producing an outline decompaction strategy to maximise the effectiveness of decompaction methods. |  | No change. |  | Natural England is satisfied with the additional clarification providied by the Applicant in [PDA-021] with reference to [APP-200] on their approach to soil compaction.
Appendix G1 Additional Comments - Onshore Ecology and Nature Conservation
RI_G38 | G52 | a) Natural England would welcome further discussion with the Applicant to determine the scale of impacts on the noctule hibernation bat roost and the judgement which their Ecologist has made regarding the possible abandonment of the noctule roost. b) If a licence is required, Natural England advise that quantitative data would be required on the roost, level of activity and use of the surrounding area. |  | No change. |  | No change.
RI_G39 | G53 | Natural England advises that commitments should be made to ensure that updated badger surveys will be undertaken before works commence to confirm that no new setts have been created, and that the outlier sett remains disused. |  | No change. |  | Resolved - see comment RI_34.
RI_G40 | G54 | Sand lizard: Given the detail contained within Section 3.11.13, the described works would likely require an A46 derogation licence to cover disturbance, damage and possibly destruction of habitat due to the exit pits for the routing of the cable within and beneath known sand lizard habitat. Natural England advise that further detail including population size estimates, mitigation and compensation should follow in a draft licence submission. |  | No change. |  | No change. Natural England acknowledges the Applicant's response in PDA-022, however our original comment is still applicable. Please also see Natural England's response to ExA Q1 - Q6.1.5 - Q6.1.7.
RI_G41 | G55 | Natural England advises that further information is required on the status of water vole burrows and the works to be undertaken in the water courses with water vole burrows present. |  | No change. |  | Resolved. Natural England acknowledges that additional surveys have been conducted and these results that have not altered the baseline survey data. In the first instance NE agrees with impacts being avoided wherever possible by trenchless techniques or other means. NE advises that impacts from trenchless crossing techniques such as frac outs (if using HDD for example) are also considered and where necessary works timed to avoid the water vole breeding season in the event of any unintentional flooding. Where impacts cannot be avoided by trenchless crossing and a licence is required NE has the class licence (CL31) available. Alternatively if the conditions of this licence cannot be met an individual mitigation licence (A05) can be applied for.
RI_G42 | G56 | a) Natural England advises the Applicant to clarify the location of otter resting places in relation to the watercourses which may be used within the Onshore Order Limits. b) Further information about the cable installation route, associated impacts and proximity to otter resting places would be required to determine the level of impacts posed. c) Natural England would expect works impacting a natal holt to be avoided. d) Natural England welcomes the proposed habitat restoration and CoT76, however there is minimal detail on how this will be monitored to know if this is compensating for the loss and degradation of habitat during construction. |  | No change. |  | No change. Natural England acknowledges the submissions at D2, [REP2-019] and [REP2-046], however the updates in these documents do not resolve the issue raised in our RR.
RI_G43 | G57 | There are several gaps in information regarding air quality emissions on designated sites during the construction, operational and decommissioning periods of the project. As a result, Natural England is unable to provide full comments on this impact pathway and state whether we agree with the conclusions on impacts on designated sites at present. These sites include: Lytham St Annes Dunes SSSI Newton Marsh SSSI Ribble Estuary SSSI Ribble and Alt Estuary SPA Ribble and Alt Estuary Ramsar Red Scar & Tun Brook Woods (Ancient Woodland & SSSI) In particular, Newton Marsh SSSI has been omitted from the air quality assessment and impacts on internationally designated sites (SPA/ SAC/ Ramsar) have not been considered, as highlighted in our previous [RR-1606]. a) We advise that additional information is provided on air quality impacts, as advised in this RR and our previous RR ([RR-1601] Appendix G Onshore Ecology and Nature Conservation). b) Natural England advises for the aforementioned designated sites, air pollution impacts as a result of traffic, machinery and dust are considered and justification is provided for where impacts have been scoped out. |  | No change. |  | No change.
RI_G44 | G58 | The air quality assessment for designated ecological sites does not appear to consider sources of air pollution other than traffic and dust. Natural England advises that information on the use of machinery and equipment (including NRMM) is provided. This should include locations, duration of operations and minimum standard of NRMM and equipment with the potential to release pollutants which may impact designated sites, for both the construction areas and all temporary construction compounds. Air quality impacts for this pathway should include all statutory designated sites within a 200m screening distance from the machinery/NRMM, but is not limited to: Lytham St Annes Dunes SSSI Newton Marsh SSSI Ribble Estuary SSSI Ribble and Alt Estuary SPA Ribble and Alt Estuary Ramsar Red Scar & Tun Brook Woods (Ancient Woodland & SSSI) If impacts on these sites can be screened out, please provide justification on this. |  | No change. |  | No change.
RI_G45 | G59 | Newton Marsh SSSI is not included within the assessment of air quality impacts on designated sites, despite the SSSI being within 200m of the proposed works. We advise that all air quality impacts and sources of pollution (including impacts from traffic, dust and machinery/ equipment) are assessed for the SSSI. |  | No change. |  | No change. Our response to RI_G20 is equally applicable here.
RI_G46 | G60 | Natural England requires clarification of the level of NOx emissions at Red Scar & Tun Brook Woods (Ancient Woodland & SSSI). If the annual-mean NOx PC is 1% of CL or more, then we advise further assessment of NOx emissions on the SSSI is required and should be secured in the Outline Landscape and Ecological Management Plan (OLEM). |  | No change. |  | No change.
RI_G47 | G61 | NH3, nitrogen deposition and acid deposition. Natural England notes that Paragraph 3.11.5.11 – 3.11.5.17 of [APP-075] assesses the impacts of exceedance of critical levels for NH3, nitrogen deposition and acid deposition. Despite critical levels being exceeded, the Applicant rules out impacts due to absence of lower plant communities or already exceeded thresholds. Natural England advises that evidence is required on the presence/ absence of lower plant species within the area of exceedance of 1% threshold within the SSSI. |  | No change. |  | No change. From reviewing Table 1.1 [APP-122], the Daily mean NOx Level as % of CL is 1 (as well as the annual mean), therefore from the data presented it shows that NOx Level Process Contribution (PC) does exceed 1%. In addition, as set out in section 1.2.6.3 the 100% of the long-term environmental standard should be used for local nature sites (i.e. for all sites assessed in this annex except Red Scar & Tun Brook Woods SSSI) which is correct. The long term environmental standard is the Predicted Environmental Concentrations (PEC). Natural England advise for designated sites a screening threshold of 1% of the PC, or more than 70% of the PEC. As the data shows the PC is greater than 1% for NOx, and no data is provided for the PEC, NE do not concur with justification provided in [PDA-022].

## H - Onshore and Intertidal Orni
Point | Point Number(s) from Appendix H [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix H - Onshore and Intertidal Ornithology | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_H1 | H1/H9 | Surveys of intertidal and terrestrial wintering birds and terrestrial breeding birds have been completed to a minimal viable level on areas within the onshore order limits, with some areas within the red line boundary only being partially surveyed. Additionally, there is a lack of survey effort of surrounding areas in close proximity to work areas which are likely to be disturbed by construction works. Natural England’s expectations are that two years of full survey are undertaken across the whole area plus the buffer to inform decision making. As further survey is unlikely to inform the Examination process due to time constraints, when considering the predictions of the Environmental Statement, the survey data should only be taken as a conservative assessment of the populations present and therefore the level of risk, rather than a precautionary one. |  | No change. |  | No change.
RI_H2 | H2/H32 | The construction works are expected to last 66 months – this is a long term, albeit not permanent, time to be having an impact when measured in avian terms. The WCS could therefore mean that all birds impacted would be displaced from the entire terrestrial work area for the full 66 months. Natural England advise that the Applicant should consider phasing the works so that only a proportion of the terrestrial works corridor are impacted at any one time. This will greatly reduce the risk that the works present. |  | No change. |  | No change.
RI_H3 | H3/H59 | Ribble and Alt Estuaries SPA/Ramsar site – inadequate assessment of wintering intertidal features There is not currently enough information within the Application to accurately identify and assess the impacts for wintering and passage features of Ribble and Alt Estuaries SPA/Ramsar site. Natural England advise that the Applicant should update the report to inform a HRA document to reflect the recorded numbers in the affected area, not a questionable area-based measure of habitat availability. A more detailed assessment of the usage of this area by SPA/Ramsar site species and the spatial and temporal patterns of that usage is required to understand the impacts of the proposal and inform mitigation strategies. |  | No change. |  | Progressed but not resolved. The Applicant has now committed to a restriction on all construction activity from November to March (inclusive) at landfall. Whilst this has addressed our concerns for the over-wintering features of the SPA, we still have concerns regarding the assessment and proposed mitigation for impacts to passage waterbirds. We have concerns that the Applicant's Deadline 2 submissions are still lacking in detail in regards to mitigating impacts to passage waterbirds at the landfall and the proposed management at Fairhaven saltmarsh. Natural England will provide further advice on these matters as soon as possible and hope it is accepted at the Examiner's discretion.
RI_H4 | H4/H21 | Adverse effects on the Ribble and Alt Estuary SPA and Ramsar site due to landfall works The landfall site and adjacent areas supports very significant numbers of SPA/Ramsar site birds during the winter and passage periods. However, the Applicant only proposes some limitations to working during these sensitive periods – a limit of 5 weeks working in November-February, with no restrictions to working outside this period. This approach both to the winter period (which we consider to run from November to March inclusive) and the lack of any restriction during passage periods will provide insufficient mitigation. In the absence of a full seasonal restriction for the appropriate periods, or a compelling case that a lower level of restriction is acceptable, Natural England advises that an AEOI cannot be ruled out. A comprehensive seasonal restriction for the sensitive winter and passage periods should be carefully considered in, with the relevant months should be identified with respect to site-specific data and SPA conservation advice. |  | No change. |  | In progress. Please see RI_H3 above. Whilst our concerns regarding overwintering SPA waterbirds is resolved, those relating to passage SPA waterbirds are outstanding.
RI_H5 | H5/H23/H60 | Unless an effective seasonal restriction can be committed to, we advise that an in-principle derogations case for the Ribble and Alt Estuaries SPA/Ramsar site will need to be developed under the Habitats Regulations, demonstrating that there are no alternative solutions and Imperative Reasons of Overriding Public Interest, including that a greater level of seasonal restriction is not achievable. In this light, the proposed roosting refuge would constitute compensatory measures under the Habitats Regulations, Accordingly, a far more detailed submission regarding the installation and management of the compensatory measures is needed addressing Natural England's concerns, and a compensation schedule in the DCO added. To ensure the compensatory measures are targeted and effective, it is critical that the significance of the affected area for SPA and Ramsar site species and their specific requirements from it are adequately described. Additionally, the Applicant should provide evidence that the use of the proposed area is currently compromised by disturbance (noting it falls within the SPA), and that the energy saving for the compensation proposal will be sufficient to offset impacts. |  | No change. |  | No change. The Applicant have not fully considered how they might reduce impacts at the landfall location before considering mitigation options elsewhere. Every effort should be made to follow the mitigation hierarchy. Natural England will provide advice on these matters as soon as possible and submit it into Examination at the Examiner's discretion. Our response to ExA Q1 - Q6.1.2 provides more detail on the question of whether the Fairhaven saltmarsh proposals are mitigation or compensation measures.
RI_H6 | H6/H52 | Ribble and Alt Estuaries SPA/Ramsar – inadequate assessment of impacts on terrestrial waterbirds: Natural England do not agree with the Applicant’s HRA conclusions. We note that the current conclusions are based on modelled information on likely habitat availability. This is often based on out-of-date information and models that claim urban/infrastructure areas are available foraging habitat. The focus should be on the populations revealed by the site-specific surveys rather than generic assumptions. Furthermore, there is a lack of information regarding the spatio-temporal implications of the habitat loss. With regards to mitigation, we advise that the Applicant provides further information on how the tunnel end works of the Ribble crossing will be managed to ensure no disruption to SPA/Ramsar site waterbirds moving along the corridor of the estuary. The justification of only using trenchless techniques is inadequate. |  | No change. |  | In progress. [REP2-044] provides further information with respect to visual and noise disturbance on birds utilising the River Ribble Crossing. The additional information satisfies Natural England's concerns due to the natural topography of the bank and location of compounds for trenchless techniques reducing impacts to SPA features. However, further information is still required to satisfy our concerns regarding HRA conclusions and spatio-temporal implications from other construction activities. Natural England will provide further advice on these matters as soon as possible and hope it is accepted at the Examiner's discretion.
RI_H7 | H7/H22/H61 | Ribble & Alt Estuaries SPA – mitigation for terrestrial impacts/compensation The proposed mitigation measures are hoping to support the needs of a number of species with different ecological needs, however no information is included showing clear design and management information to ensure that these areas are going to be fit for purpose. The terrestrial mitigation areas need reviewing against the specifics of the species (and the number of those species) that they need to host, which relates to the above comments around the phasing of works and being able to accommodate all displaced birds from the whole onshore order limits. Detailed site assessments that articulate site management and structure in relation to the role they need to fulfil need to be generated. |  | No change. |  | No change. Natural England will provide advice on the Applicant's submissions regarding these matters as soon as possible and hope it is accepted at the Examiner's discretion.
RI_H8 | H8/H15 | The potential impacts on Newton Marsh SSSI have not been adequately assessed. There is minimal information on what works will take place in close proximity to this site and how the work will be managed to not affect the site with respect to visual and noise disturbance. Further justification should be provided on how the Applicant has concluded no risk to the site. Proper consideration of this area is also applicable to the HRA as the site is well used by SPA birds, particularly in winter. |  | No change. |  | Resolution in progress. [REP2-044] satisfies our concerns relating to visual and noise disturbance on Newton Marsh SSSI. We advise the Applicant to include appropriate text in the ISAA to reflect these updates. This is necessary as the site is used by SPA birds, and therefore the issue is an SPA/Ramsar site as well as an SSSI matter. Provided that these updated documents are submitted into examination, we believe this issue will be readily resolved.
RI_H9 | H10/H11 | Reliance on the Functionally Linked Land (FLL) description in Bowland Ecology (2021) is flawed for the purposes of this survey. Natural England do not agree with the criteria used for FLL threshold. Natural England requires further information on reasoning for not using standard 1% threshold for measuring significance of FLL. Further, Natural England advises the Applicant to ensure all figures for species are included and consider the possibility of FLL for the species referenced. |  | No change. |  | No change. Whilst the Applicant has clarified that they are using the 1% population threshold for FLL, we are not persuaded that the full suite of species that might be affected by loss of FLL has been identified.
RI_H10 | H12 | Natural England requires clarification on the lapwing data and queries why the two years of data are being listed out separately, when the data represents two phases of one survey.
RI_H11 | H13 | Natural England do not agree with the justification for not following the SNH (2017) guidelines and require further information on mitigation for the impacts. Although construction is temporary, impact risk will largely depend on construction approach (and some permanent infrastructure/potential permanent land use change in mitigation areas), which could last up to 66 months. |  | No change. |  | No change.
RI_H12 | H14 | It is unclear from the report for geese, ducks and swans, waders and gulls and terns if this is referring to birds that are actually breeding or commenting on non-breeding birds gathering in the breeding season. Natural England advise the Applicant that reporting on non-breeding gatherings during the breeding season would be better presented as a separate report/separate section.
RI_H13 | H16 | Natural England notes the incomplete coverage in the survey (0-9 visits = incomplete coverage.) Natural England advises that all areas should have received some survey visits, and that the gaps in coverage inevitably reduce the confidence in the assessment conclusions as regards number and distribution of birds.
RI_H14 | H17 | Natural England note that a number of these species are also non-breeding interest of the Ribble and Alt Estuary SPA and there may be functional linkage. Natural England advises the Applicant to consider the potential for FLL for these species and whether there is potential to impact if so. |  | No change. |  | No change.
RI_H15 | H18 | Natural England note the survey limitations are reasonably well characterised, however it is not clear if survey effort was sufficient for ‘difficult’ species. For example, breeding waterfowl, raptors and crepuscular species. The Applicant should provide clarity on survey effort limitations for species which are considered more difficult to survey.
RI_H16 | H19 | Whilst Natural England acknowledges the consideration of Chapter 9 Air Quality [APP-121], as these impacts could also relate to onshore and intertidal ornithology, they should be assessed within this chapter.
RI_H17 | H21 | The Applicant still intends to carry out up to five weeks of work during the high sensitivity period of November - March inclusive. Natural England advises that all potentially disturbing works should be excluded over this period. We also advise consistency when defining the over-wintering period, which should be the same across all documents and commitments. |  | No change. |  | The Applicant has now committed to a restriction on all construction activity from November to March (inclusive) at landfall. This addresses Natural England's concerns and AEoI can now be ruled out for the over-wintering features of the SPA.
RI_H18 | H24 | Natural England requires more information to ascertain why the following statement could be impossible when there is uncertainty regarding the origin of the birds: “the 353 lesser black-backed gull reported in Table 1.67 cannot all belong to the Ribble and Alt SPA, Morecambe Bay and Duddon Estuary SPA and Ramsar, and the Bowland Fells SPA.”
RI_H19 | H25 | The citation counts and the peak count recorded during the site-specific surveys identifies that many (almost all) species are at >1% of citation value and > 1% of most recent count (noting that this is only noted for Ribble and Alt Estuary SPA for most species). These surveys indicate the importance of the area and the subsequent importance of mitigation, predominantly all at >1%.
RI_H20 | H26 | Natural England advise that Morecambe Bay and Duddon Estuary SPA and Morecambe Bay Ramsar are two separate sites and have different geographical boundaries. Duddon Estuary Ramsar should also be considered and is a separate site.
RI_H21 | H27 | Natural England advise the inclusion of the most up to date digital aerial survey for the Bowland Fells Lesser Black-backed Gull Colony Count.
RI_H22 | H28 | Over 2% of golden plover were found on the area of permanent habitat loss. Although the area represents 0.04% of the total foraging range, the number of golden plover using the area implies it is an important area. Natural England advises the Applicant consider why it may be preferentially used by golden plover, and how this will be replicated in the mitigation areas. |  | No change. |  | No change. RI_H7 is also applicable here.
RI_H23 | H29 | Natural England requires further information from the Applicant to understand if any appraisal has been made to quantify if the proposed mitigation/compensation ground is sufficient to mitigate the loss. Regularity of usage is an important factor to understand if mitigation areas will reliably accommodate the additional displaced birds. |  | No change. |  | No change. RI_H7 is also applicable here.
RI_H24 | H30 | Langley et al., (2022). appears to have been omitted from the references. Update the document to include the reference as cited.
RI_H25 | H31 | The figures set out in Table 1.76 [APP-017] appear to only represent the area of physical ground disturbance arising from the proposal not visual or acoustic disturbance which will extend some 100’s of meters (varying between species) from the works. Temporary habitat loss will therefore be much greater than suggested in the MDS. Further, recovery time of disturbed ground needs to be considered as there is minimal mention of recovery time beyond completion of works. |  | No change. |  | No change.
RI_H26 | H33 | Natural England strongly advises the Applicant to provide further information on the onshore works and ensuring work is staggered appropriately. We suggest the Applicant either needs to provide information to ensure that the mitigation areas really can support all disturbed features in the terrestrial area for the whole period or the Applicant need to identify a works approach that reduces the risk at any one point in time (but still ensure that the mitigation land can support the scaled down risk). |  | No change. |  | No change.
RI_H27 | H34 | Natural England notes that there is a definite impact for 24 months at this fixed point (400kV grid connection cable). We further note that there does not appear to be any identified mitigation for the risk of light and noise affecting the river corridor. Natural England advise the Applicant to review work approaches and clarify how risk from sound/light disturbance is to be mitigated for a period of up to 24 months. |  | No change. |  | Resolved. [REP2-044] provides further information with respect to visual and noise disturbance on birds utilising the River Ribble Crossing. The additional information satisfies Natural England's concerns due to the natural topography of the bank and location of compounds for trenchless techniques reducing impacts to SPA features. Once this information is included in the ISAA this issue will be readily resolved.
RI_H28 | H35 | Natural England note that while it is correct that pink-footed geese do not forage in the intertidal they do roost on the intertidal, which will not have been captured in the ‘overlap analysis’ and should be included.
RI_H29 | H36 | Natural England do not agree with the whole meta-population approach based on a radius around different roosts. This is not appropriate methodology for SPA site-based assessment. The applicant’s survey data identifies the risk they should be considering through their determination of the size of the population that will be impacted. Apportioning by site would be appropriate for the assessment. |  | No change. |  | No change.
RI_H30 | H37 | "Eleven Ribble and Alt Estuaries SPA ornithological features were present within the intertidal environment at the landfall, 9 of which are at >1% SPA. The Applicant should ensure all >1% SPA features are taken through to LSE and AA as significant risks are present to all these features.
RI_H31 | H38 | Natural England requires the Applicant to provide clarification on the beach/landfall Direct Pipe Trenchless installation. Natural England note the commitment to minimise time spent in the intertidal period, however we require clarification on whether the stated two-week period of beach works per cable include delivery and set up/removal of equipment and what will be the risk to the foreshore associated with cable pull. |  | No change. |  | Resolved. [REP2-045] provides clarification the duration of works per cable at landfall and within the intertidal. Natural England are satisfied with the additional information as it allows us to better understand the level of activity, though please note our concerns regarding passage SPA waterbirds remain outstanding.
RI_H32 | H39 | Natural England notes that Still et al. (2015) is repeatedly cited but is not included in the reference list. The study is heavily used as to discuss various species; however, the study is 10 years old and considers bird distribution in a dynamic environment, therefore it may not be that it can be relied upon.
RI_H33 | H40 | The ES predicts the proposal will affect over 2% of 9 species; of which 3 have more than 10% of population potentially affected. Natural England notes these figures do not account for disturbance, which could potentially affect a greater area, resulting in larger areas of temporary habitat loss. Natural England do not support the assertion that the percentage of features affected is not significant because the SPA is big. For wintering intertidal features; Natural England do not agree with the conclusion of a negligible impact from a temporary loss of supporting habitat and/or resource availability – the Applicant need to identify the actual disturbance footprint and confirm that the figures of birds at risk reflect this and not just the direct area being worked over. |  | No change. |  | In progress. Matters regarding overwintering intertidal waterbirds are now resolved, however those relating to passage intertidal waterbirds and terrestrial waterbirds are outstanding. RI_H3 is also applicable here.
RI_H34 | H41 | For passage intertidal features Natural England do not agree with the conclusion that impacts can be ruled out. Reliance on alternate feeding would require knowledge of why this area is so important and consideration in the first instance of seasonal restrictions to works for important passage periods for the species of concern. This also applies to the passage features of the SPA and Ramsar site. |  | No change. |  | No change.RI_H3 is also applicable here.
RI_H35 | H42 | Natural England do not agree with the logic and discussion on foraging ranges as tracking data from the Ribble doesn’t consider spatial displacement by Bowland (which currently supports many of the Ribble birds). Natural England agree that on this occasion there is no LSE.
RI_H36 | H43 | Natural England note that Preston Docks birds are assumed to be the displaced SPA colony, therefore it would be helpful to assess risk in the context of observed birds and this population.
RI_H37 | H44 | Natural England do not agree with the conclusions and advise the Applicant to consider the recommendations made above regarding conclusions made for wintering and passage birds and temporary habitat loss/disturbance at landfall (H41/H42). |  | No change. |  | Resolution in progress. RI_H3 is also applicable here.
RI_H38 | H45 | Further evidence is required to support the statement that trenchless techniques will avoid habitat loss at the Ribble crossing. Additional information on habitat loss from trenchless techniques, i.e. installation of equipment, onshore infrastructure at trench entry and exit pits needs to be considered and appropriately screened. |  | No change. |  | Natural England is satisfied with the additional information provided on the trenchless installation techniques at the River Ribble crossing.
RI_H39 | H46 | Shelduck numbers are clearly high in the area. More information on the habitats being used may shed light on the required mitigation requirements. Natural England advise the Applicant to include shelduck into the calculations for the mitigation areas currently for pink footed goose and whooper swan and consider in more detail what function the habitats being made unavailable provided for the species. However, the Applicant should also consider the density of birds potentially using the mitigation areas and what risks there may be e.g. disease. |  | No change. |  | No change.
RI_H40 | H47 | Natural England agree that in the long term the conclusions are appropriate for wigeon, but this conclusion does not account for effects in the short-term. Natural England advises the Applicant to consider measures to reduce impacts to wigeon in the short-term, noting that spatial scheduling of the works may reduce the requirements for this and other species. Please see advice above regarding shelduck. |  | No change. |  | No change.
RI_H41 | H48 | Natural England advises the Applicant to consider measures to reduce impacts to teal in the short-term. Please see advice above regarding shelduck and wigeon above. |  | No change. |  | No change.
RI_H42 | H49 | Natural England note the commitment to improving nearby areas of habitat for waders such as golden plover. The Applicant should provide more information on the proposed habitat improvements to ensure the measures are appropriate. |  | No change. |  | No change. Natural England will provide advice on the Applicant's submissions regarding these matters as soon as possible and hope it is accepted at the Examiner's discretion.
RI_H43 | H50 | Natural England note that Jourdan et al. (2022) report/paper is repeatedly referenced, but not included in the reference list.
RI_H44 | H51 | Natural England do not agree with the conclusion for black-tailed godwit. The Applicant should reassess their assessment framework and consider the proportions of the passage and winter populations that could be affected. If adverse effects could arise, mitigation habitat should be provided that will cater for the requirements of the species. |  | No change. |  | No change.
RI_H45 | H52 | Natural England do not agree with the conclusion of no AEOI for temporary loss of supporting habitats and/or resource availability for the features that utilise terrestrial habitats for the Ribble and Alt Estuaries SPA. The Appropriate Assessment should focus on the populations revealed by the surveys, rather than modelled information. Natural England advises the following additional evidence is also required: •Details of the locations of the alternative supporting habitat qualifying species can use, including their distance from the proposal boundary and size. •Further details of how the applicant will ensure the recovery of the temporary habitat loss. This should include details of mechanisms that will be put in place to ensure the supporting habitat recovers, and predicted timescales. |  | No change. |  | No change.
RI_H46 | H53 | The SPA non-breeding waterbird assemblage is a feature in its own right, therefore all the other species that contribute to it also have to be considered, in particular in this case in terms of numbers, as diversity and quality are more likely to be robust at a site scale. Natural England advise the Applicant to revisit the framing of [APP-017] and re-consider impacts/risks and compensation and mitigations options and planning for managing the risks. |  | No change. |  | No change. Please also refer to ExA Q1 - Q9.5.10.
RI_H47 | H54/H55 | Natural England note the following statement : “..all features have been assessed independently there is not predicted to be any additional impact ..“ and do not agree with this conclusion and methodology in relation to the breeding waterbird assemblage, but note the conclusion of no AEOI is likely to be correct in this instance.
RI_H48 | H56 | Natural England disagrees with the conclusions for Dunlin as a Ramsar site feature for the same reasons as identified for other intertidal waders. |  | No change. |  | No change.
RI_H49 | H57 | Natural England disagrees with the conclusions for Black-tailed godwit as a Ramsar feature for the same reasons as identified for other terrestrial waders. |  | No change. |  | No change.
RI_H50 | H58 | The assessment of habitat loss during the operational phase is based on habitat loss in a different site (Liverpool Bay SPA). Natural England advises the Applicant to update the report and include the habitat loss during Operation & Maintenance in Ribble and Alt Estuaries SPA.
RI_H51 | H60 | Fairhaven Saltmarsh is identified as a mitigation area, however questions remain over its suitability. Natural England strongly advise the Applicant to produce some supplemental information clarifying why this proposal is considered likely to be effective, clarifying the management required to support delivery, and justifying its energetic value to the species impacted. |  | No change. |  | No change. Natural England will provide advice on the Applicant's submissions regarding these matters as soon as possible and hope it is accepted at the Examiner's discretion.
RI_H52 | H61 | The level of detail presented in the mitigation area summaries for intertidal mitigation and terrestrial mitigation is not sufficient to fulfil the expectations of the HRA with regards to certainty of outcome. Produce some supplemental information clarifying why this proposal is considered likely to be effective, clarifying management to support delivery, and justifying its energetic value to the species impacted. |  | No change. |  | No change. RI_H7 is also applicable here.
RI_H53 | H62 | Please note that comments relating to SSSI sites are included in the sections above.

## I - Fylde MCZ
Point | Point Number(s) from Appendix I [RR-1601] | Taken from Natural England’s Relevant and Written Representations Morgan and Morecambe Transmission Assets Appendix I - Fylde MCZ | RAG Status Rel and WR Rep and D1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
RI_I1 | I1 | Up to 3% of the offshore export cables, including cable crossings within Fylde MCZ may require cable protection and this equates to a total of 0.0304km2 (30,400m2/3.04ha) of lasting habitat change/loss within the site. Natural England does not agree with the Applicants conclusion of no likelihood of hindering the conservation objectives of Fylde MCZ. Unless it can be demonstrated otherwise, the nature, scale and duration of impacts from lasting habitats change/loss from the placement of cable protection is likely to hinder the ‘maintain’ habitat feature conservation objectives of the site. We advise that the MCZ assessment should proceed to a stage 2 assessment and a without prejudice Measures of Equivalent Environmental Benefit (MEEB) proposal should be produced. |  | Resolved: The Applicant has undertaken a Stage 2 MCZ Assessment and without prejudice MEEB and submitted these into Examination at Deadline 1. Therefore this issue has been resolved at Deadline 2. Please note, other comments relating to the MCZ assessment are not resolved. This comment has specifically been resolved as the Applicant has provided the documents requested. NE has provided further comments on the Applicants 'Without prejudice MEEB proposal in 'Tab J Benthic Compensation' of this R&I Log and Appendix J of our Deadline 2 submission.
RI_I2 | I2 | Natural England agrees with the MMO in considering that in order to fully discharge regulatory duties under section 69 (1) of the MCAA, in combination and cumulative effects must be considered. Natural England considers the O&M phase activities for Morgan and Morecambe Transmission Assets combined with the projects listed in Table 1.21 and on-going Oil and Gas impacts will result in lasting habitat change / physical disturbance which will further hinder the conservation objectives of the Fylde MCZ. We strongly advise that Applicant's potentially affecting the MCZ will need to intensify their use of the mitigation hierarchy. |  | No change. |  | No change.
RI_I3 | I3 | The most recent condition assessment for Fylde MCZ concluded that subtidal sand and subtidal mud were in a favourable condition. Natural England advises that whilst the cable protection is in situ, the extent and distribution attribute of the site features can neither be maintained or restored. Nor can the impacts be considered temporary even if removal is secured at the end of the 35-year project lifespan. Therefore, we advise that the impacts will result in ‘lasting’ habitat change from mud and sand to hard substrata which may result in habitat loss as removal and/or recovery post removal is not guaranteed. Additionally, we do not agree with the Applicant that in-filling of cable protection with sediment will occur and be sufficient to provide the same structure and function in the impacted area. Unless the Applicant’s position changes it is unlikely that there will be agreement between the Applicant and Natural England during examination on this issue. Please see comment I1 on the provision of a without prejudice MEEB case. |  | No change. |  | No change.
RI_I4 | I4 | The Applicant has stated that the requirement for, and potential locations of any cable protection due to ground conditions within the Fylde MCZ are not yet known. Therefore, the MDS figures have assumed that the cable protection material for the cable crossing could occur wholly within either the subtidal sand or subtidal mud features. Therefore, the MDS for long term habitat loss of each of the features have been provided as: Subtidal sand – 0.0304km2 (0.014% of the area of this feature in the MCZ Subtidal mud – 0.0304km2 (0.069% of the area of this feature in the MCZ) Natural England does not agree with this approach. We advise that an accurate MDS and realistic Worst-Case Scenario (WCS) for each feature is presented and assessed for lasting habitat change/loss and updated withing the Application documents. We highlight the importance in providing specific figures to inform the compensation requirements for a without prejudice MEEB. |  | No change: Please see Tab J of this R&I Log and Appendix J of our Deadline 2 submission. |  | No change. Please see Tab J for more detail.
RI_I5 | I5 | Natural England disagrees with the Applicant on the scale and significance of the impacts on the interest feature of the Fylde MCZ. Natural England also advises that impacts considered as a percentage of the whole MCZ is misleading given the size of the site. The lasting habitat change/loss impacts from the Transmission Assets combined are still 0.0304 km2/3.04ha from cable protection. We do not consider this amount of lasting habitat change/loss to be small scale. Natural England does not believe that the respective positions are likely to change in relation to scale and significance of the impact to the Fylde MCZ and therefore we provide no further comment unless design parameters change through the examination. |  | No change. |  | No change.
RI_I6 | I6 | Natural England note the commitments; CoT108 and CoT109 from the Applicant that any external cable protection used within the Fylde MCZ will be designed to be removable at decommissioning stage. However, we note that this commitment does not include the action to remove cable protection at the decommissioning phase, only that the protection will be ‘removable’. Although some of the cable protection options included within the project description may be removable they are not considered as such from a nature conservation perspective due to further impacts to the designated site features e.g. rock armouring. We advise a commitment to remove all seabed infrastructure at the time of commissioning both inside and outside of Fylde MCZ should be secured in the DCO. |  | No change. |  | No change.
RI_I7 | I7 | Natural England reiterates concerns around the varying construction scenarios proposed by the Applicant. The most impactful to Fylde MCZ would be option 3b (i.e. sequential construction with a gap of up to a maximum of four years between completion of construction of the transmission assets for the first project and commencement of construction for the second project). This is mainly due to the four-year gap which may allow for some recovery of seabed habitats and species from the first works. The Applicant has not considered the potential for recovery and the impact from repeated interventions or the four-year gap, therefore we do not agree that the WCS has fully been assessed. |  | No change. |  | No change.
RI_I8 | I8 | Whilst we welcome the refinement work the Applicant has undertaken, we advise there are further mitigation options which should be explored by the Applicant to minimise impacts on Fylde MCZ and included for consideration in the Application, namely: • Commitments should be made and secured to avoid the most sensitive Priority habitats designated under Section 41 of the NERC Act (2206).This is applicable both within and outside of Fylde MCZ; • Exclusion of the use of jack up vessels within the MCZ; • UXO clearance to be moved outside of the MCZ prior to detonation to avoid impacts to the seabed where possible; • Boulder clearance using a grab not a plough; • Remove all cable and scour protection at the time of decommissioning, both within and outside of Fylde MCZ • Further mitigation measures to be adopted with regards to sediment disposal (I10) • Refining long term habitat loss for subtidal mud and subtidal sand within Fylde MCZ to provide more realistic MDS parameters for habitat loss. |  | No change. |  | No change.
RI_I9 | I9 | Natural England would welcome further information on dredge and disposal activities with regards to Fylde MCZ. The Application states that disposal activities including sandwave clearance will be conducted throughout the Transmission Assets Order Limits but that no commitments have been proposed to mitigate impacts either within or outside of benthic designated sites. Mitigation options should be adopted and disposal options should be explored to ensure that sediment is deposited in areas of similar sediment character so that the risk of permanently altering the sediment character in any given location is minimised. |  | No change. |  | No change.
RI_I10 | I10 | Natural England notes that secondary scouring needs further consideration in the Stage I MCZ Assessment in relation to impacts to sediment transportation. |  | No change. |  | No change.
RI_I11 | I11 | Natural England notes that UXO clearance activities are likely to be undertaken within the Fylde MCZ. Natural England continues to advise that UXOs should be detonated outside of Fylde MCZ to avoid the creation of a crater. As a minimum, we advise that further information is required in relation to the depth of any crater and the impacts this may have on the subtidal mud and sand features including any recovery times. |  | No change. |  | No change.
RI_I12 | I12 | We welcome the inclusion of in principal monitoring proposed for benthic subtidal and intertidal ecology in the Offshore In Principal Monitoring Plan (OIPMP). However, the focus seems to be on physical/sediment recovery and lacks sufficient ecological context. Additionally, there is no reference to pre- and post-construction monitoring which is essential to understand and assess recovery. We advise that the rationale within Table 1.3 of the OIPMP needs to be updated to additionally include “temporal and spatial changes in benthic communities and their recoverability….”. We also advise that the Applicant provides clarity that monitoring surveys will be undertaken pre- and post-construction and that temporal monitoring over an agreed time period should take place in order to confirm recovery. |  | No change. |  | No change.
RI_I13 | I13 | Natural England notes that within the Outline O&M plan there is the intention to use the cable protection allowance over the lifetime of the project. However, this is not aligned with Natural England position on cable protection. We advise that post construction and an agreed snagging time a new marine licence would be required for the placement of further cable protection within Fylde MCZ. Natural England advises that the Applicant refines the O&M requirements to be align with the SNCB and regulatory position on this. |  | No change. |  | No change.

## J - Benthic Compensation
Point | NE Ref from Appendix J | Taken from Natural England’s Detailed Comments (Part B) on the Applicant's Draft Without Prejudice MEEB In- Principle Plan (Appendix J submitted at D2 and include all points within this tab of the R&I log) | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3
Compensation measure: Strategic Compensation - New site designation or Extension for Subtidal Sand and Subtidal Mud
RI_J1 | J3 | NE does not agree with the approach taken to determine the total WCS for lasting habitat loss. The approach taken assumes that cable protection requirements could occur wholly within either the subtidal sand or subtidal mud feature. In order for us to agree the impact, the habitat loss for each feature should be calculated then summed to provide the total area of habitat loss. |  | No change.
RI_J2 | J4 | Due to potential uncertainties with the delivery mechanisms and timeframes for successful delivery of the measure, further discussions are required in relation to individual project contributions and compensatory ratios which may be required. |  | No change.
RI_J3 | J5 | Natural England recognises that there are likely to be time lags between impact occurring and compensation achieving the desired outcomes. We would wish to see the project contribution to the measure to be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project.
RI_J4 | J6 | The location of the measure is still under consideration by DEFRA, NE and JNCC and as yet nothing has been agreed and/or secured. There is likely to be consultation on potential locations during the examination.
RI_J5 | J7 | Long Term implementation is still under consideration by DEFRA, NE and JNCC and as yet nothing has been agreed and/or secured.
RI_J6 | J8 | Success criteria/Ability to prove additionality is still under consideration by DEFRA, NE and JNCC and as yet nothing has been agreed and/or secured.
Compensation measure: Biogenic Reef - Native Oyster
RI_J7 | J10 | Natural England advises that reef creation/enhancement is not considered to provide comparable ecological function and is therefore not an appropriate measure for subtidal sand and subtidal mud systems within Fylde MCZ and provide no further comment on this as a potential measure. |  | No change.
Compensation measure: Bivalve Seeding inside MCZ
RI_J8 | J11 | It remains unclear what additionally this measure would provide and therefore NE questions this as being compensation for lasting habitat loss/change to subtidal sand and subtidal mud. In addition, the seeding of bivalves is associated with biogenic reef communities on mixed sediment and not subtidal sand and subtidal mud. |  | No change.
Compensation measure: Bivalve Seeding outside of designated sites
RI_J9 | J12 | Given the legislative changes that would be required, Natural England does not consider this option is viable within the Project’s timeframe. If the Applicant wishes to pursue this there will need to be agreement from The Crown Estate for a seabed lease and management measures put into place. |  | No change.
RI_J10 | J13 | Natural England does not agree with the approach taken to determine the total WCS for lasting habitat loss. The approach taken assumes that cable protection requirements could occur wholly within either the subtidal sand or subtidal mud feature. |  | No change.
RI_J11 | J14 | The scale/extent of the measure has not been presented in detail and/or agreed with Natural England, JNCC or DEFRA. |  | No change.
RI_J12 | J15 | We do not believe that this measure will be available in the project timeframes. |  | No change.
RI_J13 | J16 | The location of the measure has not been presented in detail and/or agreed with TCE, Natural England, JNCC or DEFRA. |  | No change.
RI_J14 | J17, J18 | There is a requirement for changes in legislation for the delivery of this measure and therefore until that is secured, further long-term implementation and success criteria remains unknown. |  | No change.
RI_J15 | J19 | We do not believe that is currently suitable as a sole or part measure at this time. |  | No change.
Compensation measure: Seagrass habitat creation/restoration
RI_J16 | J20 | Natural England advises that seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for.' Natural England also highlights that seagrass is not a feature of subtidal mud and further advice on this measure should be read in this light.
RI_J17 | J21 | Natural England has significant concerns about the deliverability of seagrass restoration, even on a small scale as there have been no long term successes with seagrass restoration in the UK. Subtidal seagrass restoration should only be a minor part of a wider package in terms of the required compensation. It could be retained to supplement other measures, or potentially as an adaptive management response. |  | No change.
RI_J18 | J22 | NE does not agree with the approach taken to determine the total WCS for lasting habitat loss. The approach taken assumes that cable protection requirements could occur wholly within either the subtidal sand or subtidal mud feature. In order for us to agree the impact, the habitat loss for each feature should be calculated then summed to provide the total area of habitat loss. |  | No change.
RI_J19 | J23 | The scale/extent of the measure has not been presented in detail and/or agreed with the SNCBs.
RI_J20 | J24 | It is unclear if this measure can be delivered prior to the impacts occurring.
RI_J21 | J25 | The location of the measure has not been presented in detail and/or agreed with the SNCBs. More detail is required to address our concerns.
RI_J22 | J26, J27 | Long term implementation and Success/Ability to prove additionality is yet to be considered in detail and agreed with the SNCBs. More detail is required to address our concerns.
RI_J23 | J28 | Natural England advises that this measure could only be considered as part of a package providing <10% of the required compensation and/or potential adaptive management for part delivered compensation. There would also be a requirement for the provision of subtidal seagrass, not intertidal.
Detailed comments Documents used: [REP1-059] Stage 2 MCZ Assessment
RI_J24 | J29 | It is unclear why terrestrial issues have been included in the document. NE advises that there should be MEEB for each designated site.
RI_J25 | J30 | Natural England doesn’t agree with the Applicant in relation to small scale losses not hindering the conservation objectives of the MCZ. We refer the ExA to Appendix C Annex A of our relevant/written representation [RR-1601]. It is unlikely that either Applicant’s or Natural England position on this will change during examination.
RI_J26 | J32 | Natural England advises that lasting habitat change/loss can only be considered if removed at the time of decommissioning. After that timeframe it becomes a permanent impact. We advise that commitments should be made to ensure removal. |  | No change.
RI_J27 | J33 | Natural England advises that even where the conservation objectives are set to ‘maintain’, lasting habitats change/loss would not maintain the extent and distribution of the features; thus hindering them. This would lead to a restore conservation objective being set which can’t be achieved whilst the cable protection is in situ, therefore we advise that MEEB is required. |  | No change.
RI_J28 | J34 | DESNZ guidance on the MRF agrees with the Applicant that there is likely to be a time lag between impacts occurring and the delivery of the compensation. Therefore, allowances will be included in the MRF process for this.
RI_J29 | J35 | The EIA lifespan is 35 years. Therefore Natural England doesn’t consider the impacts to be temporary, given that the features extent and distribution will be hindered. Likely leading to changes in other attributes. It is unlikely that either Applicant’s or Natural England position on this will change during examination.
RI_J30 | J36 | Natural England highlights those consents dating back to 2000 pre-date the MCZ designation and is therefore considered part of the baseline. We advise that the existing cable is not a material consideration in any decision making.
RI_J31 | J37 | As written there is no differentiation between impacts to subtidal sand or subtidal mud except at the cable crossing which is known to be subtidal mud. We advise that unless the lasting habitat loss for the two features can be differentiated then it is likely that compensation will be required for 30,400m2 of subtidal mud, plus 26,400m2 of subtidal sand. We advise that this needs to be clearer. |  | No change.
RI_J32 | J38 | CoT 109: Natural England advises that it is not sufficient as mitigation. This mitigation measure should be considered further by the Applicant and removal of cable protection should be agreed now as part of a decommissioning plan. |  | No change.
RI_J33 | J39 | Natural England advises that the mitigation measure in CoT 116 is not sufficient in relation to sandwave levelling. Further commitments should be included such as the deposition of any sediment from sandwave levelling within the MCZ is placed adjacent to the levelling, in similar sediment and upstream of the sandwave to facilitate recovery. |  | No change.
RI_J34 | J40 | Natural England advises that the mitigation measure is CoT 117 is considered further by the Applicant. The use of Jack Up Vessels (JUVs) should be avoided in the MCZ due to potential leg depressions. |  | No change.
RI_J35 | J41 | Natural England advises that we do not believe that there are further measures within the long list of measures that could be taken forward at the project level that would provide the necessary MEEB.