## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised through our responses to the S42 statutory consultation, additional non-statutory consultation (including prior Discretionary Advice Service (DAS) comments) and throughout the Examination for the East Midlands Gateway Phase 2 (EMG2) project. Each issue has been assigned a Red, Amber, Yellow or Green risk rating, as defined below. This Risk and Issues Spreadsheet can be updated through Examination, with the rating updated at each deadline to clearly show progress made.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Natural England's key updated advice at the current project stage/ examination deadline is shown in Bold.
Requested actions are shown in red text.
The spreadsheet contains filters to enable ease of viewing. For example, filtering column D1 ('Current RAG Status') allows the user to view only those issues which are marked as yellow, amber or red.
Under 'Issue Summary' (column C1), C = Construction, O = Operation and D = Decommissioning

## R&I Log
Pre- App Ref | RR / WR Ref | Theme | Issue Summary | Current RAG Status | Advice Given in Natural England’s S42 Response - March 2025 | RAG Status S42 - March 2025 | Consultation, actions and progression May-July 2025 (including DAS and non-statutory consultation July 2025) | RAG Status Non-Stat Consultation - July 2025 | Consultation, actions, progression - pre-app chapter updates August 2025 | RAG Status | Consultation, actions, progression - Relevant Reps 09/01/26 | RAG Status Relevant Reps | Consultation, actions, progression - SoCG Discussion Feb 2026 | RAG Status | Consultation, actions, progression - Written Reps & ExQ1 | RAG Status | Consultation, actions, progression - D4 and ExQ2 | RAG Status | Consultation, actions, progression | RAG Status
n/a | NE1 | EIA | n/a | Green | n/a | n/a | n/a | n/a | n/a | n/a | DCO & MCO Projects We note in the assessment commentary on future baseline (DCO 6.9/MCO 6.9), the LLR-LNRS is not considered, despite having clear and targeted habitat priorities and measures to improve nature recovery within the landscape. This includes measures for agricultural land, woodland, grassland, urban and freshwater habitats. As such, future baseline on agricultural land could be improved in line with this document, where landowners and managers take up the outlined and mapped initiatives. The assessment should take this into account in its review. Ensure the LLR-LNRS is included in review of the future baseline within the ES. | Yellow | Applicant Response to RR (email 24/02/26): We are not at this point to amend the chapter, however the following hopefully provides some reassurance that the future baseline would not be significantly impacted. LNRS measures (combined measures shaded)) have extremely limited coverage on the application (Pink MCO, Red DCO). Restricted operational areas of highways verges are not thought likely to be subject to substantial changes in management as a result of the LNRS. The area which does merit some consideration is that of the existing rail track, which is subject to 5 measures (MN2,9,11,12 and 13). These measures promote management to benefit wildlife and control invasive species. The area includes the operational rail track footprint, and embankments which are subject to existing management objectives secured through the EMG1 scheme. As such no these areas are not expected to be subject significant changes in ecological value. NE Response (email 02/03/26): I note that you have reviewed the mapped measures of the LLR-LNRS and agree, there are none within the order limits of the project. I would say that some of the unmapped measures (Landscape Scale Priorities and Measures) are relevant. Particularly around 9.5.1.e Landscape Nature-Friendly Farming. There may be increased uptake of these measures on agricultural land as a result of the LNRS and its implementation. And this is noted in NN-NPS that projects should have regard for these plans. This general good practice may improve the future baseline. However, I take your point that it may not be to a significant level. If in the SoCG you can outline this justification in relation to this application, then we could reconsider our position on this and manage it through the SoCG and change to green. Action: Remain Yellow until updated in SoCG | Yellow | NE note the comments provided by the Applicant (via email 24/02/26) on the limited significance of the use of LNRS in the future baseline assessment. This is due to a lack of mapped measures within the Order Limits and limited ecological value within the future baseline. NE note that some of the unmapped measures could provide uplift to the future baseline, but acknowledge the limited significance of impacts for consideration in the assessment. As such we are satisfied this has been justified and can be changed to Green in the SoCG. | Green
NE1 | NE2 | Internationally Designated Sites | Study Area (C, O, D) | Green | Chapter 9, para. 9.2.8 sets out the study area used for the assessment. The use of a 15km study area for international designations is noted; however, a larger study area of 20km is often required where any international sites support birds which have an extended foraging distance, i.e. wintering geese/ swans, and 30km where bats are a feature of an international site. In this scenario, no such sites are present within 20/30km of the proposal, so Natural England raise no further issues with the study area. However, Natural England advise that amending the study area for the final submission may reduce any uncertainty here and reassure the Examining Authority (ExA) that all relevant sites have been screened appropriately. | Yellow | Following the S42 consultation, Natural England provided comments on an updated version of the ES Chapter 9: Ecology and Biodiversity (received by email on 02/05/2025). The study area used for the assessment has been updated, with the original 15km study area for internationally designated sites being extended to 20km for any international sites which support birds with extended foraging distance (i.e. wintering geese/ swans), and 30km for international sites where bats are a notifying feature. This is in line with the advice provided by Natural England and therefore the update is welcomed. | Green | No change. | Green | DCO & MCO Projects Natural England welcome the study area outlined within the ES (DCO 6.9/MCO 6.9) following our comments at the PEIR stage, to give certainty to the Examining Authority in their review of impacts to international sites, i.e.: 15km around the EMG2 Project Order Limits for sites of International Importance (e.g. Special Areas of Conservation (SACs), Special Protection Areas (SPAs), Ramsar sites), extended to 20km for international sites which support birds with extended foraging distance, i.e. wintering geese/ swans, and 30km for international sites where bats are a notifying feature. | Green | n/a | Green | n/a | Green
NE2 | NE2 | Internationally Designated Sites | Identification of relevant sites (C, O, D) | Green | Chapter 9: Ecology & Biodiversity correctly identifies the internationally designated sites within a 15km zone of influence of the Scheme boundary as being: River Mease Special Area of Conservation (SAC). The River Mease SAC is located approximately 13.5km from the Scheme at its closest point. The proposed Scheme does not lie within the catchment area of the River Mease. | Green | No change. | Green | No change. | Green | No further comment. | Green | n/a | Green | n/a | Green
NE4 | NE2 | Internationally Designated Sites | Shadow Habitats Regulations Assessment (sHRA) Stage 1 Screening (C, O, D) | Green | Natural England agrees with the findings of the Shadow Habitats Regulation Assessment (sHRA) (Appendix 9h) Stage 1 Screening Assessment, which identifies no pathways for likely significant effects in relation to the following topics: Direct Habitat Loss; Thermal Effects; Biological Connectivity and Vegetation Structure; Reduction in Water Quality (pollutants); Reduction in water quality (Nutrients); Water Abstraction; Increased risk of invasive plant species entering the watercourse; Increased risk of siltation entering the watercourse; and Inappropriate weirs, dams and other structures. The absence of significant effect pathways also eliminates the possibility for the project to have any effects on the SAC in combination with other plans/ projects. Overall, Natural England agrees with the conclusion that the project poses no risk of adverse effects on the integrity of the River Mease SAC, either alone or in combination with other projects, and that there is no need to progress to Stage 2 ‘Appropriate Assessment’. | Green | Updates to the sHRA were made following comments from the Planning Inspectorate (PINS). The updates are summarised in Para. 1.11 of the sHRA (Appendix 9H to the ES), and include more detailed explanations and clarifications to support the conclusions made in the report. Natural England agrees with the findings of the updated sHRA, which identifies no pathways for likely significant effects and thereby eliminates the possibility for the project to have any effects on the SAC in combination with other plans/ projects. Overall, Natural England agrees with the conclusion that the project poses no risk of adverse effects on the integrity of the River Mease SAC, either alone or in combination with other projects, and that there is no need to progress to Stage 2 ‘Appropriate Assessment’. | Green | No change. | Green | DCO & MCO Projects We agree with the conclusion of the sHRA (DCO 6.9H/MCO 6.9H), that no significant direct or indirect impacts are anticipated to the River Mease SAC from the DCO or MCO projects either alone or in combination with other projects, and that there is no need to progress to Stage 2 ‘Appropriate Assessment’. This is due to both distance and because the proposed projects do not lie within the catchment area of the River Mease. Natural England welcome the high sensitivity rating given to internationally designated sites and the assessment of impacts provided in the ES. However, we would note that in Tables 9.18 and 9.35 summarising residual impacts, the River Mease SAC was not listed. It would be useful for completeness and consistency to have it included in the table. Natural England are satisfied there are no impacts to the River Mease SAC from the development alone or in combination and agree with the outcomes of the sHRA. We recommend the River Mease SAC is added to Tables 9.18 and 9.35 within the ES for completeness. | Green | n/a | Green | n/a | Green
NE5 | NE3 | Nationally Designated Sites | Identification of relevant sites (C, O, D) | Green | Chapter 9: Ecology & Biodiversity identifies a 2km zone of influence for site of National or Regional Importance e.g. Sites of Special Scientific Interest (SSSIs) for the purpose of the desk study and Lockington Marshes SSSI is correctly identified as the only SSSI within 2km the Scheme. Through our Environmental Impact Assessment (EIA) Scoping Response (12 September 2024, ref. 486173), Natural England requested that potential impacts of the Scheme on Attenborough Gravel Pits SSSI (approximately 5.5km from the Scheme) is also considered. The inclusion of Attenborough Gravel Pits SSSI in Section 9.4: Baseline Conditions of the PEIR is therefore welcomed. | Green | No change. | Green | No change. | Green | DCO & MCO Projects Natural England welcome the study area of 2km outlined within the ES for nationally designated sites (DCO 6.9/MCO 6.9). We welcome the inclusion of Attenborough Gravel Pits SSSI following our comments on the PEIR, due to potential hydrological connectivity. We are satisfied the ES has considered the designated features, condition and pressures of the SSSIs. | Green | n/a | Green | n/a | Green
NE9 | NE3 | Nationally Designated Sites | Assessment of construction phase water quality impacts (C) | Amber | As above - an assessment of potential impacts to designated sites was omitted from Chapter 9: Ecology & Biodiversity of the PEIR. | Amber | The updated chapter includes assessment of construction phase water quality impacts. Natural England agrees that a potential construction impact pathway exists in the form of pollution events. Via DAS, Natural England requested that pollution prevention measures are set out in the CEMP and referenced as embedded mitigation in the ES chapter. Our comment applied to the EMG2 main site and the highway works to the north (which are within the same catchment area as the Lockington Marshes SSSI). The CEMP submitted with the non-statutory consultation covers standard good practice measures for water quality (Sections 5, 11, 12, 14 19 and Appendix 4 Silt Management Plan). Therefore Natural England agrees that impacts to the Lockington Marshes SSSI and Attenborough Gravel Pits SSSI are not likely to be significant if the CEMP and subsequent P-CEMPs are followed appropriately. However, contrary to Natural England's advice, the CEMP is still referenced as additional rather than embedded mitigation. Natural England would prefer if this was amended, but for this particular project it is unlikely to make a material difference to the residual effects, assuming the CEMP is secured by DCO requirement. | Yellow | No change. It is noted in Table 9.4 that the CEMP will remain as additional, rather than embedded, mitigation. The RAG status remains 'yellow'. This means Natural England does not agree with the Applicant’s position or approach and we would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. | Yellow | DCO Project Additional mitigation gives further measures to mitigate impacts to the SSSIs from surface water run-off, specifically from the CEMP (DCO 6.3A), which includes a Silt Management Plan. Natural England are satisfied for the construction phase that the Sustainable Drainage Statements and CEMP adequately demonstrate that surface water run-off will be managed and treated to ensure water quality and water quantity do not negatively impact sensitive waterways from surface water discharge and impact the SSSIs. We welcome reference to the CIRIA SuDS Manual and demonstration of the Simple Index Approach. We welcome the inclusion of a Silt Management Plan within the CEMP to ensure all impacts from pollution from construction surface water run-off are mitigated. Ensure the CEMP, including a Silt Management Plan where applicable, are secured by requirement within the DCO. | Amber | n/a | Amber | No update. | Amber | No update. | Amber
NE10 | NE3 | Nationally Designated Sites | Assessment of operational phase water quality impacts (O) | Amber | As above - an assessment of potential impacts to designated sites was omitted from Chapter 9: Ecology & Biodiversity of the PEIR. | Amber | The updated chapter included an assessment of operational phase water quality impacts. Natural England agrees that any pollutants released into rivers would be subject to a dilution effect before reaching the SSSIs. However, we request further explanation is added regarding the types of potentially polluting activities that may occur on site. This will allow the impact pathway to be fully explored, including consideration of whether the SuDS design is appropriate to manage such pollution, before a conclusion is made regarding the likely significance of effect. It is noted that SuDS will be designed in accordance with the latest CIRIA SuDS manual and water treatment index, which is welcomed. Further detail should be provided in the chapter regarding specific details of the SuDS design, such as the treatment components proposed and their efficacy in removing relevant pollutants that could be associated with operational activities on the site. | Amber | [To be reviewed] | Amber | DCO Project Natural England welcome the high sensitivity rating given to nationally designated sites and the assessment of impacts provided in the ES. We welcome the application of the mitigation hierarchy to avoid, mitigate and then compensate. We are satisfied this has been applied by the Applicant. Natural England are satisfied from the documents that the designated features of the SSSIs have been adequately identified and assessed for impacts from the DCO project. The ES identified hydrological links to the SSSIs as a potential impact pathway. The impacts were assessed as negligible due to the provision of embedded mitigation (avoidance, mitigation and enhancement measures such as SuDS and other green infrastructure), and dilution effect due to distance. These measures are to be compliant with the submitted Landscape and Ecological Management Plan (LEMP) (DCO 6.9J/MCO 6.9J) and Sustainable Drainage Statements (DCO 6.13H and I). We are satisfied with this appraisal. Natural England are satisfied for the operation phase that the LEMP and SuDS Statements adequately demonstrates the SuDS will be effective and monitored and maintained for 30 years. We suggest the CIRIA SuDS Manual is referenced in regard to the installation and ongoing maintenance of the features. Natural England would like to understand what the intention is for the SuDS after the 30-year period, as surface water run-off will need to be monitored and maintained for the full operational period. We welcome the inclusion of the Environment Management Plans to mitigate impacts to sensitive watercourses linked to the SSSIs. The Environment Management Plans should be secured by requirement within the DCO. We would also note that in Tables 9.18 and 9.35, summarising residual impacts, the Lockington Marshes SSSI and Attenborough Gravel Pits SSSI were not listed. It would be useful for completeness and consistency to have them included in the table. Ensure the LEMP and Sustainable Drainage Statements are secured by requirement within the DCO. Ensure the SuDS are secured for monitoring and maintenance for the full operational period of the DCO project. We recommend the CIRIA SuDS Manual is referenced in regard to the installation and ongoing maintenance of the SuDS features within the Environment Management Plans. Include Lockington Marshes SSSI and Attenborough Gravel Pits SSSI to Tables 9.18 and 9.35 within the ES for completeness. | Amber | n/a | Amber | No update. | Amber | No update. | Amber
n/a | NE4 | Nationally Designated Sites | Assessment of operational phase water quality impacts (C, O) | Amber | n/a | n/a | n/a | n/a | n/a | n/a | MCO Project Natural England welcome the study area of 2km outlined within the ES for nationally designated sites (DCO 6.9/MCO 6.9). We welcome the inclusion of Attenborough Gravel Pits SSSI following our comments on the PEIR, due to potential hydrological connectivity. We are satisfied the ES has considered the designated features, condition and pressures of the SSSIs. Natural England welcome the high sensitivity rating given to nationally designated sites and the assessment of impacts provided in the ES. We welcome the application of the mitigation hierarchy to avoid, mitigate and then compensate. We are satisfied this has been applied by the Applicant. Natural England are satisfied from the documents that the designated features of the SSSIs have been adequately identified and assessed for impacts from the MCO project. They identified hydrological links to the SSSIs as a potential impact pathway. The impacts were assessed as negligible due to the provision of embedded mitigation (avoidance, mitigation and enhancement measures such as SuDS and other green infrastructure), and dilution effect due to distance. These measures are to be compliant with the submitted LEMP (from the original EMG1 DCO) and SuDS Statement (DCO 6.13J). We are satisfied with this appraisal. Additional mitigation gives further measures to mitigate impacts to the SSSIs from surface water run-off, specifically from the Construction Management Framework Plan (from the original EMG1 DCO) and a phase specific CEMP (within the current MCO). We would welcome the inclusion of a Silt Management Plan within the phase specific CEMPs as outlined within the CEMP (DCO 6.3A), which includes a Silt Management Plan. We welcome the inclusion of the Environment Management Plans as mitigation; however Natural England has not been able to review the EMG1 LEMP or Construction Management Framework Plan. Natural England would like to understand what the intention is for the SuDS after the 30-year period, as surface water run-off will need to be monitored and maintained for the full operational period. Ensure the LEMP, Construction Management Framework Plan and phase specific CEMPs are secured by appropriate means. Ensure a Silt Management Plan is included within the phase specific CEMPs where applicable. Ensure the SuDS are secured for monitoring and maintenance for the full operational period of the MCO project. We recommend the CIRIA SuDS Manual is referenced in regard to the installation and ongoing maintenance of the SuDS features within these plans. |  | n/a | Amber | No update. | Amber | No update. Awaiting further discussion on SuDS protection at designated sites within the MCO. | Amber
n/a | NE5 | Mitigation Measures - LNRS | C, O | Yellow | n/a | n/a | n/a | n/a | n/a | n/a | DCO and MCO Projects As noted above, we welcome the mitigation outlined, including the CEMP, LEMP and Sustainable Drainage Statements. Natural England note that the NN-NPS and North West Leicestershire Local Plan are referenced on policy support for project approaches to biodiversity (DCO 6. 9/MCO 6. 9). As quoted from the NN-NPS, projects should have due regard for LNRS (paragraph 4.30 with further reference in paragraphs 5.51, 5.56, 5.67 and 5.259). The LLR-LNRS has not been included in the review of mitigation to ensure it aligns to the landscape scale initiatives outlined within the LNRS document or mapped measures. These can inform opportunities that contribute to landscape scale nature recovery and are an important tool to co-ordinate projects and deliver for nature at scale. This is supported by national policy. Within the LNRS, it cites the Leicester City Technical Guidance (2021) for urban SuDS design (see UB008 within the LLR-LNRS), which should be referenced in any SuDS designs to ensure they are of high quality and compliant with local policy. As it is referenced in the LNRS, Applicants should have due regard for this guidance document. Ensure the LLR-LNRS is referenced within any biodiversity mitigation, including the individual Environment Management Plans where relevant. | Yellow | No update. | Yellow | No update. | Yellow | No update. | Yellow
NE8(a) | NE6 | Nationally Designated Sites | Assessment of potential air quality impacts (C, O, D) | n/a | It is noted that an assessment of potential impacts to designated sites was omitted from Chapter 9: Ecology & Biodiversity of the PEIR. A placeholder was included within the text which states ‘Section holder awaiting further consultation’ (paras. 9.5.21 and 9.5.37). Consequently, Natural England was unable to provide detailed advice regarding nationally designated sites at this stage. | Amber | In the updated version of the chapter, the traffic modelling and resulting air quality assessment remains outstanding; however, the chapter acknowledges that any increase above 1,000 Annual Average Daily Traffic (AADT) for cars and 200 AADT for heavy goods vehicles on the affected road network within 200m of any SSSI will need to be screened for detailed air quality assessment, which is welcomed. It is also noted that the final assessment of impacts (Table 9.16) cannot be finalised until the air quality data is received. Natural England is unable to comment further regarding possible air quality impacts to nationally designated sites at this stage. | Amber | Overall, further evidence and justification are required to conclude negligible effects to designated sites as there is currently not enough evidence and justification provided. Further information is provided in the rows below. It may be useful to reference 'Natural England’s approach to advising competent authorities on the assessment of road traffic emissions under the Habitats Regulations - NEA001'. Although this document is focussed on European sites, the principles are the same for assessing impacts to SSSIs. | Amber | DCO & MCO Projects Natural England have recently published standard guidance for assessing impacts from air pollution to designated sites from development. This is to ensure consistency in our advice and give the Applicant and Examining Authority clear direction to assess any impacts from air pollution from development to sensitive ecological receptors. See Appendix A for the standard advice. We will not make any further comments on air quality impacts at this time. Review Appendix A for standard guidance on reviewing impacts from air pollution from development. No further comments from Natural England. | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE8(b) | NE6 | Nationally Designated Sites | Air quality - screening criteria (C, O, D) | n/a | n/a (not provided) | Amber | n/a (not provided) | Amber | The screening criteria used, i.e. sites within 200m from the affected road network with increases of more than 1000 AADT and/or 200 HDV, is acceptable for assessment of impacts to sites from air pollution. | Green | as above | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE8(c) | NE6 | Nationally Designated Sites | Air quality - in-combination effects (C, O, D) | n/a | n/a (not provided) | Amber | n/a (not provided) | Amber | Where a proposal is below the screening threshold alone (i.e. <1000 AADT or <1% depending on information available), assessment must be considered to apply the same screening threshold ‘in-combination’. Therefore, sites that were not reviewed for impacts alone due to them being under the thresholds, should be reviewed for any potential in-combination impacts with other projects. Where a project has been screened in and the Project considers that the risk of residual effects remain which are appreciable (i.e. not inconsequential) but no longer adverse in their own right, then a further in-combination assessment of these residual effects would be required at this stage to check for a combined adverse effect. | Amber | as above | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE8(d) | NE6 | Nationally Designated Sites | Air quality - Oakley Wood SSSI (C, O, D) | n/a | n/a (not provided) | Amber | n/a (not provided) | Amber | Oakley Wood SSSI is noted as exceeding >1% of its ammonia critical level from the Project (9.5.67). Impacts are concluded to be negligible due to the setting, unfavourable condition and limited extent of significant reductions in air quality (9.5.68). a. The setting – NE assumes this is based on the proximity to the M1 and the presence of a tree belt. The site is within the 200m and so the setting requires further assessment as designated features could be exposed to emissions. The presence of the tree belt is noted as not being included within the modelling. Without seeing the modelling report, we are unable to confirm this, and it is difficult for NE to comment on this point with certainty. It may be that the tree belt is providing buffering and so could be justified as reducing impacts. However, we are unable to confirm this without seeing the modelling. It would also be useful to understand background trends as an impact reducing / increasing from the M1. b. The unfavourable condition of the woodland – this often gets used as a justification for not considering the AQ impacts from a project, as unfavourable condition is usually noted as being due to land management or other non-AQ related factors. However, it is noted in the chapter (9.5.68) that nitrogen pollution can exacerbate the issues the site is facing and the features at the SSSI are sensitive to nitrogen pollution. APIS shows that the site is almost double its critical load for nitrogen deposition, but within its critical level for ammonia. So, any addition of nitrogen would be harmful to the site. NE cannot accept this as an argument as unfavourable condition is not a justification to rule out impacts. NE’s role is to protect sites and ensure they are able to recover to good condition. c. The extremely limited extent of significant reductions in air quality – The model demonstrates process contribution as exceeding >1% of its critical level from the Project. There is a risk of a significant effect on air quality alone. As such NE would not accept “limited extent of significant reductions in AQ” without seeing the impacts of the tree belt demonstrated as bringing the impact below a 1% process contribution. This statement should be clarified further. | Amber | as above | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE8(e) | NE6 | Nationally Designated Sites | Air quality - Breedon Cloud Wood & Quarry SSSI (C, O, D) | n/a | n/a (not provided) | Amber | n/a (not provided) | Amber | Breedon Cloud Wood and Quarry SSSI is noted as exceeding >1% of its acid critical level from the Project (9.5.69). Impacts are concluded to be negligible due to the woodland buffering itself. This is not an acceptable justification and the assessment should be amended. The woodland is the designated feature and any impacts to designated features where the process contribution exceeds 1% of the critical levels/ loads need to be assessed as significant. See Designated Sites View for the citation and features. | Amber | as above | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE8(f) | NE6 | Nationally Designated Sites | Air quality - Lount Meadows SSSI (C, O, D) | n/a | n/a (not provided) | Amber | n/a (not provided) | Amber | Lount Meadows SSSI is noted as exceeding >1% of its NOx critical level from the Project, exceeding 1% of the NH3 critical level from the Project and exceeding 1% of the nitrogen critical load from the Project (9.5.93). It is noted that the features of the SSSI are sensitive to changes in the levels of these pollutants. Impacts are argued to be negligible (9.5.94) due to unfavourable condition and the reduction of impacts from an existing tree belt. a. The unfavourable condition of the woodland – Comments as per those given for Oakley Wood SSSI. We cannot accept this as an argument as unfavourable condition is not a justification to rule out impacts and the assessment should be amended. NE’s role is to protect sites and ensure they are able to recover to good condition. b. The extremely limited extent of significant reductions in air quality – The model demonstrates process contribution as exceeding >1% of its critical levels/loads from the Project. There is a risk of a significant effect on air quality alone. As such, NE would not accept “limited extent of significant reductions in AQ” without seeing the impacts of the tree belt demonstrated as bringing the impact below a 1% process contribution. This information is requested. | Amber | as above | n/a | n/a | n/a | n/a | n/a | n/a | n/a
NE12 | NE7 | Protected Species | Approach to licencing (C, O, D) | Green | Natural England generally welcome the approach taken to avoid impacts to protected species, in line with the mitigation hierarchy. Natural England has reviewed draft mitigation licences for bats and European badger and Letters of No Impediment (LoNIs) (with caveats) have been provided for these species. This confirms that we consider there to be no reason that a licence would not be granted post DCO consent, subject to the caveats being noted and addressed. | Green | No change. | Green | No change. | Green | DCO and MCO Projects Full comments on the submitted ES will be provided with our Written Representations. | tbc | Query from Applicant on species licences (email 27/02/26): We were hoping you could expand on the statements around species licencing where bat and badger comments state that a licence would be issued subject to the standard conditions. There was some discussions, as to whether this referred to the licence conditions themselves, or the conditions to required for a licence to be granted. Could this be expanded on for clarity. NE Response (email 02/03/26): The project should have regard to both. In our response to the PEIR, we noted: 4.2. Regarding protected species, Natural England has worked with the Applicant through our Discretionary Advice Service, including reviewing draft mitigation licences for bats (common pipistrelle Pipistrellus pipistrellus) and European badger (Meles meles). Letters of No Impediment (LoNIs) (with caveats) have been provided for these species. This confirms that we consider there to be no reason that a licence would not be granted post DCO consent, subject to the caveats being noted and addressed. So for the licences to be granted post consent, the caveats would need to be addressed. I have also looked on the Wildlife licences guidance and it notes that conditions written into licences must be followed. So to answer your query, conditions within a licence need to be followed and caveats noted in the LONI should be satisfied to enable the granting of the licence. | Green | n/a | n/a | n/a | n/a
| NE8 | Protected Species | DLL (C,O) | Green | In addition, Natural England’s District Level Licensing (DLL) team has provided advice regarding Great Crested Newts (GCN) and an Impact Assessment and Conservation Payment Certificate (IACPC) has been prepared. As set out in PINS Advice Note 11: Annex C1 , ‘By demonstrating that the DLL scheme for GCN will be used, consideration of GCN in the ES can be restricted to cross-referring to the Natural England (or alternative provider) IACPC as a justification as to why significant effects on GCN populations as a result of the Proposed Development would be avoided.’ Natural England have no further comment with regard to GCN at this stage. It should also be noted that Natural England are unable to comment on the need for any additional licence(s), as this responsibility falls to the developer. It is recommended that the Applicant reconsults with Natural England should there be any changes to protected species licence requirements. Our protected species standing advice can be consulted. | Green | n/a | n/a | n/a | n/a | DCO Project The site in question currently holds a countersigned DLL IACPC which forms a commitment to enter the scheme. The applicant has paid a First Stage Payment (FSP), which is approximately 30% of the total DLL Conservation Payment (CP) required to fully compensate for their impacts on GCN. The FSP is used to fund compensation ponds in the landscape in advance of impacts. We would be expecting a licence application to be made upon DCO approval, which would trigger the need for the applicant to pay the remainder of the CP outlined in their IACPC. | Green | n/a | n/a | n/a | n/a | n/a | n/a
NE20 | NE9 | Biodiversity Net Gain | Draft BNG Report (C, O, D) | N/A (not yet mandatory for NSIPs) | Natural England welcomes the use of the Statutory Biodiversity Metric for the preliminary Biodiversity Net Gain (BNG) calculations. The Draft BNG Report (February 2025) (Appendix 9i) shows that the on-site proposals deliver a 13.31% area based habitat gain, a 19.75% hedgerow gain and a 27.22% watercourse gain (noting that the watercourse element is yet to be finalised). Nationally Significant Infrastructure Projects (NSIPs) are not yet subject to mandatory BNG requirements; however, the figures presented are above the minimum 10% net gain requirement which is mandatory for most Town and Country Planning Act applications, and this is welcomed by Natural England. A commitment should be made within the DCO to the delivery of Biodiversity Net Gain; where shown to be feasible, Natural England would welcome commitment in excess of 10%. | N/A (not yet mandatory for NSIPs) | The updated BNG Report submitted as part of the non-statutory consultation does not state the biodiversity units or percentages that will be gained or lost. Paragraph 6.1 states "The following section is a placeholder for the final results. And will be updated once the scheme's proposals and site boundary have been finalised ahead of the formal submission". It appears that a net gain in excess of 10% is still anticipated for area-based habitat, hedgerows and watercourses; this should be confirmed when the updated figures are available. In line with our original comment, NSIPs are not yet subject to mandatory BNG requirements; however, achieving the minimum 10% net gain requirement which is mandatory for most Town and Country Planning Act applications would be welcomed by Natural England. A commitment should be made within the DCO to the delivery of Biodiversity Net Gain; where shown to be feasible, Natural England would welcome commitment in excess of 10%. | N/A (not yet mandatory for NSIPs) | [To be reviewed] | N/A (not yet mandatory for NSIPs) | DCO and MCO Projects Natural England welcomes the use of the Statutory Biodiversity Metric for the Biodiversity Net Gain (BNG) calculations (DCO 6.9I/MCO 6.9I). The BNG Report shows that the on-site proposals deliver a 16.32% area-based habitat gain, a 20.27% hedgerow gain and a 23.54% Watercourse gain. NSIPs are not yet subject to mandatory BNG requirements; however, the figures presented are above the minimum 10% net gain requirement which is mandatory for most Town and Country Planning Act applications, and this is welcomed by Natural England. We welcome reference to the LLR-LNRS within the Report. Gains can be secured through planning obligations, conservation covenants or requirements within the DCO. Natural England would welcome a commitment in excess of 10%. | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | NE10 | Soils and Best and Most Versatile Agricultural Land | (C, O) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations. | tbc | no update | tbc | Comments provided under comments NE14 - 23. | n/a | n/a | n/a
NE21 | NE11 | Ancient Woodland and Ancient / Veteran Trees | Consideration of March Covert ancient woodland (C, O, D) | n/a | The Scheme comprises highway works within 200m of an area of ancient woodland, March Covert. Due to the proximity of the ancient woodland and the nature of the Scheme, there is the potential for air quality impacts to occur. Therefore, the ES should assess the impacts of the proposal on any ancient woodland and ancient and veteran trees, and the scope to avoid and mitigate for adverse impacts. It should also consider opportunities for enhancement.There is no specific reference to potential impacts on March Covert ancient woodland within Chapter 9: Ecology and Biodiversity of the PEIR. Natural England requests that this topic is explored in sufficient detail within the ES. | Amber | No change. | Amber | It is noted that there will be no direct loss to Ancient Woodland or Ancient and Veteran Trees as a result of the development. As a result, NE have no specific comment to make in this regard and refer to our Standing Advice for Ancient Woodland, Ancient Trees and Veteran trees (1). | Green | DCO & MCO Projects Natural England have no comments further to our standing advice: Ancient woodland, ancient trees and veteran trees: advice for making planning decisions - GOV.UK | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | NE12 | Connecting People with Nature | Green Infrastructure (O) | Green | n/a | n/a | n/a | n/a | n/a | n/a | DCO & MCO Projects Natural England welcome the retained, enhanced and new blue-green infrastructure features, including the community park, SuDS, habitat creation, increased connectivity and additional PROWs (DCO project) and retained habitats, new green spaces, habitat connectivity and SuDS (MCO Project) DCO 6. 9/MCO 6. 9). We acknowledge the mix of habitats and plans for both people and nature. We note that the LLR-LNRS has not been referenced in the design of the retained, enhanced and new habitats. As discussed in NE5 the LNRS is an important tool for landscape scale nature recovery and referenced within policy NN-NPS. As such it should be given due regard. We would also direct the Applicant to our Green Infrastructure Framework, which includes a Design Guide. Referencing these in the designs will demonstrate good practice and high standards including the use of the Urban Greening Factor and Green Flag Criteria. We welcome the outlined actions within the LEMP to install, monitor and maintain the green infrastructure. We welcome the intention for early establishment. In regard to the Bioswale and SuDS features outlined in the LEMP, the CIRIA SuDS Manual should be referenced for establishment and ongoing monitoring and maintenance. Ensure the LEMP, CEMP and phase specific CEMP are secured by requirement within the DCO and by appropriate means for the MCO. We recommend the CIRIA SuDS Manual is referenced in regard to the installation and ongoing maintenance of the SuDS features within these plans. We would welcome reference to the LLR-LNRS in the design and implementation of the retained and enhanced habitats. We recommend referencing the Natural England Green Infrastructure Framework in the design development of the green infrastructure. | Green | n/a | n/a | n/a | n/a | n/a | n/a
NE22 | NE13 | Connecting People with Nature | PRoW (O) | Green | The ES should consider potential impacts on access land, common land, public rights of way and, where appropriate, the England Coast Path and coastal access routes and coastal margin in the vicinity of the development, in line with NPPF paragraph 104 and NNNPS paragraphs 5.193 & 5.198. It should assess the scope to mitigate for any adverse impacts. Rights of Way Improvement Plans (ROWIP) can be used to identify public rights of way within or adjacent to the proposed site that should be maintained or enhanced. Chapter 6: Traffic and Transportation of the PEIR sets out a number of active travel and public transport improvements associated with the Scheme, including new public footpaths, cycle tracks, a new toucan crossing and improvements to PRoW L57. These measures are welcomed by Natural England. Consideration of the proposed Isley Woodhouse settlement in the emerging North West Leicestershire Local Plan, as referenced in Chapter 6 of the PEIR, is also welcomed. Natural England’s Green Infrastructure Framework may be a useful resource to ensure the opportunities to connect people with nature are taken advantage of. | Green | No change. | Green | No change. | Green | DCO Project Natural England welcome the additional access opportunities to connect the local community to nature, including enhancements to the existing PRoW at Hyam’s Lane and the additional proposed paths, connecting the existing network and community park (DCO 6. 9/MCO 6. 9). We welcome the management of existing PRoWs through the construction phase via the CEMP with all permanent routes to be completed as soon as practicable. There may be further opportunities for connectivity between the DCO project and the Isley Woodhouse development project to increase connectivity for both people and nature connecting up the access routes and green infrastructure, such as via any PRoW and Sustrans routes. Ensure the LEMP and CEMP are secured by requirement in the DCO. Review any connectivity opportunities between the DCO project with the Isley Woodhouse development project. | Green | n/a | Green | n/a | Green | n/a | n/a
NE13 | NE14 (WR) | Soils and Best and Most Versatile Agricultural Land | ALC Report (C, O, D) | Yellow | Through our DAS service, Natural England has provided comments (02 December 2024) on an earlier iteration of the Soils and Agricultural Land Quality report (06 March 2023). An updated version of the report (14 February 2025) has been provided along with a summary of the consultant’s responses to Natural England’s comments. Natural England has reviewed the updated ALC survey report (Appendix 15a) in combination with the consultant clarification document and the presented methodology appears reasonably robust, following the MAFF (1988) Agricultural Land Classification for England and Wales: Guidelines and Criteria for Grading the Quality of Agricultural Land. Natural England has no further concerns regarding the validity of this survey. | Green | No change. | Green | No change. | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | Natural England have provided advice to the Applicant on the Agricultual Land Classification (ALC) Report through our Discretionary Advice Service since November 2024. Following consultation in March 2025, Natural England reviewed the updated ALC survey report in combination with the consultant clarification document and the presented methodology appears reasonably robust, following the MAFF (1988) Agricultural Land Classification for England and Wales: Guidelines and Criteria for Grading the Quality of Agricultural Land. Natural England has no further concerns regarding the validity of this survey. NE have provided previous comments on the ALC Survey during pre-app, which should ideally be addressed to ensure the baseline presented in the ALC report is as robust as possible, however, remain satisfied that the report constitutes a record of the pre-working ALC grading and physical characteristics of the land within the application site boundary. NE’s comments have been included below Table 1 in Annex A of our Written Reps response for reference. Ensure NE’s previous comments are addressed, and any remaining clarifications or deficiencies resolved, before the survey can be accepted as a valid baseline. | Yellow | 12/06 Email: FCPR have acknowledged the comments. No further update. | Yellow
NE14 | NE15 (WR) | Soils and Best and Most Versatile Agricultural Land | Policy and guidance (C, O, D) | Green | Natural England support the use of Technical Information Note 049, as referenced in para. 15.2.1 of Chapter 15: Agriculture and Soils. Standard EIA methodology as presented in DMRB LA109, the ICE EIA Handbook and the IEMA 'A New Perspective on Land and Soil in Environmental Impact Assessment’ should be followed. The ES and associated Soil Management Plan (SMP) needs to clearly demonstrate how the Agricultural Land Classification (ALC) Grades and soil types will inform soil handling and restoration, setting out the site specific mitigation measures with reference to the best practice guidance (Defra Construction Code of Practice), i.e. secondary mitigation measures. The British Society of Soil Science has published the Guidance Note Benefitting from Soil Management in Development and Construction which also contains useful guidance. | Amber | The following guidance is now referenced in para. 15.2.1 which is welcomed: DMRB LA109; The ICE EIA Handbook; and IEMA 'A New Perspective on Land and Soil in Environmental Impact Assessment’; the LCRM (Environment Agency, 2023); and Agricultural Land Classification: Protecting the Best and Most Versatile Agricultural Land Technical Information Note TIN049 (Natural England, 2012). However, there are multiple instances where the proposed methodology does not follow to the aforementioned guidance. Refer to comments S42-15, S42-16 and S42-17 for further information and recommended actions. | Amber | NE are satiisfied that the relevant guidance has now been followed appropriately. See Ref NE15, NE16 and NE17 in this document for further comment. | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | Natural England have provided advice to the Applicant on the application of policy & guidance in assessment of impacts through our Discretionary Advice Service since March 2025. Following consultation in August 2025, NE are satisfied that the relevant guidance has now been followed appropriately. See NE16, -17 and -18 below. | Green | n/a | n/a
NE15 | NE16 (WR) | Soils and Best and Most Versatile Agricultural Land | Magnitude of impact (C, O, D) | Green | With regards to para. 15.2.11, Natural England do not agree that losses of less than 20ha of BMV agricultural land should be considered a minor effect. Magnitude of impact should follow the aforementioned IEMA guidelines for identifying impact on soil resources and soil function (Table 3, page 49). The magnitude table proposed for the Scheme (Table 15.3) presents area thresholds substantially greater than those presented in the ICE (2019) EIA handbook and IEMA guidelines (2022). The scale of magnitude considered should be in line with the thresholds presented in the ICE (2019) EIA handbook and IEMA guidelines (2022): - Major Magnitude: Permanent loss of >20ha BMV land - Moderate Magnitude: Permanent loss of >5ha <20ha BMV land - Minor Magnitude: Permanent loss of >5ha BMV land | Red | The updated chapter still states that losses of less than 20ha of BMV agricultural should be considered a minor effect, which Natural England does not agree with. Therefore, our original comment still stands. The scale of magnitude considered should be in line with the thresholds presented in the ICE (2019) EIA handbook and IEMA guidelines (2022): - Major Magnitude: Permanent loss of >20ha BMV land - Moderate Magnitude: Permanent loss of >5ha <20ha BMV land - Minor Magnitude: Permanent loss of >5ha BMV land | Red | The Magnitude criteria used within the Agriculture and Soils Chapter have been updated in line with IEMA guidance as per NE advice (table 15.6). | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | The Magnitude criteria used within the Agriculture and Soils Chapter have been updated in line with IEMA guidance as per NE advice (table 15.6). | Green | n/a | n/a
NE16 | NE17 (WR) | Soils and Best and Most Versatile Agricultural Land | Sensitivity classification (C, O, D) | Green | The Sensitivity/ Value Criteria table (Table 15.2) presents sensitivities attributed to different ALC grades. The table includes grades 1 and 2 as high sensitivity, and grade 3a as medium. Natural England advise that grade 3a land should be attributed high sensitivity, and Grades 1 and 2 should be attributed very high sensitivity, in line with the IEMA Guidelines (2022) (Table 2, page 48). | Red | Para. 15.2.3.ii states that Subgrade 3a land can either be afforded moderate or high sensitivity based on the evaluation of its availability in the locality of the site. Natural England does not agree with this statement. By downgrading the sensitivity of Grade 3a agricultural land where it is locally abundant, this approach risks undermining national planning policy and the strategic protection of BMV land. Grade 3a is explicitly recognised as BMV and holds intrinsic value for food production, soil quality, and long-term sustainability. Sensitivity should reflect the land’s inherent characteristics and national importance not its relative scarcity in a given area. Downgrading based on prevalence ignores cumulative impacts and sets a precedent that could erode protections for high-quality soils across the country. Natural England therefore dispute the assertion that abundance justifies reduced sensitivity and recommends that assessments maintain a consistent, policy-aligned approach to BMV land classification. In line with our earlier comment, Natural England advises that grade 3a land should be attributed high sensitivity, and Grades 1 and 2 should be attributed very high sensitivity, in line with the IEMA Guidelines (2022) (Table 2, page 48). | Red | The Sensitivty criteria used within the Agriculture and Soils Chapter have been updated in line with IEMA guidance as per NE advice (table 15.5). | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | The Sensitivity criteria used within the Agriculture and Soils Chapter have been updated in line with IEMA guidance as per NE advice (table 15.5). | Green | n/a | n/a
NE17 | NE18 (WR) | Soils and Best and Most Versatile Agricultural Land | Assessment methodology (C, O, D) | Green | In para. 5.2.16 (Limitations and Assumptions) of Chapter 15, it is noted that ‘there is no one widely accepted assessment criteria’ for impacts on agricultural land resources (i.e. BMV) or soil resources, and therefore the assessment methodology has been developed in-house by the author of the chapter. Natural England refute this statement and would like to point the Applicant to the published approaches listed above (e.g. DMRB LA109, the ICE EIA Handbook and the IEMA 'A New Perspective on Land and Soil in Environmental Impact Assessment’). Natural England does not agree with the approach taken within Chapter 15: Agriculture and Soils and request that the methodology is amended in line with our advice and published guidelines. | Red | The following guidance is now referenced in para. 15.2.1 which is welcomed: DMRB LA109; The ICE EIA Handbook; and IEMA 'A New Perspective on Land and Soil in Environmental Impact Assessment’; the LCRM (Environment Agency, 2023); and Agricultural Land Classification: Protecting the Best and Most Versatile Agricultural Land Technical Information Note TIN049 (Natural England, 2012). However, there are multiple instances where the proposed methodology does not follow to the aforementioned guidance, e.g. sensitivity classification of grade 3a land and the scale of magnitude thresholds. In Table 15.2 [labelled as 15.1, potential typo], the Applicant states that "The methodology is robust and finds the loss of 20 ha of BMV land to be significant which is consistent with the IEMA guidelines. The only difference in methodology used is in relation to the magnitudes for the loss of 3b land". Natural England dispute this statement as there are various instances where the methodology is not in line with published guidance in relation to BMV land (grades 1-3a), e.g. the sensitivity classification of grade 3a land and the scale of magnitude thresholds. Para 15.2.22 states that: "Impact magnitudes for loss of best and most versatile land relates to consultation thresholds in Technical Information Note 049 (TIN049), published by Natural England to provide general guidance". Natural England notes that, whilst TIN049 states that consultations are required on applications with loss of 20 ha or more BMV agricultural land, it does not state this consultation threshold should be interpreted in relation to significance of effect. Natural England's original comment still stands and we request that the methodology is amended in line with our advice and published guidelines. | Red | The Methodology for assessing impacts to Agricultural Land and Soils has been amended in line with our comments (Agriculture and Soils Chapter, Table 15.4 & throughout). As a result, the permanent loss of BMV land now been assessed as a significant major adverse effect arising from the EMG2 Works. Where appropriate steps have been taken to first avoid BMV land where possible, then to manage and re-use the soil resource appropriately, NE would not raise significant concerns regarding the loss of BMV land. Nonetheless, PINS will still need to consider the permanent significant major adverse effect in the decision-making process. At this stage, NE have not reviewed all of the ES submission material; as such, our comments on avoidance of BMV and soil management/re-use are limited to the below (in summary): The draft Agriculture and Soils Chapter makes little reference to the avoidance of BMV land, although it is noted this this information may be contained in separate ES chapters. The draft Soil Management Plan and ALC survey report include consideration of soil management and re-use, which is welcomed. | Amber | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | DCO 6.15 Environmental Statement Chapter 15 Agriculture and Soils The Methodology for assessing impacts to Agricultural Land and Soils has been amended in line with our comments given to the Applicant March to August 2025 (Agriculture and Soils Chapter, Table 15.4 & throughout). As a result, the permanent loss of ‘best and most versatile’ (BMV) land now been assessed as a significant major adverse effect arising from the EMG2 Works. Where appropriate steps have been taken to first avoid BMV land where possible, then to manage and re-use the soil resource appropriately, in line with National Networks National Policy Statement (NNNPS) paragraphs 5.189, 5.190 & 5.202, NE would not raise any further concerns regarding the loss of BMV land. Nonetheless, PINS and the Secretary of State will still need to consider this permanent significant major adverse effect in the decision-making process Ensure methodology is clear on steps taken to avoid impacts to BMV agricultural land in the first instance for clarity to inform decision makers. | Green | n/a | n/a
NE18 | NE19 (WR) | Soils and Best and Most Versatile Agricultural Land | Cumulative effects (C, O, D) | Green | The cumulative impacts section of Chapter 15 (para. 15.8.1) states that soil and agricultural land are finite resources and loss from an individual site should be considered on a site-by-site basis, against the benefits of the scheme. In this instance, it is concluded that there are no relevant cumulative inter-project effects of the Scheme. Natural England disagrees with this statement and rationale. BMV agricultural land is a national dataset and therefore cumulative impacts should be considered against the national BMV figure. Cumulative effects should be considered as part of robust assessment of effects on soils and agricultural land, as noted in para 4.12 of the National Networks NPS. The IEMA guidance (A New Perspective on Land and Soils in EIA (February 2022)) is described as a “work in practice”, and as such it has no formal standing. However, this guidance is recognised by Natural England, and it sets out parameters for the assessment of cumulative impacts, based on some current informal practice. | Red | Natural England concur with the approach taken to assessing cumulative impacts on soils, recognising that, while there is currently no formally prescribed methodology, the consideration of cumulative effects remains essential to understanding long-term soil degradation and land use pressures. The guidance supports a pragmatic, evidence-led approach that draws on best available data, professional judgement, and contextual analysis to evaluate how multiple developments may collectively affect soil function, quality, and resilience. This alignment reinforces the importance of integrating soil conservation into strategic planning, even in the absence of a standardised framework. The RAG status has been updated to green. | Green | No change. | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | DCO 6.21 Environmental Statement Chapter 21 Cumulative Impacts Natural England concur with the approach taken to assessing cumulative impacts on soils, recognising that, while there is currently no formally prescribed methodology, the consideration of cumulative effects remains essential to understanding long-term soil degradation and land use pressures. The guidance supports a pragmatic, evidence-led approach that draws on best available data, professional judgement, and contextual analysis to evaluate how multiple developments may collectively affect soil function, quality, and resilience. This alignment reinforces the importance of integrating soil conservation into strategic planning, even in the absence of a standardised framework. | Green | n/a | n/a
NE19 | NE20 (WR) | Soils and Best and Most Versatile Agricultural Land | Soil Management Plan (C, O, D) | Amber | Natural England support the provision of a site-specific Soil Management Plan (SMP), as referenced in para. 15.5.4. The Soil Management Plan and Peat Management Plan (based on a soil resource survey) should include the following: a) A detailed specification of the top and subsoil types existing on site informed through a detailed soil resource survey; b) A site working strategy and soil balance, including the type and volume of each soil type to be stripped and stockpiled, and the location of soil storage; c) How site master-planning and layout/design demonstrates best use of the available soils; d) Habitat specification/design based on topsoil and subsoil types; e) Soil protection, stripping, storage, handling, amelioration and placement to ensure it is fit for purpose and minimises adverse impacts on ecosystem service provision; f) Restoration or reinstatement specification (where applicable); g) An aftercare plan (where applicable). | Green | In the updated chapter, the Soils Management Plan (SMP) is no longer listed as a supporting appendix. Natural England requests clarification on whether the SMP will accompany the DCO application. | Amber | From communications with the applicant, and upon receipt of the draft SMP, NE assume the SMP will accompany the DCO application. At this stage, NE have not made detailed comments on the draft SMP; may provide further comment on it's content in our representations to the Planning Inspectorate following review of the full suite of application documents. | Green | DCO & MCO Projects Full comments on the submitted ES will be provided with our Written Representations | tbc | n/a | tbc | DCO 6.15C Environmental Statement Appendix C Soil Management Plan Paragraph 4.2 We welcome use of the Defra Construction Code of Practice for the Sustainable Use of Soils on Construction Sites (2009) to guide soil management during construction. However, no commitment has been made to restore temporarily disturbed land to it’s current ALC grade and condition. Include a commitment for BMV agricultural land temporality required for the development to be returned to its original ALC grade in the Soil Management Plan. Where soils are being returned to agricultural use there should be a specific commitment for BMV agricultural land temporily required for the development to be returned to its original ALC grade. This includes areas such as field scale ecological mitigation areas and borrow pits where reinstatement to the physical characteristics of BMV quality may also be required. To reduce the incidence of anaerobic conditions developing below the normal cultivation depth, no replaced topsoils should be more than 40cm deep. | Amber | No update. Awaiting further discussion on soil management. | Amber
| NE21 (WR) | Soils and Best and Most Versatile Agricultural Land | Soil Management Plan (C, O, D) | Amber | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | DCO 6.15C Environmental Statement Appendix C Soil Management Plan Paragraph 4.5 Soil handling should normally be avoided during October to March inclusive, irrespective of soil moisture conditions, because it will generally not be possible to establish green cover over winter to help dry out soils and protect them from erosion. Soils should only be handled in a dry and friable condition. A field suitable method for assessing whether soils are in a dry and friable condition based on plastic limits is set out in Part One (Explanatory Note 4 – Table 4.2) of the Institute of Quarrying’s Good Practice Guide for Handling Soils in Mineral Working, and this approach together with the associated rainfall protocols should be adopted. It is important where these judgements are being made that there is a high level of supervision by a suitably qualified soils scientist form part of the mitigation. Include commitment to avoid working soils October – March where possible in the Soil Management Plan. Ensure soils are only worked when dry and friable, referencing guidance on field tests in the Soil Management Plan. Ensure judgements on suitable working conditions are made by suitably qualified soils scientist areincluded in the Soil Management Plan. | Amber | No update. Awaiting further discussion on soil management. | Amber
| NE22 (WR) | Soils and Best and Most Versatile Agricultural Land | Soil Management Plan (C, O, D) | Yellow | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | DCO 6.15C Environmental Statement Appendix C Soil Management Plan Paragraph 4.6 The cited reference in this paragraph does not work. Paragraph 4.8 Natural England has provided comments on the ALC survey report (2098/1). These should be addressed, and any remaining clarifications or deficiencies resolved (see NE14). Paragraph 4.9 The 2000 MAFF guidance has now been superseded by the Good Practice Guide for Handling by the Institute of Quarrying (2021), link above para 4.5. Ensure all guidance cited is up to date and all linked references are working in the ES. Ensure all NE’s comments on the ALC Survey are addressed (see NE14). | Yellow | No update. Awaiting further discussion on soil management. | Yellow
| NE23 (WR) | Soils and Best and Most Versatile Agricultural Land | Soil Management Plan (C, O, D) | Amber | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Additional information, refinement, or commitments are required to ensure that soil resources are adequately protected throughout construction and, where applicable, restored following temporary works. In such cases, Natural England would expect the Soil Management Plan to be strengthened and appropriately secured as part of the DCO to ensure deliverability and long-term soil protection. Natural England advise the following details should be included to strengthen the SMP: • Soil management should be consistent across all documents. Much of the Applicant’s commitments for soil handling / stockpiling are addressed in Appendix 15A Soils and Agricultural Land Quality Report (Document DCO 6.15A/MCO 6.15A) but do not appear in Appendix 15C (Document DCO 6.15C/MCO 6.15C). • A soil budget should be provided, this should include schedules of volumes for each soil type in situ; the volumes to be stored; the volumes to be reinstated and a soil surplus or deficit identified. • There is no information provided on location of stockpiles and whether the there is sufficient space on site to accommodate soil required for reinstatement purposes. This could include but not limited to maps showing the areas to be stripped and left in-situ; phasing plans; stockpile locations. Detail on Soil reuse: Destination and use of each soil resource (topsoil, subsoil, imported soils) should be included. • Information on erosion and runoff control (silt fencing, buffer zones); Pollution prevention measures. • Site inspection regime (before, during and after soil operations). Record keeping: dates, conditions, volumes, deviation notes. Compliance with planning conditions (e.g., biodiversity net gain, tree protection). • A soil aftercare programme should be secured for all retained and reinstated areas, with defined monitoring (e.g. quarterly in year one and biannually thereafter for a minimum of five years) to assess settlement, compaction, drainage and vegetation establishment. Maintenance should include aeration or subsoiling, organic matter incorporation, reseeding and trafficking control. Clear remedial triggers must be set, with measures such as regrading, decompaction, soil amelioration and replacement planting implemented as necessary to ensure soils achieve a stable condition appropriate to their intended use. | Amber | No update. Awaiting further discussion on soil management. | Amber
| NE24 (WR) | Protected Species | Badger Survey (C, O) | Green | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Updated badger surveys will be required post-consent within the 6 months prior to a formal licence application being submitted to Natural England. The date of the most recent survey and the results must be detailed in the Method Statement document that will be submitted as part of the licence application. | Green | n/a | n/a
| NE25 (WR) | Protected Species | Badger Impacts (C, O) | Yellow | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | The Badger Report details that SUDS areas will be created within 30m of sett S2 and within 20m of setts S3 and S4. This information was not included in the Method Statement document previously submitted to Natural England for this scheme. Natural England have concerns about the proximity of the SUDS basins to the retained setts and recommend amending the design so that the SUDS areas are located at least 30m away from all badger setts. If all other locations for the SUDS area are unsuitable, Natural England will require further details in order to be satisfied that the setts will not be damaged during the construction of the SUDS areas and that there will be no risk of the setts flooding if the SUDS basins were to overflow. Maps/figures showing the locations of the SUDS basins in relation to the sett entrances should also be provided, with 10m, 20m and 30m buffer zones around the sett entrances and the directions of sett tunnels shown. The Badger Report also states that a public footpath will be created within 20m of setts S2, S3 and S4, which was not detailed in the Method Statement document previously reviewed by Natural England. We recommend considering amending the location of the footpath so that it is located at least 30m away from each sett. If alternative routes are not feasible, we recommend planting vegetation between the footpath and the setts to shield the setts. Furthermore, details should be provided in the Method Statement document to satisfy Natural England that the setts will not be damaged during the construction of the footpath. Sections 5.5 and 5.9 – 5.11 of the Badger Report detail that some machinery will be used within 30m of setts S1 – S4 to adjust the site levels and construct green infrastructure in the Community Park. The type of machinery that will be used and the distance from the setts will need to be detailed in the Method Statement document. NE will require an updated license application with the following being addressed: Ensure details and justification of the SuDS in relation to the badger setts are presented to Natural England for review and comment. This should include maps with buffer zones. This should include maps with buffer zones and details of contruction methods. Ensure details and justification of the footpaths in relation to the badger setts are presented to Natural England for review and comment. This should include maps with buffer zones and details of contruction methods. Ensure any construction machinery methods for the community park impacting badger setts are detailed in the Method Statement. | Yellow | Email 30/04: FCPR provided updated badger method statement for review following NE comments. Email 08/06: NE provided further comments on the badger method statement, noting information is outstanding on the construction machinery, SuDS and new footpath in relation to badger setts. NE also provided further clarity on the need for a new full application for a Letter of No Impediment. From the information submitted to date, the NEWLS team believe it is possible NE could issue a LONI with caveats at this stage, depending on the additional information provided in the application form. It would be preferred that concerns are addressed regarding the location of the footpath and SuDs pond prior. Awaiting response from Applicant. Email 12/06: FCPR note the below in regards to SuDS. NE suggest this information to be included in the resubmitted LONI application. 1. SuDS location To drain effectively under gravity and thus operate as a sustainable drainage system the SuDS need to be located below the proposed development parcels at an elevation that will allow appropriate gradients to be used on the connecting pipe runs. This requires them to be located along the western boundary to serve the development to the north of Hyam’s Lane, and the south-western and southern boundary to serve the development to the south of Hyam’s Lane. Locating the SuDS features on the low-lying boundaries also allows any exceedance flows from the development to be captured before leaving the site, in accordance with best practice. 2. Flooding of setts. The setts are adjacent to the Hall Brook and are subject to existing flood risks. The Hall Brook is too small to have been mapped by the EA, but LCC LLFA have a model of the area which has informed the FRA. Outputs suggest flood water (which is essentially the outflow from the airport) is largely contained within bank, though there will be some shallow overland flows from the existing site entering the channel from the east. As the SuDS scheme intercepts the contributing flood water runoff from the site, helping to lower peak flood levels in the brook, this would reduce the risk of the setts being flooded out. | Yellow
| NE26 (WR) | Protected Species | Badger Mitigation & Compensation (C, O) | Yellow | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Details of the methods that will be used to monitor setts S5 and S6 to confirm that badgers have not re-entered the setts during the exclusion process must be detailed in the Method Statement document that will be submitted as part of the formal badger licence application. If setts S5 and S6 cannot be destroyed immediately following a successful exclusion period, then they must be destroyed before the expiry of the licence to prevent a breach of licence conditions. Natural England recommend providing more details about the landscaping proposals for the Community Park so that we can be satisfied that badgers will have access to sufficient suitable habitats post-development. Section 4.86 of the LEMP details that two new artificial badger setts will be created, which were not discussed in the Badger Report dated August 2025 or in the Method Statement submitted to Natural England in November 2024. If these setts are to be created, details must be provided in the Method Statement document regarding the size of the artificial setts and the materials they will be constructed from. Maps/figures must also be provided showing the locations of the artificial setts. Alternatively, if the setts are not to be created as the main sett will be retained, please ensure that this detail is removed from the LEMP. NE will require an updated license application with the following being addressed: Detail methods that confirm badgers have not re-entered setts S5 and S6 during the exclusion process in the Method Statement with the formal license application. Where setts S5 and S6 cannot be destroyed immediately, they must be destroyed before the expiry of the license. Confirmation is required that badgers will not have access to suitable habitat post-development. Details must be provided in the Method Statement of the two new artificial setts proposed in the LEMP, including maps / figures. | Yellow | Email 30/04: FCPR provided updated badger method statement for review following NE comments. Email 08/06: NE provided further comments on the badger method statement, noting information is outstanding on the mitigation in relation to badger setts S5 and S6. | Yellow
| NE27 (WR) | Protected Species | Badger Maps / Figures (C, O) | Yellow | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Maps/figures should be submitted that show the location of each sett entrance, its status (active, partially active or inactive) and the tunnel directions for all surveyed setts. We recommend providing a figure that shows the final development layout with the current sett locations included to help to evidence why setts S5 and S6 need to be destroyed. It would be helpful to provide a figure that shows the location of the Community Park. NE will require an updated license application with the following being addressed: Provide maps / figures of all sett entrances, status and tunnel directions in relation to the development layout and Community Park. | Yellow | Email 30/04: FCPR provided updated badger method statement for review following NE comments. Email 08/06: NE provided further comments on the badger method statement, noting maps and figures should be updated alongside the requested outstanding information. | Yellow
| NE28 (WR) | Protected Species | Bats | Green | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Bat surveys were completed in 2022 and 2024. The details of the 2022 surveys have not been provided for review, and therefore Natural England cannot comment on their appropriateness. This includes the trees considered unsafe to climb (T13U, T14U and T66C), which were subject to one top up survey during the 2024 surveys, following a full suite of surveys in 2022. This is not considered a significant constraint given it is recognised in the report that surveys should be updated if survey data is older than 12 months. Given the surveys were conducted in 2024, updated surveys would be expected prior to the start of the works. Section 3.11 of the Bat Report indicates that further inspections were conducted on trees if they had potential roosting features and were to be lost under the proposals. Natural England would recommend indirect impact assessment of trees with bat roosting potential is completed prior to the start of the works. The Bat Report details that one common pipistrelle roost has been identified in T21C for which the Letter of No Impediment was issued on the 24th November 2024. No additional roosts have been identified; therefore, an updated Letter of No Impediment is not necessary. In the Ecology chapter, it has been detailed that foraging and commuting impacts may occur if hedgerows are broken for access proposes, with proposed establishment of hop-overs to aid crossing over the breaks. Natural England would recommend these breaks are as small as much as possible, to known distances bats species will cross. NE are satisfied there remains no impediment to a license being granted, subject to the following being addressed: Ensure updated bat surveys are completed within 12 months prior to the start of works. This should include indirect impact assessment. Ensure detail and justification provided for any gaps in hedges for access and in line with known break distances bats can cross. | Yellow | Email 12/06: NE agreed that this has been resolved and can be reviewed post-consent. FCPR confirmed the information will be captured in the CEMP post-consent. | Green
| NE29 (WR) | Protected Species | Water Vole & Otter | Green | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Currently, in addition to the redacted information, insufficient information has been provided in the survey report to comment on the suitability of the surveys with respect to water voles and otters; no specific dates of surveys, survey conditions etc have been provided. Table 9.5.33 of the Ecology Chapter indicates that evidence of otter was detected along Diseworth brook tributary, an offsite location, adjacent to the western boundary. The scheme is proposing enhancement of the riparian zone through additional planting and reduction in land under agricultural use, and an artificial log otter holt. Currently, no specific mitigation measures are proposed for otters. Given their proximity to the development and wide-ranging territory Natural England would recommend mitigation measures for otters are incorporated into the scheme. No draft licence application has been submitted for Natural England to review; given this, it has been assumed that the Applicant does not consider a licence for impacts to otters is necessary. Consider mitigation measures for impacts to otter due to evidence of activity in proximity to the development and otter’s wide ranging territory. Where licence need is identified, a draft licence application should be submitted to natural England for review. | Yellow | Natural England’s Wildlife Licensing Service (NEWLS) has reviewed Appendix 9F: Water Vole and Otter Report in relation to the East Midlands Gateway 2 proposals, and considers the approaches to be consistent with recognised good practice and the relevant NE standing advice for these species. With respect to water voles, the surveys have been undertaken in accordance with established best practice, as set out in The Water Vole Mitigation Handbook. The presence/absence surveys have been completed during the optimal survey season and appropriately spaced to account for potential seasonal variability in field sign detectability. The surveys have extended along the full length of relevant watercourses and included bankside habitats up to an appropriate distance. NEWLS is satisfied that the level of survey effort is proportionate and sufficient to inform an assessment of likely presence or absence within the affected areas. The absence of water vole field signs across all survey visits, considered alongside the lack of desk study records within the surrounding area, provides reasonable evidence to support the conclusions presented. On this basis, the interpretation that water voles are unlikely to be present within the surveyed sections of ditch D1 or D2 would seem valid. Provided there are no material changes in the habitat suitability prior to construction that might increase the likely presence of water voles, the proposal that a water vole mitigation licence is not currently required would appear reasonable. In relation to otters, NEWLS notes that surveys were undertaken following standard walkover methods, consistent with NE standing advice for otter surveys accompanying development proposals. The identification of sprainting activity along the Diseworth Brook Tributary confirms otter use of this watercourse, on land outside the Order Limits. The report appropriately interprets this evidence as indicative of commuting or foraging activity, rather than the presence of an otter holt or other place of rest or shelter affected by the proposals. Given that the Diseworth Brook Tributary will not be directly impacted by construction works, the proposals as described are unlikely to result in damage to, or disturbance of, an otter resting place. Consequently, on the information provided, the scheme does not appear to trigger the requirement for an otter mitigation licence. NEWLS welcomes the inclusion of enhancement measures, in particular the provision of an artificial log otter holt located within a low disturbance section of the riparian corridor. While not strictly required to mitigate direct impacts, the proposed holt represents a reasonable and proportionate enhancement measure that may provide additional resting opportunities for otters using the watercourse during construction and in the long term. Overall, Natural England considers that the survey work has been undertaken to an appropriate standard, the impact assessment is proportionate to the scale of works and level of risk identified, and the conclusions reached are supported by the evidence presented. NEWLS has no significant concerns with respect to the approaches proposed in relation to water voles and otters at this time. Email 12/06: FPCR confirmed "No licensable activities are anticipated in regards otter and water vole. " | Green
| BNG Requirement | draft DCO |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Gains can be secured through planning obligations, conservation covenants or requirements within the DCO. Natural England would welcome commitment in excess of 10% alongside the LEMP, to ensure the habitats are retained for the 30 years. | n/a | n/a | n/a | n/a | n/a
| DCO Requirement 10 | draft DCO |  | Green | n/a | n/a | n/a | n/a | n/a | n/a | Natural England welcome the inclusion of the LEMP as requirement 10 of the DCO. We welcome the commitment to manage the green infrastructure upon its completion, prior to occupancy, and for the lifetime of the authorised development. | Green | n/a | Green | n/a | Green
| DCO Requirement 11 | draft DCO |  | Amber | n/a | n/a | n/a | n/a | n/a | n/a | We welcome the inclusion of the CEMP as requirement 11 of the DCO and the commitment for no works to begin until an agreed phase specific CEMP has been completed. We note there is no mention of Silt Management Plan within the requirement. We recommend this is included to ensure no polluting activities from construction surface water run off occur to sensitive waterways linked to designated sites. This was included as an Appendix within the submitted CEMP (Document DCO 6.3A). As noted in NE3 and NE4. | Amber | n/a | Amber | No update. | Amber
| DCO Requirement 17 | draft DCO |  | Amber | n/a | n/a | n/a | n/a | n/a | n/a | We welcome the inclusion of requirement 17, which ensures both construction and operational surface water are managed in accordance with the Sustainable Drainage Statements through the use of SuDS. This includes the ongoing maintenance of the SuDS. The requirement should clarify that the ongoing monitoring and maintenance of the SuDS should be for the lifetime of the development. As noted in NE3 and NE4 | Amber | n/a | Amber | No update. | Amber
| DCO Requirement 28 | draft DCO |  | Green | n/a | n/a | n/a | n/a | n/a | n/a | We welcome the inclusion of requirement 28 to secure the community park prior to occupation and in perpetuity. | Green | n/a | Green | n/a | Green
NE3 | n/a | Internationally Designated Sites | Assessment of effects (C, O, D) | Green | It is noted that an assessment of potential impacts to designated sites is omitted from Chapter 9: Ecology & Biodiversity. A placeholder is included within the text which states ‘Section holder awaiting further consultation’ (paras. 9.5.21 and 9.5.37). Consequently, Natural England is unable to provide detailed advice regarding internationally designated sites based on the information provided in the PEIR. Instead, comments are provided on the Shadow Habitats Regulation Assessment (sHRA) (Appendix 9h) below. | Amber | New information has been added to the draft ES chapter regarding potential construction and operational phase impacts on internationally designated sites. Natural England agrees with the conclusion that no significant direct or indirect effects are anticipated on the River Mease SAC, due to the distance from the site and the lack of potential impact pathways. This is in line with the findings of the Shadow Habitats Regulations Assessment (sHRA) which Natural England agreed with as part of our Section 42 consultation response. The River Mease SAC is the only internationally designated site within the study area. Overall, Natural England agrees with the conclusions set out in ES Chapter 9: Ecology and Biodiversity regarding internationally designated sites. | Green | No change. | Green | No further comment. | Green | n/a | Green | n/a | Green
NE11 | n/a | Nationally Designated Landscapes | Nationally designated landscapes (C, O, D) | n/a | The proposed Scheme is not located within, or within the setting of, any nationally designated landscapes (National Parks or National Landscapes). As a result, Natural England has no specific comments to make on the further landscape implications of this proposal. We welcome the reference made to Natural England’s National Character Areas and advise that the Scheme should avoid impact to and, where possible, enhance local distinctiveness. | Green | No change. | Green | No change. | Green | The proposed projects are not located within, or within the setting of, any nationally designated landscapes (National Parks or National Landscapes). As a result, Natural England has no specific comments to make on the further landscape implications of this proposal. No further detailed comments are given. | n/a | n/a | n/a | n/a | n/a
NE6 | n/a | Nationally Designated Sites | SSSI Impact Risk Zones (C, O, D) | n/a | It is welcomed that reference to SSSI IRZs is made in para. 9.4.7. However, the statements are currently vague and do not determine which IRZs are triggered for each individual designated site. It is requested that the triggered IRZs are listed by site, along with a justification for which sites are subsequently screened in or out of the EIA. | Yellow | Since the PEIR was reviewed during the Section 42 consultation, further detail has been added to the draft ES chapter regarding the specific SSSI Impact Risk Zones (IRZs) that are triggered by the development. This includes the specific characteristics of the scheme that are considered relevant for each SSSI IRZ. The update is welcomed by Natural England. | Green | No change. | Green | No further comment. | n/a | n/a | n/a | n/a | n/a
NE7 | n/a | Nationally Designated Sites | Future baseline (C, O, D) | n/a | It is noted that a statement has been added in para. 9.4.20 that the condition of statutory sites would be reasonably expected to decline over time as pollution accumulates and desirable management interventions are not fulfilled. Natural England request further clarification on this point, for example which site(s) this statement relates to, and what data/ information has been used to inform the statement. | Yellow | Further clarification has been added to the Future Baseline section of the ES chapter, providing an explanation as to the existing pressures on designated sites and clarifying that the future baseline assumes habitats would be managed to maintain their condition (the exception being the ash trees which are declining due to ash dieback). The additional information is welcomed. | Green | No change. | Green | No further comment. | n/a | n/a | n/a | n/a | n/a
(1) |  | https://www.gov.uk/guidance/ancient-woodland-ancient-trees-and-veteran-trees-advice-for-making-planning-decisions